## Sheet1
PENNSYLAVNIA RAPID BRIDGE PROJECT - PWKP
Line Number | Early Completion (Y/N) | JV # | Bridge Key # | MPMS # | BMS # | District | County | Location | Feature Carried | Feature Intersected | Municipality Code | Latitude | Longitude | Utility Type | Utility Owner | Utility Owner Contact | Utility Location | Overhead or Underground | Size | D-419 Utility Relocation Classification | Anticipated Construction Start Date
1a | -- | 1 | 12879 | 97120 | 20000604100000 | 1 | Crawford | VERNON TOWNSHIP | SR 6,GRAND ARMY HY | OVER TR CONNEAUT LK OUT | 20/230 - VERNON | 41.6151 | -80.2379 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2016-06-06
1b | -- | 1 | 12879 | 97120 | 20000604100000 | 1 | Crawford | VERNON TOWNSHIP | SR 6,GRAND ARMY HY | OVER TR CONNEAUT LK OUT | 20/230 - VERNON | 41.6151 | -80.2379 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com | Penelec is not affected by this project. Outside the scope |  |  |  | 2016-06-06
2a | -- | 2 | 12902 | 90155 | 20000608400273 | 1 | Crawford | CAMBRIDGE TOWNSHIP | SR 6,LAKES TO SEA | OVER FRENCH CREEK TRIB #3 | 20/204 - CAMBRIDGE | 41.7962 | -80.0781 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | Conflict. Lines Nearby | UG |  |  | 2016-08-05
2b | -- | 2 | 12902 | 90155 | 20000608400273 | 1 | Crawford | CAMBRIDGE TOWNSHIP | SR 6,LAKES TO SEA | OVER FRENCH CREEK TRIB #3 | 20/204 - CAMBRIDGE | 41.7962 | -80.0781 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | CONFLICT. LINES NEARBY. | OH |  |  | 2016-08-05
2c | -- | 2 | 12902 | 90155 | 20000608400273 | 1 | Crawford | CAMBRIDGE TOWNSHIP | SR 6,LAKES TO SEA | OVER FRENCH CREEK TRIB #3 | 20/204 - CAMBRIDGE | 41.7962 | -80.0781 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com | DID NOT RESPOND | OH |  |  | 2016-08-05
2d | -- | 2 | [11 empty] | Comm | Armstrong | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-05
2e | -- | 2 | [11 empty] | Comm | ZITO MEDIA COMMUNICATIONS LLC | TODD MCMANUS, todd.mcmanus@zitomedia.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-05
2f | -- | 2 | [11 empty] | Comm | COAXIAL CABLE TELEVISION CORPORATION | CHRIS LOVELL, clovell@coaxpa.com | Possible Conflict | OH |  |  | 2016-08-05
3 | -- | 3 | 13084 | 97121 | 20028501000629 | 1 | Crawford | NORTH SHENANGO TOWNSHIP | SR 285,LICKING ST | OVER BENNETT RUN | 20/213 - NORTH SHENANGO | 41.6021 | -80.4312 |  | all facilities responded clear per one call | [5 empty] | 2017-07-10
4a | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | Gas | Laurel Mountain Midstream LLC | Delbert Woloski, 724-301-2499 , delbert.woloski@williams.com | Marked 12/29/14. Gas line on edge of construction easement | UG |  |  | 2016-05-12
4b | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 |  | Richmond TWP | Charlie Hartman, 814-967-3822, richmondtwprc@windstream.net | Clear No Conflict. Phone call 8/6/15 | UG |  |  | 2016-05-12
4c | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | Comm | Verizon North LLC | Gary Goss, 814-440-2443, Gary.Goss@cyient.com Eric Rodrigues, 814 871-2317, eric.rodrigues@verizon.com | CONFLICT. LINES NEARBY. | OH |  |  | 2016-05-12
4d | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | Comm | Armstrong | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Clear. No Conflict | OH |  |  | 2016-05-12
4e | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | Gas | Atlas America, Inc | Cory Masson, 724-662-0300 x108, cmasson@atlasenergy.com | Clear No Conflict | OH |  |  | 2016-05-12
4f | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | Elect | Northwestern Rural Electric Co-op | Steve Miller, 814-398-5313, smiller@northwesternrec.com | Clear No Conflict. Overhead Lines outside construction area | OH |  |  | 2016-05-12
5a | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | Storm | Hydetown Borough | Pat Myer, 814-827-1617, hydetownboro@yahoo.com | MARKED on 1/20/15. have storm drains come out at the base of the bridge | UG |  |  | 2016-05-23
5b | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | Comm | Armstrong | Mike Schuwerk, 814-333-6731x224, mschuwerk@agoc.com | CONFLICT. LINES NEARBY. | OH |  |  | 2016-05-23
5c | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | Conflict. Lines Nearby | UG |  |  | 2016-05-23
5d | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 |  | Pennsylvania Electric Company | Charles Vroman, 814-676-7540, cvroman@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-05-23
5e | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com | CONFLICT. LINES NEARBY. | OH |  |  | 2016-05-23
5f | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | Comm | Verizon | Gary Goss, 814-440-2443, Gary.Goss@cyient.com Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | CONFLICT. LINES NEARBY. | OH |  |  | 2016-05-23
5g | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | Comm | Lumos Networks | Bill Beaver, O: 724-216-9015, C: 412-992-7655, beaverw@lumosnet.com | CONFLICT. LINES NEARBY. | OH |  |  | 2016-05-23
6a | -- | 6 | 13027 | 89176 | 20088601600750 | 1 | Crawford | WOODCOCK BOROUGH | SR 886,MAIN STREET | OVER GRAVEL RUN | 20/414 - WOODCOCK | 41.7519 | -80.0878 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal. Do not dig prior to being contacted by National Fuel. | UG |  |  | 2017-03-27
6b | -- | 6 | 13027 | 89176 | 20088601600750 | 1 | Crawford | WOODCOCK BOROUGH | SR 886,MAIN STREET | OVER GRAVEL RUN | 20/414 - WOODCOCK | 41.7519 | -80.0878 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | CONFLICT. LINES NEARBY. |  |  |  | 2017-03-27
6c | -- | 6 | 13027 | 89176 | 20088601600750 | 1 | Crawford | WOODCOCK BOROUGH | SR 886,MAIN STREET | OVER GRAVEL RUN | 20/414 - WOODCOCK | 41.7519 | -80.0878 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com | DID NOT RESPOND |  |  |  | 2017-03-27
7a | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com James Kennedy, 716-857-7368, kennedyj@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2016-07-19
7b | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | Gas | KASTLE RESOURCES ENTERPRISES INC | Jesse Welcheck, 814-602-6231, jwelcheck25@gmail.com | DID NOT RESPOND | UG |  |  | 2016-07-19
7c | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | sanitary | SAEGERTOWN AREA SEWER AUTHORITY | Matt Handley, 724-814-7503, matthew.handley@veolia.com | DID NOT RESPOND | UG |  |  | 2016-07-19
7d | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | Comm | Armstrong | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Conflict. Lines Nearby | OH |  |  | 2016-07-19
7e | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | Comm | WINDSTREAM COMMUNICATIONS | Linda Gilligan, 814-333-0285, linda.gilligan@windstream.net | DID NOT RESPOND | OH |  |  | 2016-07-19
7f | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | Elect | Northwestern Rural Electric Co-op | Steve Miller, 814-398-5313, smiller@northwesternrec.com | DID NOT RESPOND | OH |  |  | 2016-07-19
8 | -- | 8 | 16373 | 1140 | 25401100800860 | 1 | Erie | MILL CREEK TOWNSHIP | SR 4011,GRUBB ROAD | OVER WALNUT CREEK | 25/213 - MILLCREEK | 42.0566 | -80.1481 | Gas | National Fuel/National Fuel Supply Erie | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | Design Conflict. Please send plans to: James Kennedy National Fule Gas 6363 Main St Williamsville, NY 14221. | UG |  |  | 2017-09-08
9 | -- | 9 | 17195 | 74663 | 27006201302194 | 1 | Forest | TIONESTA BOROUGH | SR 62,ELM STREET | OVER TUBBS RUN | 27/401 - TIONESTA | 41.5088 | -79.4497 | Comm | Armstrong | Keith Smith, ksmith@agoc.com | CONFLICT. LINES NEARBY. |  |  |  | 2017-03-27
10a | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2016-05-23
10b | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | Comm | Armstrong | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Clear No Conflict | OH |  |  | 2016-05-23
10c | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | Comm | Verizon North LLC | Sue Hoover, susan.a.hoover@verizon.com Barbara Witkowski, barb.witkowski@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-05-23
10d | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 |  | Hickory TWP | George Oliver, 814-516-5134 | Clear No Conflict | UG |  |  | 2016-05-23
10e | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | Elect | Warren Electric Cooperative | Christopher Evans, 814 563-7548, cevans@warrenec.coop | Conflict. Lines Nearby | OH |  |  | 2016-05-23
11a | -- | 11 | 17208 | 93595 | 27066600900000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5858 | -79.3397 | Comm | ARMSTRONG | Keith Smith, ksmith@agoc.com | Conflict. Lines Nearby |  |  |  | 2017-06-05
11b | -- | 11 | 17208 | 93595 | 27066600900000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5858 | -79.3397 |  | Hickory TWP | Nicholas Melnick, 814-676-5805, hickorytwp@verizon.net | Did Not Respond |  |  |  | 2017-06-05
11c | -- | 11 | 17208 | 93595 | 27066600900000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5858 | -79.3397 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | Conflict. Lines Nearby. |  |  |  | 2017-06-05
12a | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | Comm | Verizon North LLC | Sue Hoover, susan.a.hoover@verizon.com | CONFLICT. LINES NEARBY. | OH |  |  | 2017-05-23
12b | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | Comm | Armstrong | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | CONFLICT. LINES NEARBY. | OH |  |  | 2017-05-23
12c | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | Elect | Warren Electric Cooperative | Christopher Evans, 814 563-7548, cevans@warrenec.coop | Conflict. Lines Nearby | OH |  |  | 2017-05-23
12d | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 |  | Hickory TWP | George Oliver, 814-516-5134 | Clear No Conflict | UG |  |  | 2017-05-23
12d | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | Gas | Unknown |  | Abandoned gas line. Unknown Owner. | UG |  |  | 2017-05-23
13a | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | Comm | ARMSTRONG | Keith Smith, ksmith@agoc.com | Conflict. Lines Nearby. |  |  |  | 2016-12-05
13b | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | Gas | Vista Resources Inc | 412-833-8884, info@vistaresources.com | Field Marked. | UG |  |  | 2016-12-05
13c | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | Engineering Completed - A PDF File or Marked Up Plans were sent to the requestor. Please see map located in the one call folder for the bridge in sharepoint. | Both |  |  | 2016-12-05
13d | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Please see map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2016-12-05
14a | -- | 14 | 25858 | 1686 | 43031801500622 | 1 | Mercer | LACKAWANNOCK TOWNSHIP | SR 318,W.MDLSX-MRC | OVER LT NESHANNOCK CK BR | 43/212 - LACKAWANNOCK | 41.1918 | -80.3903 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | Marked 2/9/15. National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Do not dig prior to being contacted by National Fuel. | UG |  |  | 2016-07-25
14b | -- | 14 | 25858 | 1686 | 43031801500622 | 1 | Mercer | LACKAWANNOCK TOWNSHIP | SR 318,W.MDLSX-MRC | OVER LT NESHANNOCK CK BR | 43/212 - LACKAWANNOCK | 41.1918 | -80.3903 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com | Did Not Respond | UG |  |  | 2016-07-25
14c | -- | 14 | 25858 | 1686 | 43031801500622 | 1 | Mercer | LACKAWANNOCK TOWNSHIP | SR 318,W.MDLSX-MRC | OVER LT NESHANNOCK CK BR | 43/212 - LACKAWANNOCK | 41.1918 | -80.3903 | Elect | Verizon North LLC | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Did Not Respond | OH |  |  | 2016-07-25
14d | -- | 14 | 25858 | 1686 | 43031801500622 | 1 | Mercer | LACKAWANNOCK TOWNSHIP | SR 318,W.MDLSX-MRC | OVER LT NESHANNOCK CK BR | 43/212 - LACKAWANNOCK | 41.1918 | -80.3903 | Elect | Armstrong | Dick Ross, 724-458-7165 x 224, dross@agoc.com | Did Not Respond | OH |  |  | 2016-07-25
14e | -- | 14 | 25858 | 1686 | 43031801500622 | 1 | Mercer | LACKAWANNOCK TOWNSHIP | SR 318,W.MDLSX-MRC | OVER LT NESHANNOCK CK BR | 43/212 - LACKAWANNOCK | 41.1918 | -80.3903 | Elect | TIME WARNER CABLE | Doug Lawrentz, 330-472-8960, doug.lawrentz@twcable.com | Conflict. Lines Nearby | OH |  |  | 2016-07-25
15 | -- | 15 | 26008 | 58092 | 43302001700000 | 1 | Mercer | JEFFERSON TOWNSHIP | SR 3020,LAMOR ROAD | OVER LACKAWANNOCK CREEK | 43/211 - JEFFERSON | 41.246 | -80.3028 |  | all facilities responded clear per one call | [5 empty] | 2017-05-30
16a | -- | 16 | 33765 | 93160 | 60042702200000 | 1 | Venango | PLUM TOWNSHIP | SR 427 | OVER SUGAR CREEK TRIB | 60/214 - PLUM | 41.5748 | -79.8654 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | Verizon has a 25pr buried copper cable along the West side of SR 427. You will need to have this marked to determine the distance from the center line. Any construction plans involving Verizon should be sent to Barbara Witkowski | UG |  |  | 2017-02-24
16b | -- | 16 | 33765 | 93160 | 60042702200000 | 1 | Venango | PLUM TOWNSHIP | SR 427 | OVER SUGAR CREEK TRIB | 60/214 - PLUM | 41.5748 | -79.8654 | Gas | Range Resources | Brian Sprague, 814-425-3100, bsprague@rangeresources.com | Marked | UG |  |  | 2017-02-24
16c | -- | 16 | 33765 | 93160 | 60042702200000 | 1 | Venango | PLUM TOWNSHIP | SR 427 | OVER SUGAR CREEK TRIB | 60/214 - PLUM | 41.5748 | -79.8654 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com | DID NOT RESPOND |  |  |  | 2017-02-24
17a | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | Comm | ARMSTRONG | Keith Smith, ksmith@agoc.com | Conflict. Lines Nearby. |  |  |  | 2017-06-01
17b | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | Gas | UGI Central Penn Gas | Roy Carr (570) 829-8967 | Did Not Respond | UG |  |  | 2017-06-01
17c | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | Engineering Completed - A PDF File or Marked Up Plans were sent to the requestor. Please see map located in the one call folder for the bridge in sharepoint. | Both |  |  | 2017-06-01
17d | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 |  | Rockland TWP | 814-498-2768 | Did Not Respond |  |  |  | 2017-06-01
17e | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2017-06-01
18a | -- | 18 | 33956 | 97457 | 61000603502233 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER WINTROTH RUN | 61/201 - BROKENSTRAW | 41.8386 | -79.3614 | sanitary | BROKENSTRAW VALLEY AREA AUTHORITY | Joel Turk, bvaa@verizon.net, Beverly Moore, 814-563-7681 | marked. Gravity sewer lines run parallel to Rt. 6 on the north side | UG |  |  | 2017-02-21
18b | -- | 18 | 33956 | 97457 | 61000603502233 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER WINTROTH RUN | 61/201 - BROKENSTRAW | 41.8386 | -79.3614 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | CONFLICT. LINES NEARBY. | UG |  |  | 2017-02-21
19a | -- | 19 | 33957 | 2438 | 61000603900000 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER MEAD RUN | 61/201 - BROKENSTRAW | 41.8471 | -79.3363 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | Response 1 on 2/4/15: National Fuel has facilities in the area of your One Call Design Request. Forward design drawings to James Kennedy, Engineering Dept. 6363 Main Street, Williamsville, NY 14221, Email: KennedyJ@natfuel.com, Fax: (716) 857-7456 or call (716) 857-7368. Response 2 on 2/9/15: NO gas lines in area of concern. see attached map in one call folder in sharepoint | UG |  |  | 2017-03-08
19b | -- | 19 | 33957 | 2438 | 61000603900000 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER MEAD RUN | 61/201 - BROKENSTRAW | 41.8471 | -79.3363 | sanitary | BROKENSTRAW VALLEY AREA AUTHORITY | Joel Turk, bvaa@verizon.net, Beverly Moore, 814-563-7681 | Responsed that this work shouldn’t come close to their lines. There is a map of their utilties located in the one call folder for this bridge on sharepoint | UG |  |  | 2017-03-08
19c | -- | 19 | 33957 | 2438 | 61000603900000 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER MEAD RUN | 61/201 - BROKENSTRAW | 41.8471 | -79.3363 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com | DID NOT RESPOND |  |  |  | 2017-03-08
20a | -- | 20 | 33982 | 2546 | 61000608200000 | 1 | Warren | SHEFFIELD TOWNSHIP | SR 6,GRAND ARMY HY | OVER FOUR MILE RUN | 61/218 - SHEFFIELD | 41.7256 | -79.0548 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby | UG |  |  | 2017-06-02
20b | -- | 20 | 33982 | 2546 | 61000608200000 | 1 | Warren | SHEFFIELD TOWNSHIP | SR 6,GRAND ARMY HY | OVER FOUR MILE RUN | 61/218 - SHEFFIELD | 41.7256 | -79.0548 | Gas | National Fuel/National Fuel Supply Roystone | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | Field Marked. National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal. | UG |  |  | 2017-06-02
20c | -- | 20 | 33982 | 2546 | 61000608200000 | 1 | Warren | SHEFFIELD TOWNSHIP | SR 6,GRAND ARMY HY | OVER FOUR MILE RUN | 61/218 - SHEFFIELD | 41.7256 | -79.0548 | Gas | SLT Production LLC FRMLY Sheffield Land | 814-723-8650, 13 Six Mile Road Sheffield PA 16347 | Did Not Respond | UG |  |  | 2017-06-02
21a | -- | 21 | 34001 | 2580 | 61002705203359 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 27,NORTH MAIN | OVER HAZELTINE HOLLOW RUN | 61/201 - BROKENSTRAW | 41.904 | -79.3447 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | National Fuel has facilities in the area of your One Call Design Request. Forward design drawings to James Kennedy, Engineering Dept. 6363 Main Street, Williamsville, NY 14221, Email: KennedyJ@natfuel.com, Fax: (716) 857-7456 or call (716) 857-7368. see attached map in one call folder in sharepoint for approx location if exact locations are needed for design purposes, we suggest that you utilize a reputable locating/vacuum excavation company familiar with Subsurface Utility Engineering techniques. Three to ten days prior to the start of construction, the excavator must call the Pennsylvania One Call System to request a locate. The contractor must use prudent techniques, such as hand dug test holes, to ascertain the precise locations of the lines, whenever they are working in the tolerance zone (within 18"). This is required for all types of mechanical excavation, including trenchless techniques such as directional drilling. Due to locating inaccuracies of pipelines as well as drill heads, special requirements will apply if using trenchless technology within 6' of a gas line. | UG |  |  | 2016-08-12
21b | -- | 21 | 34001 | 2580 | 61002705203359 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 27,NORTH MAIN | OVER HAZELTINE HOLLOW RUN | 61/201 - BROKENSTRAW | 41.904 | -79.3447 | sanitary | BROKENSTRAW VALLEY AREA AUTHORITY | Joel Turk, bvaa@verizon.net, Beverly Moore, 814-563-7681 | marked. Sanitary on hazeltine road crossing rt. 27. Also sugar grove twp has a sanitary line on hazeltine that crosses rt. 27 and connects into the brokenstraw line | UG |  |  | 2016-08-12
21c | -- | 21 | 34001 | 2580 | 61002705203359 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 27,NORTH MAIN | OVER HAZELTINE HOLLOW RUN | 61/201 - BROKENSTRAW | 41.904 | -79.3447 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com | DID NOT RESPOND |  |  |  | 2016-08-12
22a | -- | 22 | 34056 | 2548 | 61012700902381 | 1 | Warren | TRIUMPH TOWNSHIP | SR 127,BABLIN HILL | OVER GORDON RUN | 61/222 - TRIUMPH | 41.68 | -79.4221 | Gas | National Fuel/National Fuel Supply Warren | James Kennedy, kennedyj@natfuel.com, 716-857-7368 | Design Conflict. Please send plans to: James Kennedy National Fuel Gas 6363 Main Street Williamsville NY 14221 | UG |  |  | 2017-08-21
22b | -- | 22 | 34056 | 2548 | 61012700902381 | 1 | Warren | TRIUMPH TOWNSHIP | SR 127,BABLIN HILL | OVER GORDON RUN | 61/222 - TRIUMPH | 41.68 | -79.4221 | Gas | OZ Gas LTD | 814-484-0270 | Field Marked. | UG |  |  | 2017-08-21
22c | -- | 22 | 34056 | 2548 | 61012700902381 | 1 | Warren | TRIUMPH TOWNSHIP | SR 127,BABLIN HILL | OVER GORDON RUN | 61/222 - TRIUMPH | 41.68 | -79.4221 |  | Tidioute Boro/SW Warren County Municipal Auth | 814-484-7424, tboro@tidioute.org | Did Not Respond |  |  |  | 2017-08-21
23a | -- | 23 | 34077 | 84954 | 61095701700981 | 1 | Warren | FREEHOLD TOWNSHIP | SR 957 | OVER LITTLE BROKENSTRAW | 61/210 - FREEHOLD | 41.9515 | -79.4433 | Gas | Enervest Operating LLC | 304-343-5505 | Conflict. Lines Nearby. | UG |  |  | 2017-05-18
23b | -- | 23 | 34077 | 84954 | 61095701700981 | 1 | Warren | FREEHOLD TOWNSHIP | SR 957 | OVER LITTLE BROKENSTRAW | 61/210 - FREEHOLD | 41.9515 | -79.4433 | Gas | National Fuel/National Fuel Supply Warren | James Kennedy, kennedyj@natfuel.com, 716-857-7368 | Design Conflict. Please send plans to: James Kennedy National Fuel Gas 6363 Main Street Williamsville NY 14221 | UG |  |  | 2017-05-18
24a | -- | 24 | 34169 | 97452 | 61301000600428 | 1 | Warren | SPRING CREEK TOWNSHIP | SR 3010,SPRING CK | OVER WHITNEY RUN | 61/220 - SPRING CREEK | 41.846 | -79.5687 | Comm | Verizon North LLC | Linda Rohleder, Linda.Rohleder@cyient.com Eric Rodrigues, 814 871-2317, eric.rodrigues@verizon.com | Not Affected | UG |  |  | 2016-03-30
24b | -- | 24 | 34169 | 97452 | 61301000600428 | 1 | Warren | SPRING CREEK TOWNSHIP | SR 3010,SPRING CK | OVER WHITNEY RUN | 61/220 - SPRING CREEK | 41.846 | -79.5687 | Elect | Warren Electric Cooperative | Christopher Evans, 814 563-7548, cevans@warrenec.coop | Not Affected | OH |  |  | 2016-03-30
25a | -- | 25 | 8831 | 85095 | 12012000400000 | 2 | Cameron | TRUMAN | SR 120-PA 120 | BIG RUN | 12/205 - SHIPPEN | 41.4708 | -78.3911 | GAS | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel was unable to determine the location of the proposed excavation. Please define the work site better. Use white paint if possible. Re-notify the One-Call center. | UG |  |  | 2017-05-12
25b | -- | 25 | 8831 | 85095 | 12012000400000 | 2 | Cameron | TRUMAN | SR 120-PA 120 | BIG RUN | 12/205 - SHIPPEN | 41.4708 | -78.3911 | Elect | West Penn Power | Zach Reedy (engineering supervisor), zreedy@firstenergycorp.com, 724-548-3578 | Conflict. Lines nearby. (one call) Per initial site visit there is OH electric with poles 30 ft offset to right (looking east). Pole marking; WPP CO 750059, SAC-EM #1, OSMOSE 2011 MITC-Fume | OH |  |  | 2017-05-12
26a | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | sanitary | Haines Woodward Mun Auth | Susan Coffman, 814-349-2420, 814-574-6790 (cell), 184 Woodward Gap Road, Aaronsburg, PA 16820 | Conflict. Lines nearby per one call. | UG |  |  | 2017-06-13
26b | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | Comm | Northeastern ITS | John Bruce, 877-601-7662, john.bruce@spreadnetworks.com; William Hosack, william.hosack@spreadnetworks.com | Design Conflict. Please send plans to Nick Williams, Northeastern ITS, LLC C/O Williams Comm, 5524 Bee Cave Road Suite C-1, Austin TX 78746.Per initial site visit there is OH elec/phone/catv on right (Facing east). Pole #s from east to west; "West Penn Systems 76728", "WPPCo 593293 and CEI 925". Confirmed that they own the UG fiber line | UG |  |  | 2017-06-13
26c | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | Elect | West Penn Power | Robert Rhodes, rwrhodes@firstenergycorp.com, 2800 East College Avenue, State College, PA 16801, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com,724-548-3578 | Conflict. Lines nearby (one call). Per initial site visit there is OH elec/phone/catv on right (Facing east). Pole #s from east to west; "West Penn Systems 76728", "WPPCo 593293 and CEI 925". | OH |  |  | 2017-06-13
26d | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 |  | Haines TWP | Susan Wenrick, 814-349-8193 | DID NOT RESPOND per one call. Spoke on phone on 12/1/15 and they do not have facilities in the area. |  |  |  | 2017-06-13
26e | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit there is OH elec/phone/catv on right (Facing east). Pole #s from east to west; "West Penn Systems 76728", "WPPCo 593293 and CEI 925". Not their facilities |  |  |  | 2017-06-13
26f | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | Comm | Verizon Pennsylvania LLC | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com, 250 S Allen Street, State College, PA 16801 | Per initial site visit there is OH elec/phone/catv on right (Facing east). Pole #s from east to west; "West Penn Systems 76728", "WPPCo 593293 and CEI 925". | OH |  |  | 2017-06-13
27a | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | wtr | Bellefonte Borough | Ralph Stewart, 814-355-1501, rstewart@bellefonte.net | marked per one call. Per initial site visit there is UG water line that crosses stream about 35' left (looking north). There is a meter behind guardrail on northwest corner. | UG |  |  | 2017-02-13
27b | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | Gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com, Nelson White (Manager) nwhite@nisource.com, 150 Hillside Drive, Bethel Park, PA 15102 | Conflict. Lines nearby (per one call). Per initial site visit there is gas upstream parallel to road under stream marker near right (looking north). | UG |  |  | 2017-02-13
27c | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | sanitary | Spring Benner Walker Joint Auth | Warren Miller, wmiller@sbwja.com | Conflict. Lines nearby. Direct contact to follow by facility owner. if you need this marked in the field please call our office at 814-355-4778. See as-builts located in the on-call folder on sharepoint. (per one call) Per initial site visit there is a pump station just south of bridge on the east side of road. Also sanitary line going under stream on left side (looking north) west of UG phone and water and goes south to MH at Log Cabin Motors and then crosses road south of bridge towards the pump station. | UG |  |  | 2017-02-13
27d | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | Elect | West Penn Power | Jeffrey (Jeff) Miller, jmill20@firstenergy.com, 814-231-5320, 2800 East College Avenue, State College, Pennsylvania 16801; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | Conflict. Lines nearby (per one call). OH elec/phone/catv on right (looking north). | OH |  |  | 2017-02-13
27e | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Clear per one call. Per initial site visit UG phone (3 lines?) crossing stream on left (looking north) and then goes to vault south of bridge at Log Cabin Motors. OH elec/phone/catv on right (looking north). Also OH phone service that crosses bridge from northeast corner to southwest corner. | Both |  |  | 2017-02-13
27f | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | OH elec/phone/catv on right (looking north) | OH |  |  | 2017-02-13
28a | -- | 28 | 9576 | 85135 | 14100200501555 | 2 | Centre | YARNELL | SR 1002 | LITTLE MARSH CREEK | 14/202 - BOGGS | 40.9992 | -77.8114 | Elect | West Penn Power | Jeffrey (Jeff) Miller, jmill20@firstenergy.com, 814-231-5320, 2800 East College Avenue, State College, Pennsylvania 16801; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | Conflict. Lines nearby (per one call). Per initial site visit there is OH e/t crosses bridge from pole 24' north of bridge on the west to pole 60' south of sub station east of road (pole tag L7-112). OH elec comes from northwest and crosses stream and then the road south of the bridge to the pole with tag L7-112. OH e/t/catv runs east-west from pole tag L7-112 south of bridge. Sub station south of bridge on east side of road. | OH |  |  | 2016-08-31
28b | -- | 28 | 9576 | 85135 | 14100200501555 | 2 | Centre | YARNELL | SR 1002 | LITTLE MARSH CREEK | 14/202 - BOGGS | 40.9992 | -77.8114 | Comm | Verizon Pennsylvania LLC | Paul Deering, 814-231-6507, paul.e.deering@verizon.com, 250 S. Allen Street State College, PA 16801 | Clear per one call. Per initial site visit there is OH e/t crosses bridge from pole 24' north of bridge on the west to pole 60' south of sub station east of road (pole tag L7-112). OH e/t/catv runs east-west from pole tag L7-112 south of bridge. | OH |  |  | 2016-08-31
28c | -- | 28 | 9576 | 85135 | 14100200501555 | 2 | Centre | YARNELL | SR 1002 | LITTLE MARSH CREEK | 14/202 - BOGGS | 40.9992 | -77.8114 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | OH e/t/catv runs east-west from pole tag L7-112 south of bridge. Sub station south of bridge on east side of road. Not their facilities |  |  |  | 2016-08-31
29a | -- | 29 | 9577 | 81359 | 14100200801726 | 2 | Centre | YARNELL | SR 1002 | BRANCH LITTLE MARSH CR | 14/202 - BOGGS | 41.0091 | -77.7908 | Elect | West Penn Power | Jeffrey (Jeff) Miller, jmill20@firstenergy.com, 814-231-5320, 2800 East College Avenue, State College, Pennsylvania 16801; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | Conflict. Lines nearby (per one call). Per initial site visit OH elec/phone far right of bridge (looking east). Pole is located west of bridge on south side of the road near the end of the guardrail. | OH |  |  | 2017-08-01
29b | -- | 29 | 9577 | 81359 | 14100200801726 | 2 | Centre | YARNELL | SR 1002 | BRANCH LITTLE MARSH CR | 14/202 - BOGGS | 41.0091 | -77.7908 | Gas | Dominion Transmission Inc Luthersburg | Russell (Russ) Gregory, 814-583-1007, russell.l.gregory@dom.com; Andrew (Andy) Haag, Andrew.P.Haag@dom.com, 814-771-3590 | DID NOT RESPOND per one call. Per initial site visit didn’t see any indication of gas |  |  |  | 2017-08-01
29c | -- | 29 | 9577 | 81359 | 14100200801726 | 2 | Centre | YARNELL | SR 1002 | BRANCH LITTLE MARSH CR | 14/202 - BOGGS | 41.0091 | -77.7908 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH elec/phone far right of bridge (looking east). Pole is located west of bridge on south side of the road near the end of the guardrail. | OH |  |  | 2017-08-01
30 | -- | 30 | 9679 | 2893 | 14201300100000 | 2 | Centre | 2 MI NE COBURN | ON TSR 508 | PINE CREEK | 14/208 - HAINES | 40.8819 | -77.4198 | Elect | West Penn Power | Jeffrey (Jeff) Miller, jmill20@firstenergy.com, 814-231-5320, 2800 East College Avenue, State College, Pennsylvania 16801; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | Conflict. Lines nearby (per one call). Per initial site visit no utilities were visible |  |  |  | 2017-07-05
31a | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | Elect | West Penn Power | Jeffrey (Jeff) Miller, jmill20@firstenergy.com, 814-231-5320, 2800 East College Avenue, State College, Pennsylvania 16801; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | Conflict. Lines nearby per one call. Per initial site visit there is OH power/phone/catv on left (looking north) directly adjacent to bridge and road. Pole directly behind guardrail just north of bridge has an aerial crossing diagonal across road to house on east side of road north of bridge, a crossing to house on west side of road north of pole, and a crossing to house south of bridge on right (facing north). | OH |  |  | 2017-05-15
31b | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit there is OH power/phone/catv on left (looking north) directly adjacent to bridge and road. Pole directly behind guardrail just north of bridge has an aerial crossing diagonal across road to house on east side of road north of bridge, a crossing to house on west side of road north of pole, and a crossing to house south of bridge on right (facing north). | OH |  |  | 2017-05-15
31c | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit there is OH power/phone/catv on left (looking north) directly adjacent to bridge and road. Pole directly behind guardrail just north of bridge has an aerial crossing diagonal across road to house on east side of road north of bridge, a crossing to house on west side of road north of pole, and a crossing to house south of bridge on right (facing north). | OH |  |  | 2017-05-15
31d | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | wtr | Port Matilda Bourough | Vance Barndt, 814-692-0092, cell 814-441-7777 | Conflict. Lines Nearby per one call. Also per initial site visit water meter located. | UG |  |  | 2017-05-15
32a | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Conflict. Lines nearby per one call. Per site visit OH phone/catv 5 ft to right (looking north). This is not their facilities. Suggested it may be country cable (814-359-3161) |  |  | NA | 2016-03-23
32b | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | sanitary | Port Matilda Borough Auth | Tim Estright (at the plant), 814-692-7513, 171 Bradford Drive, Port Matilda PA 16870; engineering consulant, Thomas Holleran, 814-574-0191, tholleran@hrg-inc.com | Conflict. Lines nearby per one call. Low pressure sewer adjacent to bridge. Approx. 15-20 feet north of bridge. See as-builts located in the on-call folder on sharepoint. Per initial site visit sanitary vaults left and right at zendt lane (pads are 5'x6'). This is about 2500 ft from bridge so need to confirm if it crosses bridge. | UG | 3" | Not affected | 2016-03-23
32c | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | Elect | West Penn Power | Jeffrey (Jeff) Miller, jmill20@firstenergy.com, 2800 East College Avenue, State College, Pennsylvania 16801; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | Conflict. Lines nearby per one call. Per site visit OH power 5 ft to right (looking north). | OH |  | Not affected | 2016-03-23
32d | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | Comm | Windstream | Jay Knight, Jay.Knight@windstream.com, 814-272-2648, 441 Science Park Road, State College, PA 16827 | DID NOT RESPOND per one call. Per site visit OH phone 5 ft to right (looking north). The poles are next to the OH power poles. Phone on separate pole at crossing but positioned next to other pole.Phone line crosses road about 180' north of bridge. | OH |  | Not affected | 2016-03-23
32e | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | Comm | Country Cable | Lee Dorman, 814-359-3161, dormanrep@aol.com | Per Comcast the cable facilities may be Country Cable. Verified that it isnt Country Cable. Verified all of the lines are owned by Windstream |  |  | NA | 2016-03-23
32f | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | Based on research online to confirm cable company. Confirmed on phone that it isnt tele-media or nittany media. It is all windstream. |  |  |  | 2016-03-23
33a | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | sanitary | Mid-Centre County Auth | Chad A. Bechdel, 814-355-8435, mccaio@hotmail.com | DESIGN CONFLICT. PLEASE SEND PLANS TO, LAWRENCE CHERRY MID CENTRE COUNTY AUTHORITY 296 MID-CENTRE LN PO BOX 811, MILESBURG PA 16853 (per one call) | UG |  |  | 2017-05-15
33b | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | Elect | West Penn Power | Jeffrey (Jeff) Miller, jmill20@firstenergy.com, 814-231-5320, 2800 East College Avenue, State College, Pennsylvania 16801; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | Conflict. Lines nearby per one call. Per initial site visit there is OH elec about 3-1 ft left (looking east). OH electric that crosses road east of bridge. | OH |  |  | 2017-05-15
33c | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | sanitary | Unionville Borough | Sherry A. Lucas, 814-355-4837, uboro@vicon.net | DID NOT RESPOND per one call. |  |  |  | 2017-05-15
33d | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH phone/catv 0-1 ft rt of bridge (looking east). OH phone/catv that crosses bridge from pole just east of bridge on south side of road and heads northwest. | OH |  |  | 2017-05-15
33e | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH phone/catv 0-1 ft rt of bridge (looking east). OH phone/catv that crosses bridge from pole just east of bridge on south side of road and heads northwest. | OH |  |  | 2017-05-15
34a | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com, Nelson White (Manager) nwhite@nisource.com, 150 Hillside Drive, Bethel Park, PA 15102 | Conflict. Lines nearby (per one call). See as-builts located in the on call folder for this bridge on sharepoint. Per initial site visit gas main is in church lot and crosses roadway about 50' west of bridge. | UG |  |  | 2016-07-08
34b | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | sanitary | Mountaintop Area Municipal Auth | Kenneth Hall, 814-387-4321, mama1993@verizon.net | Marked (Per one call). Per initial site visit sanitary MH in church parking lot and line is 10' west of bridge. | UG |  |  | 2016-07-08
34c | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Wtr | Mountaintop Regional Water Auth | Josh Cingle, 814-360-6362, mtrwa@verizon.net | Marked (Per one call). Per initial site visit water line is 18' left of structure (looking east). Valve located east of bridge behind guardrail near utility pole. | UG |  |  | 2016-07-08
34d | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | sanitary | Snow Shoe TWP | 814-387-6012 | DID NOT RESPOND per one call |  |  |  | 2016-07-08
34e | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com (manager), 820 S. 4th Street, Clearfield, PA 16830 | Per initial site visit OH power/phone/catv 8' lt of far abutment (looking east) | OH |  |  | 2016-07-08
34f | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH power/phone/catv 8' lt of far abutment (looking east) | OH |  |  | 2016-07-08
34g | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH elec/phone/catv 8' lt of far abutment (looking east). Not their facilities. |  |  |  | 2016-07-08
34h | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Comm | Tele-Media Corporation | Dean Colbert, dcolbert@tele-media.com, 814-359-3481, PO Box 39, Bellefonte, PA 16823 | Per initial site visit OH elec/phone/catv 8' lt of far abutment (looking east). | OH |  |  | 2016-07-08
34i | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Comm | Clarence Cable TV | Tim Cramer, 814-387-4234 | Per power and verizon they own the cable on the poles. Out of business |  |  |  | 2016-07-08
34j | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | Comm | Cequel Communications (SuddenLink) | 314-315-9630, Gordon Bourne | OH fiber company per Verizon. Spoke with SuddenLink on the phone on 11/13/15 and they sold this fiber several years ago and don’t have any records as to who bought it. |  |  |  | 2016-07-08
35a | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | wtr | Cooper TWP Municipal Auth | Lisa Howe, 814-345-5673, ctma46@hotmail.com, water operator - Donovan | Design Conflict. Please send plans to: Martha Dukeman, 4596 Winburne-Munson Rd, PO Box 446, Winburne PA 16879 (per one call). Per initial site visit valve box located east of bridge far right of road (looking east) and 6" main visible on right side of bridge. The main is 4" galvanized and is no longer in service and can be removed with bridge project. | UG | 4" |  | 2016-05-20
35b | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com (manager), 820 S. 4th Street, Clearfield, PA 16830 | Per initial site visit OH power/phone/catv. Poles are located 15' right (looking east) | OH |  |  | 2016-05-20
35c | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | Comm | Verizon Pennsylvania LLC | Paul Deering, 814-231-6507, paul.e.deering@verizon.com, 250 S. Allen Street State College, PA 16801 | Per initial site visit OH power/phone/catv. Poles are located 15' right (looking east) | OH |  |  | 2016-05-20
35d | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH power/phone/catv. Poles are located 15' right (looking east) | OH |  |  | 2016-05-20
35e | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | Comm | Tele-Media Corporation | Dean Colbert, dcolbert@tele-media.com, 814-359-3481, PO Box 39, Bellefonte, PA 16823 | Per initial site visit OH power/phone/catv. Poles are located 15' right (looking east). No facilities |  |  |  | 2016-05-20
36a | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | Wtr | Pennsylvania American Water CO | Mark Rice, mark.rice@amwater.com, 814-342-0995, 1912 Tyrone Pike, Philipsburg, PA 16866 | Marked per one call. Per initial site visit there are 5 water valves clustered north of bridge on left (looking north) and not sure if it crosses the stream or goes towards bridge. | UG |  | Not affected | 2016-04-14
36b | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | sanitary | Municipal Auth of the Township of Morris | Vic Couturiaux, 814-574-5278, sewercat@msn.com, vcouturiaux@hriinc.com, 135 Lil Troy Drive, Philipsburg, PA 16866; Tom Holleran HRG Inc, consultant), tholleran@hrg-inc.com, 814-574-0191 | Marked per one call. Sent out plans for review in mail. Sent email back that utilities are depicted correctly | UG |  | Not affected | 2016-04-14
36c | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com (manager), 820 S. 4th Street, Clearfield, PA 16830 | OH E/T/CATV located west of bridge not in conflict with work but picked up by surveyors | OH |  | Not affected | 2016-04-14
36d | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | Comm | Verizon Pennsylvania LLC | Paul Deering, 814-231-6507, paul.e.deering@verizon.com, 250 S. Allen Street State College, PA 16801 | OH E/T/CATV located west of bridge not in conflict with work but picked up by surveyors | OH |  | Not affected | 2016-04-14
36e | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | Comm | Tele-Media Corporation | Dean Colbert, dcolbert@tele-media.com, 814-359-3481, PO Box 39, Bellefonte, PA 16823 | OH E/T/CATV located west of bridge not in conflict with work but picked up by surveyors. Confirmed not their facility. |  |  | NA | 2016-04-14
36f | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | OH E/T/CATV located west of bridge not in conflict with work but picked up by surveyors | OH |  | Not affected | 2016-04-14
37a | -- | 37 | 11390 | 91508 | 17021902800000 | 2 | Clearfield | MCGEES MILLS | SR 219-US 219 | WHISKEY RUN | 17/202 - BELL | 40.8848 | -78.7566 |  | all facilities responded clear per one call | [5 empty] | 2017-02-13
37b | -- | 37 | 11390 | 91508 | 17021902800000 | 2 | Clearfield | MCGEES MILLS | SR 219-US 219 | WHISKEY RUN | 17/202 - BELL | 40.8848 | -78.7566 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | per initial site visit there is power 12' off bridge on rt side (looking north) | OH |  |  | 2017-02-13
37c | -- | 37 | 11390 | 91508 | 17021902800000 | 2 | Clearfield | MCGEES MILLS | SR 219-US 219 | WHISKEY RUN | 17/202 - BELL | 40.8848 | -78.7566 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | per initial site visit there is phone and fiber 20' off bridge on left side (looking north). There is also a small guy wire crossing over the road near abutment and guy pole at 25' left (looking north) | OH |  |  | 2017-02-13
38a | -- | 38 | 11399 | 85076 | 17021904201459 | 2 | Clearfield | CURRY RUN | SR 219-US 219 | CURRY RUN | 17/217 - GREENWOOD | 40.9094 | -78.6707 |  | all facilities responded clear per one call | [5 empty] | 2016-07-01
38b | -- | 38 | 11399 | 85076 | 17021904201459 | 2 | Clearfield | CURRY RUN | SR 219-US 219 | CURRY RUN | 17/217 - GREENWOOD | 40.9094 | -78.6707 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | per initial site visit OH catv. Poles adjacent to road 2' left (facing northeast). Verified not their facilities |  |  |  | 2016-07-01
38c | -- | 38 | 11399 | 85076 | 17021904201459 | 2 | Clearfield | CURRY RUN | SR 219-US 219 | CURRY RUN | 17/217 - GREENWOOD | 40.9094 | -78.6707 | Comm | Verizon Pennsylvania LLC | John Grech, 814-577-0703, john.m.grech@verizon.com; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126, 115 E Scribner Avenue, DuBois, PA 15801 | per initial site visit OH fiber and phone. Poles adjacent to road 2' left (facing northeast). Potential UG phone in area. Need to investigate. | OH |  |  | 2016-07-01
38d | -- | 38 | 11399 | 85076 | 17021904201459 | 2 | Clearfield | CURRY RUN | SR 219-US 219 | CURRY RUN | 17/217 - GREENWOOD | 40.9094 | -78.6707 | Comm | Atlantic Broadband | Dana Wells, 814-368-4541, dwells@atlanticbb.com, 24 Main St, Bradford, PA 16701 | per initial site visit OH catv. Poles adjacent to road 2' left (facing northeast). Not in the area. Confirmed that it is only fiber and phone on the poles no CATV. |  |  |  | 2016-07-01
39a | -- | 39 | 11403 | 85079 | 17021904602606 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | POPLAR RUN | 17/217 - GREENWOOD | 40.9303 | -78.6468 | Gas | Alliance Petroleum Corp | 724-349-9070 | Marked per one call. Per initial site visit it was marked and crosses road 200' south of bridge | UG |  |  | 2017-02-13
39b | -- | 39 | 11403 | 85079 | 17021904602606 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | POPLAR RUN | 17/217 - GREENWOOD | 40.9303 | -78.6468 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | Conflict. Lines Nearby (per one call). Per initial site visit OH power/phone/catv crosses road 150' north of bridge parallel to Bell Run Road. Closes pole is 75' north of bridge (tag 9 282). | OH |  |  | 2017-02-13
39c | -- | 39 | 11403 | 85079 | 17021904602606 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | POPLAR RUN | 17/217 - GREENWOOD | 40.9303 | -78.6468 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit UG phone runs parallel to road on lt (looking north) and stops 50' north of bridge. Per initial site visit OH power/phone/catv crosses road 150' north of bridge parallel to Bell Run Road. Closes pole is 75' north of bridge (tag 9 282). | Both |  |  | 2017-02-13
39d | -- | 39 | 11403 | 85079 | 17021904602606 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | POPLAR RUN | 17/217 - GREENWOOD | 40.9303 | -78.6468 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH power/phone/catv crosses road 150' north of bridge parallel to Bell Run Road. Closes pole is 75' north of bridge (tag 9 282). | OH |  |  | 2017-02-13
40a | -- | 40 | 11404 | 93323 | 17021904700185 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | BELL RUN | 17/217 - GREENWOOD | 40.9311 | -78.6461 | Gas | Alliance Petroleum Corp | 724-349-9070 | Marked per one call. | UG |  |  | 2017-02-13
40b | -- | 40 | 11404 | 93323 | 17021904700185 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | BELL RUN | 17/217 - GREENWOOD | 40.9311 | -78.6461 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | Conflict. Lines Nearby (per one call). Per initial site visit OH elec/phone/catv 100' south of bridge. | OH |  |  | 2017-02-13
40c | -- | 40 | 11404 | 93323 | 17021904700185 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | BELL RUN | 17/217 - GREENWOOD | 40.9311 | -78.6461 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH elec/phone/catv 100' south of bridge. UG phone 13' lt (looking north). | OH |  |  | 2017-02-13
40d | -- | 40 | 11404 | 93323 | 17021904700185 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | BELL RUN | 17/217 - GREENWOOD | 40.9311 | -78.6461 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH elec/phone/catv 100' south of bridge. | OH |  |  | 2017-02-13
41a | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | Elect | Pennsylvania Electric Company | Michael (Mike) Kephart, mkephart@firstenergycorp.com, 814-768-4171, 820 South Fourth Street, Clearfield, PA 16830 | Conflict. Lines Nearby per one call. There was no initial site visit performed due to the fact that the bridge was being refurbished at the time of the visit. | OH |  |  | 2016-06-07
41b | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | Comm | Verizon Pennsylvania LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | OH power/phone/catv from google earth on east side of bridge. Not their facilities. Windstream. |  |  |  | 2016-06-07
41c | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | Comm | Zito Media LP (DuBois Comm) | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | OH power/phone/catv from google earth on east side of bridge | OH |  |  | 2016-06-07
41d | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | Comm | Comcast Cable Communications, Inc. (Level3) | Doug Olszewski, douglas_olszewski@cable.comcast.com, 724-459-5660 X 72661; Level 3 rep - Stephen Putt, stephen.putt@level3.com, 412-728-6496 | have a fiber line on the pole that is used by level3. told by Zito that there is fiber on the power poles that is used by Level3 but they arent the owners. | OH |  |  | 2016-06-07
41e | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | Comm | Windstream | Brian Cook, Brian.A.Cook@windstream.com, 814-849-3558, 98 Industrial Park Road, Brookville, PA 15825 | OH power/phone/catv from google earth on east side of bridge. | OH |  |  | 2016-06-07
42a | -- | 42 | 11461 | 88626 | 17025503200000 | 2 | Clearfield | HOLLYWOOD | SR 255-PA 255 | MINE CAVE IN | 17/219 - HUSTON | 41.2422 | -78.5402 | Elect | Pennsylvania Electric Company | John Forbes, 814-676-7551, jforbes@firstenergycorp.com | Conflict. Lines Nearby (per one call). OH E/T/catv 4' lt (looking east) | OH |  |  | 2017-02-13
42b | -- | 42 | 11461 | 88626 | 17025503200000 | 2 | Clearfield | HOLLYWOOD | SR 255-PA 255 | MINE CAVE IN | 17/219 - HUSTON | 41.2422 | -78.5402 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal (per one call). | UG |  |  | 2017-02-13
42c | -- | 42 | 11461 | 88626 | 17025503200000 | 2 | Clearfield | HOLLYWOOD | SR 255-PA 255 | MINE CAVE IN | 17/219 - HUSTON | 41.2422 | -78.5402 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH E/T/catv 4' lt (looking east) | OH |  |  | 2017-02-13
42d | -- | 42 | 11461 | 88626 | 17025503200000 | 2 | Clearfield | HOLLYWOOD | SR 255-PA 255 | MINE CAVE IN | 17/219 - HUSTON | 41.2422 | -78.5402 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Per initial site visit OH E/T/catv 4' lt (looking east) | OH |  |  | 2017-02-13
42e | -- | 42 | 11461 | 88626 | 17025503200000 | 2 | Clearfield | HOLLYWOOD | SR 255-PA 255 | MINE CAVE IN | 17/219 - HUSTON | 41.2422 | -78.5402 | wtr | Huston TWP Water Auth | 814-637-5345 | Did not respond through one call. Per initial site visit hydrant west of bridge on south side of road. | UG |  |  | 2017-02-13
43a | -- | 43 | 11658 |  |  | 2 | Clearfield | HAWK RUN | SR 1009 | HAWK RUN | 17/224 - MORRIS | 40.9375 | -78.2029 | wtr | Pennsylvania American Water CO | Mark Rice, mark.rice@amwater.com, 814-342-0995, 1912 Tyrone Pike, Philipsburg, PA 16866 | Marked. 6" PVC line located on Empire Road crosses creek to the south of the bridge (1 ft from wing wall with 2' depth). Please see attached utility sketch located in the survey data for design folder for the bridge in sharepoint. (per one call) | UG | 6" |  | 2016-08-08
43b | -- | 43 | 11658 |  |  | 2 | Clearfield | HAWK RUN | SR 1009 | HAWK RUN | 17/224 - MORRIS | 40.9375 | -78.2029 | Comm | Verizon Pennsylvania LLC | Paul Deering, 814-231-6507, paul.e.deering@verizon.com, 250 S. Allen Street State College, PA 16801 | Per initial site visit OH phone crosses bridge to pole on southeast side of road. | OH |  |  | 2016-08-08
44a | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Conflict. Lines Nearby per one call. Per initial site visit there is OH catv and phone 8' left (looking north). Fiber and coax. | OH |  |  | 2016-05-27
44b | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | wtr | Pennsylvania American Water CO | Mark Rice, mark.rice@amwater.com, 814-342-0995, 1912 Tyrone Pike, Philipsburg, PA 16866 | Marked per one call. | UG |  |  | 2016-05-27
44c | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | GAS | UGI Central Penn Gas | Thomas (Tom) Shaffer, tshaffer@ugi.com, 814-577-6862, 5 Technology Dr., Clearfield, PA 16830 | Design Conflict. Please send plans to: Andrew Black UGI Central Penn Gas 225 Morgantown Rd Reading PA 19611. (Per one call) Per initial site visit Gas line 15' left (looking north) | UG |  |  | 2016-05-27
44d | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | sanitary | Wallaceton-Boggs Municipal Auth | Denny Knepp, Gloria Knepp, 814-342-0725, 814-592-1600 (cell), 63 Apple Lane, West Decatur PA 16878 (home address) don’t call until after 10 am. | Design Conflict. Please send plans to owner. (per one call) Per initial site visit manholes on left side on both sides of bridge. Faint sanitary marks at road crossing north and south of bridge. | UG |  |  | 2016-05-27
44e | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 |  | Boggs TWP | 814-342-5243 | DID NOT RESPOND per one call. Spoke to them on phone on 7/7/15 and they don’t have facilities on the bridge |  |  |  | 2016-05-27
44f | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com (manager), 820 S. 4th Street, Clearfield, PA 16830 | Per initial site visit OH power. Poles are 3' right (looking north). OH line crosses bridge from pole north of bridge on left to house south of bridge on right. | OH |  |  | 2016-05-27
44g | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | comm | Verizon Pennsylvania LLC | Paul Deering, 814-231-6507, paul.e.deering@verizon.com, 250 S. Allen Street State College, PA 16801 | Conflict. Lines Nearby. Per initial site visit there is OH catv and phone 8' left (looking north). Pole tag verizon 1131 F-3830, 56670. Have fiber and copper | OH |  |  | 2016-05-27
44h | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | Comm | Sunesys | Dave Hayward, 267-927-2000, dhayward@sunesys.com, 185 Titus Avenue, Warrington, PA 18976 | fiber on poles per verizon. Lines are barely within limits of work so should not be affected. | OH |  |  | 2016-05-27
45a | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | Elect | United Electric Coop Inc | Stephen (Steve) Long, 814-503-8509, slong@unitedpa.com, 29 United Road, DuBois, PA 15801 | Conflict. Lines Nearby. UG and aerial lines in area. Per initial site visit OH power 8' from edge of shoulder (looking east). Becomes UG at pole just west of bridge on left (looking east). UG line heads NW away from pole. | Both |  |  | 2016-06-16
45b | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | sanitary | Brady TWP | 814-583-7660 | DID NOT RESPOND per one call. Spoke to TWP on 9/10 and they don’t have facilities in the area of the bridge. |  |  |  | 2016-06-16
45c | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | wtr | Brady TWP Troutville Boro Water Assn Inc | 814-583-5680 | DID NOT RESPOND per one call. Spoke to Sharon on 9/9 and they have no facilities. |  |  |  | 2016-06-16
45d | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | Comm | Windstream | Brian Cook, Brian.A.Cook@windstream.com, 814-849-3558, 98 Industrial Park Road, Brookville, PA 15825 | Underground copper on SR 3009 (McGees Mill Rd) near bridge. Please see the utility map located in the one call folder for the bridge located on sharepoint. | UG |  |  | 2016-06-16
46a | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Conflict. Lines Nearby (per one call). Per initial site visit OH power/phone on right (looking east) and then crosses road east of bridge at pole # 119128. | OH |  |  | 2017-02-13
46b | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Conflict. Lines Nearby (per one call). Per initial site visit OH catv lt of road (looking east) west of bridge and crosses bridge at pole # 582 150 towards southeast | OH |  |  | 2017-02-13
46c | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call. |  |  |  | 2017-02-13
46d | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | Elect | West Penn Power | Zach Reedy (engineering supervisor), zreedy@firstenergycorp.com, 724-548-3578 | Conflict. Lines Nearby (per one call). Per initial site visit OH E/T on right (looking east) and then crosses road east of bridge at pole # 119128. | OH |  |  | 2017-02-13
47a | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Conflict. Lines Nearby per one call. Per initial site visit OH E/T/CATV 6' left side of road (looking north). Verified that they are pole owners with West Penn. They have fiber and copper lines. | OH |  |  | 2016-05-20
47b | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | sanitary | East Nittany Valley Joint Municipal Auth | Ray Zwald, 570-726-6224, 200 Clintondale Hill Road Millhall, PA 17751, envjma@centurylink.net | UG sanitary lines on east side of road. | UG |  |  | 2016-05-20
47c | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | Comm | TDS Telecom/Sugar Valley Telephone CO | Stewart Walker, 315-562-0091, stewart.walker@tdstelecom.com, 159 Main Street Edwards, NY 13635 | Conflict. Lines Nearby per one call. Per initial site visit OH E/T/CATV 6' left side of road (looking north). Confirmed no facilities. |  |  |  | 2016-05-20
47d | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | Elect | West Penn Power | Robert Rhodes, rwrhodes@firstenergycorp.com, 2800 East College Avenue, State College, PA 16801, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com,724-548-3578 | Conflict. Lines Nearby per one call. Per initial site visit OH E/T/CATV 6' left side of road (looking north) | OH |  |  | 2016-05-20
47e | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | CenturyLink mentioned that comcast may be on poles. They are on the poles | OH |  |  | 2016-05-20
47f | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | Comm | Sunesys | Dave Hayward, 267-927-2000, dhayward@sunesys.com, 185 Titus Avenue, Warrington, PA 18976 | Determined at utility site visit that Sunesys may be present | OH |  |  | 2016-05-20
48a | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | air | Air Liquide | Rich Smitty, 814-781-6990, rich.smitty@airliquide.com | DID NOT RESPOND per one call. Per verification plans they don’t have facilities in the vacinity of the bridge. |  |  |  | 2016-07-05
48b | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | DID NOT RESPOND per one call. Per email dated 4/27/15 from PennDot there is a gas main attached to the bridge. Received map from gas company. There is a 6" steel pipe that runs E-W 18' north of CL of road and crosses road west of bridge and attached to bridge on south side and continues east 18-26' south of CL of road. 2" plastic main about 25' north of bridge (downstream) runs E-W. Confirmed at site visit. | UG | 6 and 2" |  | 2016-07-05
48c | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | sanitary | City of Saint Marys | Tim Brennan, 814-781-1718 x234 or 235, tim@cityofstmarys.com, 11 Lafayette Street, St. Marys PA 15857; Travis Skrzypek (GIS Tech), tskrzypek@cityofstmarys.com, 814-781-1718 x 235 | Marked per one call. | UG |  |  | 2016-07-05
48d | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | Wtr | Saint Marys Area Water Authority | Dwight Hoare, 814-834-4362, stwaterdhoare@windstream.net, 967 State St, St Marys, PA 15857 (hours M-F 8-4:30) | Marked per one call. Per initial site visit 25' north of bridge (downstream) | UG |  |  | 2016-07-05
48e | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | Elect | West Penn Power | Cheryl Moore (distribution specialist), cmoore4@firstenergycorp.com, 814-781-5545, 323 State Street, Saint Marys, PA 15857; Zach Reedy (engineering supervisor), zreedy@firstenergycorp.com, 724-548-3578 | Conflict. Lines Nearby per one call. Per initial site visit OH E/T/CATV. OH service line crosses bridge from pole located on west of bridge on right (facing east) to property on east side of bridge on right side | OH |  |  | 2016-07-05
48f | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | Comm | Windstream | Brian Cook, Brian.A.Cook@windstream.com, 814-849-3558, 98 Industrial Park Road, Brookville, PA 15825 | Aerial line on SR120 (Brusselles St) and Fillmore Rd. Please see the utility map located in the one call folder for the bridge located on sharepoint. (per one call) Per initial site visit OH E/T/CATV. | OH |  |  | 2016-07-05
48g | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | West Penn stated that they may be on the poles. Confirned that they are on the poles. | OH |  |  | 2016-07-05
49a | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | Conflict. Lines Nearby per one call. Per initial site visit there is OH E/T/CATV. Power poles on right (looking north). E/T/CATV crosses road heading west just south of bridge. Pole tag 259, 4056 139. Confirmed that this isnt their facilities. |  |  |  | 2016-05-23
49b | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | sanitary | Brockway Area Sewage Authority | Rick Boleen (Plant Manager), 814-591-2852, basa@brockwaytv.com, 70 Industrial Park Drive, Brockway, PA 15824 | Marked per one call. | UG |  |  | 2016-05-23
49c | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Comm | Comcast Cable Communications, Inc. | Doug Olszewski, douglas_olszewski@cable.comcast.com, 724-459-9042 x72661 | Conflict. Lines Nearby per one call. Phone pole just north of bridge 24' left of EOP. Phone line crosses bridge from this pole to power pole south of bridge on right side. Phone and catv cross road from phone pole to power pole further north. | OH |  |  | 2016-05-23
49d | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | Marked per one call. National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal. Per initial site visit gas main crosses stream about 25' left of EOP. | UG | 3 and 4" |  | 2016-05-23
49e | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Elect | West Penn Power | George Dragich, 814-781-5522, gdragi1@firstenergycorp.com; engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com | Conflict. Lines Nearby per one call. Per initial site visit there is OH E/T/CATV. Power poles on right (looking north). E/T/CATV crosses road heading west just south of bridge. Pole tag 259, 4056 139. | OH |  |  | 2016-05-23
49f | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Comcast stated that Zito may be on these poles as well. Confirmed no facilities at site |  |  |  | 2016-05-23
49g | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | wtr | Brockway Municipal Water Auth | Mike Starr, 814-265-1114, h2o@brockwaytv.com, 501 Main Street, Brockway, PA 15824 | Marked per one call. | UG |  |  | 2016-05-23
49h | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Comm | Windstream | Brian Cook, Brian.A.Cook@windstream.com, 814-849-3558, 98 Industrial Park Road, Brookville, PA 15825 | Per power windstream is on poles and owns some poles | OH |  |  | 2016-05-23
49i | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Comm | Verizon Pennsylvania LLC | John Grech, 814-577-0703, john.m.grech@verizon.com; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126, 115 E Scribner Avenue, DuBois, PA 15801 | Per windstream verizon is on the poles. Have inter-office fiber on poles | OH |  |  | 2016-05-23
49j | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | Comm | Brockway TV | Howard Olay, 814-265-8291, headend@brockwaytv.com, 501 Main Street, Brockway, PA 15824 | Per windstream brockway tv on poles | OH |  |  | 2016-05-23
50a | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | Comm | Comcast Cable Communications, Inc. | Doug Olszewski, douglas_olszewski@cable.comcast.com, 724-459-9042 x72661 | Conflict. Lines Nearby. Per initial site visit OH E/T/CATV. Phone and catv cross just north of bridge to pole on right side of road. Not their facilities. |  |  |  | 2016-06-17
50b | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | wtr | Johnsonburg Municipal Auth | Lisa Sorg, 814-965-4218, managerjmawater@ncentral.com, 434 Center Street Johnsonburg, PA 15845; Travis Long (Engineer with GD&F) | DID NOT RESPOND per one call. Confirmed that they are the owners of the water and sanitary systems | UG |  |  | 2016-06-17
50c | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | Marked. National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal. Per initial visit gas crosses stream on left. visible markers | UG | 2 and 4" |  | 2016-06-17
50d | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | Comm | Windstream | Brian Cook, Brian.A.Cook@windstream.com, 814-849-3558, 98 Industrial Park Road, Brookville, PA 15825 | Marked. Per initial site visit OH E/T/CATV. Confirmed cable and fiber | OH |  |  | 2016-06-17
50e | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | storm | Johnsonburg Borough | Mary Polasky, 814-965-5682, jbgboro@ncentral.com, Ryan Miller (Consultant Engineer ARS Engineering Services), 814-965-2211, miller@arsengineeringservices.com | DID NOT RESPOND per one call. Owners of stormwater system only. |  |  |  | 2016-06-17
50f | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | Elect | West Penn Power | George Dragich, 814-781-5522, gdragi1@firstenergycorp.com; engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com | Conflict. Lines Nearby. Per initial site visit OH E/T/CATV. Power poles 35-50 feet left (looking North). Crosses road just south of bridge and then runs east. Warning, "buried electric cable call Allegheny Power" Pole tag 3152 001 Alltel 50A; 3200 025 alltel 732; 3 1; allg pwr 1106889; 3200 026 alltel | OH |  |  | 2016-06-17
50g | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | sanitary | Johnsonburg Municipal Auth | Lisa Sorg, 814-965-4218, managerjmawater@ncentral.com, 434 Center Street Johnsonburg, PA 15845; Travis Long (Engineer with GD&F) | DID NOT RESPOND per one call. Confirmed that they are the owners of the sanitary systems | UG |  |  | 2016-06-17
51a | -- | 51 | 19992 | 88195 | 34003507200000 | 2 | Juniata | MCALISTERVILLE | SR 35-PA 35 | TRIB LOST CREEK | 34/203 - FAYETTE | 40.6347 | -77.2779 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | voice message - UG facilities exist in the area. Please call 484-634-3296 for field maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. Per initial site visit there is OH elec/phone/catv on rt (looking east). guy wire crosses road just west of the bridge to a guy pole located on the north side of the road. Guy wires crossing creek on south side of bridge from pole located on the south side of the road just west of the bridge. | UG |  |  | 2017-02-13
51b | -- | 51 | 19992 | 88195 | 34003507200000 | 2 | Juniata | MCALISTERVILLE | SR 35-PA 35 | TRIB LOST CREEK | 34/203 - FAYETTE | 40.6347 | -77.2779 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | DID NOT RESPOND per one call. Per initial site visit there is OH E/T/CATV on rt (looking east). guy wire crosses road just west of the bridge to a guy pole located on the north side of the road. | OH |  |  | 2017-02-13
51c | -- | 51 | 19992 | 88195 | 34003507200000 | 2 | Juniata | MCALISTERVILLE | SR 35-PA 35 | TRIB LOST CREEK | 34/203 - FAYETTE | 40.6347 | -77.2779 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Clear per one call. Per initial site visit there is OH E/T/CATV on rt (looking east). guy wire crosses road just west of the bridge to a guy pole located on the north side of the road. | OH |  |  | 2017-02-13
51d | -- | 51 | 19992 | 88195 | 34003507200000 | 2 | Juniata | MCALISTERVILLE | SR 35-PA 35 | TRIB LOST CREEK | 34/203 - FAYETTE | 40.6347 | -77.2779 | sanitary | McAlisterville Area Joint Authority | 814-698-2194 | Responded clear per one call. Per initial site visit MH east of the bridge and 27' lt from EOP (looking east) | UG |  |  | 2017-02-13
52a | -- | 52 | 20021 | 4194 | 34007502501504 | 2 | Juniata | EAST WATERFORD | SR 75-PA 75 | HORSE VALLEY RUN CREEK | 34/212 - TUSCARORA | 40.3722 | -77.6006 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Field Marked per one call. Per initial site visit OH E/T/CATV 2' rt (looking east). OH T/catv 2' lt (looking east). Guy wire crosses road just east of guardrail from pole approx 2' north of EOP to guy pole about 1' south of EOP. No UG was visible during site visit. | Both |  |  | 2017-06-06
52b | -- | 52 | 20021 | 4194 | 34007502501504 | 2 | Juniata | EAST WATERFORD | SR 75-PA 75 | HORSE VALLEY RUN CREEK | 34/212 - TUSCARORA | 40.3722 | -77.6006 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | Per initial site visit OH E/T/CATV 2' rt (looking east). OH T/catv 2' lt (looking east). Guy wire crosses road just east of guardrail from pole approx 2' north of EOP to guy pole about 1' south of EOP. OH catv crosses road just west of bridge from pole (has light) 1' south of EOP behind guardrail to pole about 8' north of EOP. | OH |  |  | 2017-06-06
52c | -- | 52 | 20021 | 4194 | 34007502501504 | 2 | Juniata | EAST WATERFORD | SR 75-PA 75 | HORSE VALLEY RUN CREEK | 34/212 - TUSCARORA | 40.3722 | -77.6006 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | Per initial site visit OH E/T/CATV 2' rt (looking east). Guy wire crosses road just east of guardrail from pole approx 2' north of EOP to guy pole about 1' south of EOP. | OH |  |  | 2017-06-06
53a | -- | 53 | 20106 | 4214 | 34100200200000 | 2 | Juniata | 0.5 MI E CUBA MILLS | SR 1002 | LOST CREEK | 34/204 - FERMANAGH | 40.5937 | -77.3999 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | Did Not Respond per one call. Per initial site visit OH CATV 2' south of EOP coming fron west to pole located behind guardrail just west of bridge. From pole it crosses bridge diagonally to pole just east of bridge 2' north of EOP behind guardrail. | OH |  |  | 2017-05-22
53b | -- | 53 | 20106 | 4214 | 34100200200000 | 2 | Juniata | 0.5 MI E CUBA MILLS | SR 1002 | LOST CREEK | 34/204 - FERMANAGH | 40.5937 | -77.3999 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | Voice Message. UG facilities located in the vicinity of the one call area. Please call 484-634-4217 for maps of the area (per one call). Per initial site visit OH E/T 2' north of EOP coming from the west to pole west of bridge behind guardrail 2' north of EOP. From this pole OH elec travels northeast away from bridge. | Both |  |  | 2017-05-22
53c | -- | 53 | 20106 | 4214 | 34100200200000 | 2 | Juniata | 0.5 MI E CUBA MILLS | SR 1002 | LOST CREEK | 34/204 - FERMANAGH | 40.5937 | -77.3999 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Responded clear per one call. Per initial site visit OH E/T 2' north of EOP coming from the west to pole west of bridge behind guardrail 2' north of EOP. | OH |  |  | 2017-05-22
54a | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Did Not Respond per one call. Per initial site visit OH elec/phone/catv cming from east about 1' north of EOP to pole located on the northeast corner of intersection of water ave and SR 1004. From that pole OH E/T/CATV continues west to pole located on the northeast corner of bridge behind guard rail. From that pole it crosses the bridge diagonally to pole located at the northwest corner of the driveway of the first house west of bridge. From the pole located on the northeast corner of intersection of water ave and SR 1004 OH E/T/CATV crosses bridge to the south and travels south along creek. | OH |  |  | 2017-06-13
54b | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | wtr and sanitary | McAlisterville Area Joint Authority | 814-698-2194 | Insufficient information. Do not dig (per one call). Per initial site visit MH located on north and south side of creek east of bridge. Water valve located on south side of water avenue south of bridge. | UG |  |  | 2017-06-13
54c | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | DID NOT RESPOND per one call. Per initial site visite OH E/T/CATV cming from east about 1' north of EOP to pole located on north east corner of the intersection of water ave and SR 1004. From that pole OH cable crosses road and bridge diagonally to pole located at the northwest corner of the driveway of the first house west of bridge. From the pole located on the northeast corner of the intersection of water ave and SR 1004 OH E/T/CATV continues west to the pole located on the northeast corner of bridge behind guard rail. From that pole it crosses the bridge diagonally to pole located at the northwest corner of the driveway of the first house west of bridge. From the pole located on the northeast corner of intersection of water ave and SR 1004 OH E/T/CATV crosses bridge to the south and travels south along creek. | OH |  |  | 2017-06-13
54d | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | Voice Message. UG facilities located in the vicinity of the one call area. Please call 484-634-4127 for maps of the area (per one call). Per initial site visite OH E/T/CATV cming from east about 1' north of EOP to pole located on north east corner of intersection of water ave and SR 1004. From that pole OH E/T/CATV continues west to pole located on the northeast corner of bridge behind guard rail. From that pole it crosses the bridge diagonally to pole located at the northwest corner of the driveway of the first house west of bridge. From the pole located on the northeast corner of intersection of water ave and SR 1004 OH E/T/CATV crosses bridge to the south and travels south along creek. | Both |  |  | 2017-06-13
55a | -- | 55 | 20137 | 81508 | 34200601501696 | 2 | Juniata | VAN WERT | SR 2006 | DOE RUN | 34/213 - WALKER | 40.5835 | -77.2954 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | DID NOT RESPOND per one call. OH CATV 2 ft lt (looking east) running adjacent to bridge. From pole 2 ft lt (looking east) cable runs west diagonally across road to pole rt of road. Spoke to Scott with Nittany Media on 8/14/15 and he comfirmed no facilities at bridge. |  |  |  | 2016-05-23
55b | -- | 55 | 20137 | 81508 | 34200601501696 | 2 | Juniata | VAN WERT | SR 2006 | DOE RUN | 34/213 - WALKER | 40.5835 | -77.2954 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | voice message - UG facilities exist in the area. Please call 484-634-3296 for field maps. Per initial site visit OH power poles far left running adjacent to bridge. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. Conflirmed with PPL that there are no UG primary lines in this are but may have UG services. | OH |  |  | 2016-05-23
55c | -- | 55 | 20137 | 81508 | 34200601501696 | 2 | Juniata | VAN WERT | SR 2006 | DOE RUN | 34/213 - WALKER | 40.5835 | -77.2954 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Not on one call but there is OH phone. Confirmed that it is their OH phone | OH |  |  | 2016-05-23
56a | -- | 56 | 20147 | 91518 | 34200701400000 | 2 | Juniata | OAKLAND MILLS | SR 2007 | LOST CREEK | 34/203 - FAYETTE | 40.6119 | -77.3132 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | voice message - UG facilities exist in the area. Please call 484-634-4127 for field maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. Per the initial site visit OH E/T/CATV on rt looking north and then crosses road to the west at pole north of bridge behind guard rail. Guy wire crosses perpendicular from north pole to the west to guy pole located behind guardrail. | Both |  |  | 2017-04-03
56b | -- | 56 | 20147 | 91518 | 34200701400000 | 2 | Juniata | OAKLAND MILLS | SR 2007 | LOST CREEK | 34/203 - FAYETTE | 40.6119 | -77.3132 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Conflict. Lines Nearby (per one call). Per the initial site visit OH E/T/CATV on rt looking north and then crosses road to the west at pole north of bridge behind guard rail. Guy wire crosses perpendicular from north pole to the west to guy pole located behind guardrail. | OH |  |  | 2017-04-03
56c | -- | 56 | 20147 | 91518 | 34200701400000 | 2 | Juniata | OAKLAND MILLS | SR 2007 | LOST CREEK | 34/203 - FAYETTE | 40.6119 | -77.3132 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | DID NOT RESPOND per one call. Per the initial site visit OH E/T/CATV on rt looking north and then crosses road to the west at pole north of bridge behind guard rail. Guy wire crosses perpendicular from north pole to the west to guy pole located behind guardrail. | OH |  |  | 2017-04-03
57a | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Conflict. Lines Nearby (per one call). Per initial site visit no OH CATV was visible | OH |  |  | 2017-05-15
57b | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | sanitary | Hamlin TWP | 814-778-5855 | DID NOT RESPOND per one call. |  |  |  | 2017-05-15
57c | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call. |  |  |  | 2017-05-15
57d | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2017-05-15
57e | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | Elect | Pennsylvania Electric Company | John Forbes, 814-676-7551, jforbes@firstenergycorp.com | All responded clear to one call. Per initial site visit OH elec crosses road south of bridge running east/west. | OH |  |  | 2017-05-15
58a | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Conflict. Lines Nearby (per one call). OH T/CATV on rt (looking north). | OH |  |  | 2017-05-15
58b | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | sanitary | Hamlin TWP | 814-778-5855 | DID NOT RESPOND per one call. |  |  |  | 2017-05-15
58c | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | Marked. National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal. Per initial site visit gas on lt (looking north). | UG |  |  | 2017-05-15
58d | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | Elect | Pennsylvania Electric Company | John Forbes, 814-676-7551, jforbes@firstenergycorp.com | Conflict. Lines Nearby per one call. Per initial site visit OH elec on left (looking north). OH service crosses bridge from pole located at southwest corner of bridge behind guardrail to pole on northeast corner. OH elec crosses road south of bridge. | OH |  |  | 2017-05-15
58e | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call. |  |  |  | 2017-05-15
58f | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | Elect | West Penn Power | Zach Reedy (engineering supervisor), zreedy@firstenergycorp.com, 724-548-3578 | Conflict. Lines Nearby (per one call). Per initial site visit OH elec on left (looking north). OH service crosses bridge from pole located at southwest corner of bridge behind guardrail to pole on northeast corner. OH elec crosses road south of bridge. | OH |  |  | 2017-05-15
58g | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | OH T/CATV on rt (looking north). | OH |  |  | 2017-05-15
59 | -- | 59 | 25243 | 4344 | 42004600600000 | 2 | McKean | 3 MI SE BETULA | SR 46-PA 46 | HAVENS BROOK | 42/212 - NORWICH | 41.6341 | -78.3574 |  | all facilities responded clear per one call. No visible OH per initial site visit. | [5 empty] | 2017-05-22
60a | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | Comm | Comcast Cable Communications, Inc. | Doug Olszewski, douglas_olszewski@cable.comcast.com, 724-459-9042 x72661 | Conflict. Lines Nearby per one call. Not their facilities |  |  |  | 2016-06-22
60b | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | DID NOT RESPOND per one call. Confirmed no facilities on 9/3/15 |  |  |  | 2016-06-22
60c | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. |  |  |  | 2016-06-22
60d | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 |  | No visible OH per initial site visit. | [5 empty] | 2016-06-22
60e | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | Gas | Seneca Resources | Josh McLaughlin, 412-548-2516, mclaughlinj@srcx.com | National Fuel stated that there is an abandonded gas main owned by Seneca Resources within the project area. | UG | 8" |  | 2016-06-22
61a | -- | 61 | 25297 | 88183 | 42015500200000 | 2 | McKean | LIBERTY | SR 155-PA 155 | PORTAGE CREEK | 42/211 - LIBERTY | 41.7083 | -78.2148 | Elect | Tri-County Rural Electric Cooperative Inc. | Steve Salada, 570-662-8034, steves@ctenterprises.com | Conflict. Lines Nearby (per one call). | OH |  |  | 2017-03-06
61b | -- | 61 | 25297 | 88183 | 42015500200000 | 2 | McKean | LIBERTY | SR 155-PA 155 | PORTAGE CREEK | 42/211 - LIBERTY | 41.7083 | -78.2148 | sanitary | Liberty TWP | Dominic Picarelli (Sewage Enforcement Officer with KPI Technology), 717-339-0612, 143 Carlisle St Gettysburg, PA 17325 | DID NOT RESPOND per one call |  |  |  | 2017-03-06
61c | -- | 61 | 25297 | 88183 | 42015500200000 | 2 | McKean | LIBERTY | SR 155-PA 155 | PORTAGE CREEK | 42/211 - LIBERTY | 41.7083 | -78.2148 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-03-06
62a | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Conflict. Lines Nearby (Per one call). Per initial site visit 8" steel HP 60 ft north of bridge. | UG | 8" |  | 2016-06-29
62b | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | sanitary | Liberty TWP | Dominic Picarelli (Sewage Enforcement Officer with KPI Technology), 717-339-0612, 143 Carlisle St Gettysburg, PA 17325 | DID NOT RESPOND to one call. Did not pick up sanitary in initial site visit. Confirmed on 8/26/15 that they have no facilities at the bridge. |  |  |  | 2016-06-29
62c | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | Comm | Verizon Pennsylvania LLC | Susan Hoover, susan.a.hoover@verizon.com, 814-368-8404, 30 E Corydon St, Bradford, PA 16701; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH phone approx 8' rt (looking north). | OH |  |  | 2016-06-29
62d | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | Elect | Pennsylvania Electric Company | Edward (Ed) King, 814-726-5054, Eking@firstenergycorp.com, 1500 Pennsylvania Avenue W, Warren, PA 16365 | Per Verizon they are on the poles | OH |  |  | 2016-06-29
62e | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Per survey there is CATV. Not their facilities. |  |  |  | 2016-06-29
62f | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Per survey there is CATV. Per comcast it is Zito. | OH |  |  | 2016-06-29
63a | -- | 63 | 25313 | 4341 | 42015502701162 | 2 | McKean | 3 MI SE LARABEE | SR 155-PA 155 | ROCK RUN | 42/201 - ANNIN | 41.8788 | -78.349 | comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Marked UG facilities across roadway (Per one call). | UG |  |  | 2017-05-18
63b | -- | 63 | 25313 | 4341 | 42015502701162 | 2 | McKean | 3 MI SE LARABEE | SR 155-PA 155 | ROCK RUN | 42/201 - ANNIN | 41.8788 | -78.349 |  | Annin TWP | Robert Strait, 814-642-7959 | DID NOT RESPOND per one call |  |  |  | 2017-05-18
63c | -- | 63 | 25313 | 4341 | 42015502701162 | 2 | McKean | 3 MI SE LARABEE | SR 155-PA 155 | ROCK RUN | 42/201 - ANNIN | 41.8788 | -78.349 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-05-18
64a | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Conflict. Lines Nearby (per one call). | OH |  |  | 2017-06-19
64b | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 | sanitary | Eldred TWP | 814-225-4777, eldredboro@adelphia.net | DID NOT RESPOND per one call |  |  |  | 2017-06-19
64c | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 |  | Annin TWP | Robert Strait, 814-642-7959 | DID NOT RESPOND per one call |  |  |  | 2017-06-19
64d | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Conflict. Lines Nearby (per one call). | UG |  |  | 2017-06-19
65a | -- | 65 | 25418 | 85234 | 42034604101617 | 2 | McKean | 3 MI E BRADFORD | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5844 | wtr | Bradford City Water Auth | Kim Benjamin, 814-362-3004, watr@atlanticbb.net, 28 Kennedy St, Bradford, PA 16701 | Conflict. Lines Nearby (per one call). | UG |  |  | 2017-03-21
65b | -- | 65 | 25418 | 85234 | 42034604101617 | 2 | McKean | 3 MI E BRADFORD | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5844 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com, Nelson White (Manager) nwhite@nisource.com, 150 Hillside Drive, Bethel Park, PA 15102 | Conflict. Lines Nearby (per one call). | UG |  |  | 2017-03-21
65c | -- | 65 | 25418 | 85234 | 42034604101617 | 2 | McKean | 3 MI E BRADFORD | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5844 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Conflict. Lines Nearby (per one call). | OH |  |  | 2017-03-21
66a | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | wtr | Bradford City Water Auth | Kim Benjamin, 814-362-3004, watr@atlanticbb.net, 28 Kennedy St, Bradford, PA 16701 | Conflict. Lines Nearby (per one call). | UG |  |  | 2017-03-21
66b | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com, Nelson White (Manager) nwhite@nisource.com, 150 Hillside Drive, Bethel Park, PA 15102 | Conflict. Lines Nearby (per one call). | UG |  |  | 2017-03-21
66c | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Conflict. Lines Nearby (per one call). | OH |  |  | 2017-03-21
66d | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | sanitary | Foster TWP | 814-362-4656, fostertownship@charter.net | Marked per one call. | UG |  |  | 2017-03-21
67a | -- | 67 | 25459 | 85237 | 42064602900000 | 2 | McKean | 1 MI N GILMORE | SR 646-PA 646 | PENNBROOK RUN | 42/206 - FOSTER | 41.9784 | -78.5575 | wtr | Bradford City Water Auth | Kim Benjamin, 814-362-3004, watr@atlanticbb.net, 28 Kennedy St, Bradford, PA 16701 | Conflict. Lines Nearby (per one call). | UG |  |  | 2017-06-16
67b | -- | 67 | 25459 | 85237 | 42064602900000 | 2 | McKean | 1 MI N GILMORE | SR 646-PA 646 | PENNBROOK RUN | 42/206 - FOSTER | 41.9784 | -78.5575 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com, Nelson White (Manager) nwhite@nisource.com, 150 Hillside Drive, Bethel Park, PA 15102 | Conflict. Lines Nearby (per one call). | UG |  |  | 2017-06-16
67c | -- | 67 | 25459 | 85237 | 42064602900000 | 2 | McKean | 1 MI N GILMORE | SR 646-PA 646 | PENNBROOK RUN | 42/206 - FOSTER | 41.9784 | -78.5575 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Conflict. Lines Nearby (per one call). | OH |  |  | 2017-06-16
68a | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | wtr | Bradford City Water Auth | Kim Benjamin, 814-362-3004, watr@atlanticbb.net, 28 Kennedy St, Bradford, PA 16701 | Conflict. Lines Nearby (Per one call). Per initial site visit fire hydrant on left (looking east) approx 250' west of bridge. | UG |  |  | 2016-08-12
68b | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | sanitary | Bradford TWP | Ken Swanson, 814-362-4431, swanbagger@gmail.com, 136 Hemlock St. Bradford, PA 16701 | Field Marked. Contact Ken Swanson 5 days prior to survey in order to coordinate the layout of his facilities. (Per one call). Not their facilities. It is a private line for a home. Spoke to Ken on 9/25 and clarified that they own the manhole and facilities east of manhole | UG |  |  | 2016-08-12
68c | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | Marked. National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal. (Per one call) Per initial site visit gas line is 5' lt (looking east) from EOP adjacent to bridge. It crosses creek aerial abutting the bridge. | UG | 2" |  | 2016-08-12
68d | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | Elect | Pennsylvania Electric Company | Edward (Ed) King, 814-726-5054, Eking@firstenergycorp.com, 1500 Pennsylvania Avenue W, Warren, PA 16365 | Conflict. Lines Nearby (per one call). Per initial site visit OH E/T/CATV 15 ft rt (looking east) from EOP adjacent to bridge. Pole tag 161 20 C-25-18 | OH |  |  | 2016-08-12
68e | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | Comm | Verizon Pennsylvania LLC | Susan Hoover, susan.a.hoover@verizon.com, 814-368-8404, 30 E Corydon St, Bradford, PA 16701; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH E/T/CATV 15 ft rt (looking east) from EOP adjacent to bridge. | OH |  |  | 2016-08-12
68f | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | Comm | Atlantic Broadband | Dana Wells, 814-368-4541, dwells@atlanticbb.com, 24 Main St, Bradford, PA 16701 | Per initial site visit OH E/T/CATV 15 ft rt (looking east) from EOP adjacent to bridge. | OH |  |  | 2016-08-12
68g | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | sanitary | Private Sanitary Main |  | Not on one call. Was told by Bradford TWP that the lateral heading west is a private line. | UG |  |  | 2016-08-12
69a | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | wtr | Bradford City Water Auth | Kim Benjamin, 814-362-3004, watr@atlanticbb.net, 28 Kennedy St, Bradford, PA 16701 | Marked. Picked up in initial site visit. Sent plans by email on 7/20 for verification and after following up 3 times it was requested by utility on 8/13 to send hard copy. Responded on 9/2. | UG |  |  | 2016-06-16
69b | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | Marked. National Fuel has marked its active facilities within 15` of the described work area. Verify the location using hand dug test holes. There may also be abandoned gas lines in the work area. Contact National Fuel if such gas lines require removal. (per one call) Per initial site visit gas line on south side of bridge on left (looking north) that is cut and capped at bridge. | UG | 2" |  | 2016-06-16
69c | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | Elect | Pennsylvania Electric Company | Edward (Ed) King, 814-726-5054, Eking@firstenergycorp.com, 1500 Pennsylvania Avenue W, Warren, PA 16365 | DID NOT RESPOND per one call. Per initial site visit OH E/T/CATV 40 ft rt (looking north). Light Pole 10 ft rt south of bridge behind guardrail. Sent it to West Penn by mistake and they responded no facilities in the area on 7/16/15. Sent to Penelec on 7/17/15. | OH |  |  | 2016-06-16
69d | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | sanitary | Bradford TWP | Ken Swanson, 814-362-4431, swanbagger@gmail.com, 136 Hemlock St. Bradford, PA 16701 | Field Marked. Contact Ken Swanson 5 days prior to survey in order to coordinate the layout of his facilities. (Per one call) | UG |  |  | 2016-06-16
69e | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | Comm | Verizon Pennsylvania LLC | Susan Hoover, susan.a.hoover@verizon.com, 814-368-8404, 30 E Corydon St, Bradford, PA 16701; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH E/T/CATV 40 ft rt (looking north). | OH |  |  | 2016-06-16
69f | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Per initial site visit OH E/T/CATV 40 ft rt (looking north). Not a comcast area |  |  |  | 2016-06-16
69g | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | Comm | Atlantic Broadband | Dana Wells, 814-368-4541, dwells@atlanticbb.com, 24 Main St, Bradford, PA 16701 | Per initial site visit OH E/T/CATV 40 ft rt (looking north). | OH |  |  | 2016-06-16
70a | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | Comm | Comcast Cable Communications, Inc. | Doug Olszewski, douglas_olszewski@cable.comcast.com, 724-459-9042 x72661 | Conflict. Lines Nearby per one call. Per initial site visit OH E/CATV 40 ft rt (looking north). Have fiber and coax on poles. | OH |  |  | 2016-08-12
70b | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Design Conflict. Please send plans to: Andrew Black UGI Central Penn Gas 225 Morgantown Rd Reading PA 19611. (per one call) Per initial site visit 4 " poly gas main crosses road perp. 14 ft south of bridge and 3 " steel gas main crosses road perp. 39 ft south of bridge. | UG |  |  | 2016-08-12
70c | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | Gas | Vineyard Oil & Gas CO | Eric (Skippy) Canfield, 814-572-6010, Skippy33canfield@yahoo.com, 10299 W Main Street, North East, PA 16428 | Marked. Gas line runs under pavement at edge of bridge. Skip stated that UGI owns gas lines in this area as well. Call Skippy 5 days in advance of surveying in order for him to mark the line/s at the site. Per initial site visit 4 " poly gas main crosses road perp. 14 ft south of bridge and 3 " steel gas main crosses road perp. 39 ft south of bridge. | UG |  |  | 2016-08-12
70d | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | DID NOT RESPOND per one call. Per initial site visit OH E/CATV 40 ft rt (looking north). Not their facilities. |  |  |  | 2016-08-12
70e | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | Elect | Pennsylvania Electric Company | Edward (Ed) King, 814-726-5054, Eking@firstenergycorp.com, 1500 Pennsylvania Avenue W, Warren, PA 16365 | Per initial site visit OH E/CATV 40 ft rt (looking north). | OH |  |  | 2016-08-12
70f | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | Comm | Verizon Pennsylvania LLC | Susan Hoover, susan.a.hoover@verizon.com, 814-368-8404, 30 E Corydon St, Bradford, PA 16701; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Design stated that verizon was on the poles | OH |  |  | 2016-08-12
71a | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | Gas | Dominion Transmission Inc Luthersburg | Russell (Russ) Gregory, 814-583-1007, russell.l.gregory@dom.com; Andrew (Andy) Haag, Andrew.P.Haag@dom.com, 814-771-3590 | Conflict. Lines Nearby. Two lines in the same ROW that go under the bridge. Lines were marked. Please see utility map located in the one call folder for this bridge in sharepoint. Per initial site visit 14" gas crosses road north of bridge and 12" (tagged LN-10) crosses bridge diagonal from north to south. The 12" is abandoned being used as anode and the 14" is high pressure line. | UG |  |  | 2016-09-27
71b | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 |  | Sergeant TWP | Russ Braun, 814-723-3775 | DID NOT RESPOND per one call. Confirmed no utilities on phone 8/5/15. |  |  |  | 2016-09-27
71c | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call. No utilities per verification. |  |  |  | 2016-09-27
71d | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | Elect | West Penn Power | engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com, 724-548-3578 | Conflict. Lines Nearby. No visible OH power per initial site visit. Confirmed no facilities during verification |  |  |  | 2016-09-27
71e | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | Comm | Windstream | Aldona (Ann) Pilarczyk, 319-790-6779, Aldona.Pilarczyk@windstream.com | Did not respond through one call but sent email in response with utility map and confirmed that they dont have any facilities. Please see utility map located in the one call folder for this bridge in sharepoint. Per initial site visit buried phone adjacent to bridge on east side and then crosses bridge on south side. No facilities. |  |  |  | 2016-09-27
71f | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 |  | No visible OH per initial site visit. | [5 empty] | 2016-09-27
72a | -- | 72 | 25500 | 78611 | 42200200320000 | 2 | McKean | BETULA | SR 2002 | WEST BRANCH POTATO CREEK | 42/212 - NORWICH | 41.6713 | -78.3998 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Design Conflict. Please send plans to: Andrew Black UGI Central Penn Gas 225 Morgantown Rd Reading PA 19611 (per one call) | UG |  |  | 2017-05-22
72b | -- | 72 | 25500 | 78611 | 42200200320000 | 2 | McKean | BETULA | SR 2002 | WEST BRANCH POTATO CREEK | 42/212 - NORWICH | 41.6713 | -78.3998 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. (Per one call) | UG |  |  | 2017-05-22
73a | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | wtr | Bradford City Water Auth | Kim Benjamin, 814-362-3004, watr@atlanticbb.net, 28 Kennedy St, Bradford, PA 16701 | Conflict. Lines Nearby (per one call). Verified that they don’t have facilities in the project area. |  |  |  | 2016-08-09
73b | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | sanitary | Bradford TWP | Ken Swanson, 814-362-4431, swanbagger@gmail.com, 136 Hemlock St. Bradford, PA 16701 | Conflict. Lines Nearby (per one call). | UG |  |  | 2016-08-09
73c | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | gas | Columbia Gas of PA Design | Shane Matejka, 724-421-3682, smatejka@nisource.com, 2021 West State Street New Castle, PA 16101 | Conflict. Lines Nearby (per one call). Per initial site visit exposed at creek 15 ft lt (looking north) | UG |  |  | 2016-08-09
73d | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. (Per one call). Have 16" main about 300 ft east of bridge | UG | 16" |  | 2016-08-09
73e | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | Elect | Pennsylvania Electric Company | Edward (Ed) King, 814-726-5054, Eking@firstenergycorp.com, 1500 Pennsylvania Avenue W, Warren, PA 16365 | Per initial site visit OH E/T/CATV 6-20 ft lt (looking north) tag C1-19, VZ 72-49 | OH |  |  | 2016-08-09
73f | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | Comm | Verizon Pennsylvania LLC | Susan Hoover, susan.a.hoover@verizon.com, 814-368-8404, 30 E Corydon St, Bradford, PA 16701; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH E/T/CATV 6-20 ft lt (looking north) tag C1-19, VZ 72-49 | OH |  |  | 2016-08-09
73g | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | Comm | Comcast Cable Communications, Inc. | Mark Veltman, Mark_Veltman@cable.comcast.com | Per initial site visit OH E/T/CATV 6-20 ft lt (looking north) tag C1-19, VZ 72-49. Not their facilities may be Tim Warner. |  |  |  | 2016-08-09
73h | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | Comm | Time Warner Cable | Jeff Bohne, 607-798-0422, jeff.bohne@twcable.com | Per comcast the cable may be Time Warner. Not Time Warner. |  |  |  | 2016-08-09
73i | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | Comm | Atlantic Broadband | Dana Wells, 814-368-4541, dwells@atlanticbb.com, 24 Main St, Bradford, PA 16701 | Per Verizon Atlantic BB is on the poles. OH cable and fiber on poles | OH |  |  | 2016-08-09
74a | -- | 74 | 26468 | 4642 | 44065502201820 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | FROG HOLLOW RUN | 44/209 - UNION | 40.6278 | -77.6746 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Conflict. Lines Nearby (per one call). | OH |  |  | 2017-05-15
74b | -- | 74 | 26468 | 4642 | 44065502201820 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | FROG HOLLOW RUN | 44/209 - UNION | 40.6278 | -77.6746 | wtr | Lewistown Borough Municipal Auth | Craig Bubb, 717-248-0165 | Marked (per one call). | UG |  |  | 2017-05-15
74c | -- | 74 | 26468 | 4642 | 44065502201820 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | FROG HOLLOW RUN | 44/209 - UNION | 40.6278 | -77.6746 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net; 201 Poplar Road Lewistown, PA 17044 | DID NOT RESPOND per one call. Spoke to them on 8/21/15 and they have OH facilities near bridge. | OH |  |  | 2017-05-15
75a | -- | 75 | 26469 | 85297 | 44065502300022 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | ALEXANDER RUN | 44/209 - UNION | 40.6279 | -77.6742 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Field Marked per one call. | UG |  |  | 2017-05-15
75b | -- | 75 | 26469 | 85297 | 44065502300022 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | ALEXANDER RUN | 44/209 - UNION | 40.6279 | -77.6742 |  | Lewistown Borough Municipal Auth | Craig Bubb, 717-248-0165 | Field Marked per one call. | UG |  |  | 2017-05-15
75c | -- | 75 | 26469 | 85297 | 44065502300022 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | ALEXANDER RUN | 44/209 - UNION | 40.6279 | -77.6742 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net; 201 Poplar Road Lewistown, PA 17044 | DID NOT RESPOND per one call. Spoke to them on 8/21/15 and they have OH facilities near bridge. | OH |  |  | 2017-05-15
76a | -- | 76 | 26472 | 4676 | 44100200800896 | 2 | Mifflin | 3 MI NE REEDSVILLE | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.6888 | -77.5584 |  | Armagh TWP Authority/Armagh TWP | 717-667-6260 | Field Marked per one call. | UG |  |  | 2017-05-26
76b | -- | 76 | 26472 | 4676 | 44100200800896 | 2 | Mifflin | 3 MI NE REEDSVILLE | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.6888 | -77.5584 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Field Marked per one call. | UG |  |  | 2017-05-26
76c | -- | 76 | 26472 | 4676 | 44100200800896 | 2 | Mifflin | 3 MI NE REEDSVILLE | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.6888 | -77.5584 |  | Lewistown Borough Municipal Auth | Craig Bubb, 717-248-0165 | Field Marked per one call. | UG |  |  | 2017-05-26
77 | -- | 77 | 26477 | 4677 | 44100201200618 | 2 | Mifflin | LOCKE MILLS | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.7052 | -77.5347 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | Field Marked per one call. | UG |  |  | 2017-06-01
78a | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby (per one call). Per initial site visit OH E/T/CATV far lt of bridge (looking north). OH E/T/CATV crosses road about 35 ft north of bridge. | OH |  |  | 2016-07-05
78b | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net; 201 Poplar Road Lewistown, PA 17044 | DID NOT RESPOND per one call. Spoke to them on 8/21/15 and they do not have facilities at this bridge. |  |  |  | 2016-07-05
78c | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | Comm | Verizon Pennsylvania LLC | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com, 250 S ALLEN ST, STATE COLLEGE, PA 16801 | Per initial site visit OH E/T/CATV far lt of bridge (looking north) and OH T/CATV rt of bridge (looking north). On power poles and also on the east side of bridge on their on poles | OH |  |  | 2016-07-05
78d | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | Comm | Nittany Media Inc. | Craig Yohn, 717-248-3733, cyohn@nmax.net | Per initial site visit OH E/T/CATV far lt of bridge (looking north) and OH T/CATV rt of bridge (looking north). On power poles | OH |  |  | 2016-07-05
79a | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | sanitary | Coudersport Area Municipal Auth | Beverly Morris, 814-274-9776, coudyboro@zitomedia.net, John Segursky (Uni-Tech Consultant Engineers) | Field Marked per one call. | UG |  |  | 2017-05-30
79b | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | wtr | Coudersport Borough Authority | Beverly Morris, 814-274-9776, coudyboro@zitomedia.net, Patrick Ward (Uni-Tech Consultant Engineers) | DID NOT RESPOND per one call |  |  |  | 2017-05-30
79c | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | wtr | Coudersport Borough Authority | Beverly Morris, 814-274-9776, coudyboro@zitomedia.net, Patrick Ward (Uni-Tech Consultant Engineers) | Field Marked per one call. | UG |  |  | 2017-05-30
79d | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-05-30
80a | -- | 80 | 30144 | 69501 | 52004402700000 | 2 | Potter | CARTER CAMP | SR 44-PA 44 | LITTLE KETTLE CREEK | 52/201 - ABBOTT | 41.625 | -77.7181 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-03-21
80b | -- | 80 | 30144 | 69501 | 52004402700000 | 2 | Potter | CARTER CAMP | SR 44-PA 44 | LITTLE KETTLE CREEK | 52/201 - ABBOTT | 41.625 | -77.7181 | comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Marked. Please see utility map located in the one call folder for this bridge in sharepoint. (Per one call) | UG |  |  | 2017-03-21
81a | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | sanitary | Hebron TWP | Roger Bickleman, 814-698-2120, hebrontwp@zitomedia.net, 786 Baker Creek Rd. Coudersport PA 16915 | DID NOT RESPOND per one call. Confirmed on 10/8/15 that they don’t have any facilities |  |  |  | 2016-07-06
81b | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | Elect | Tri-County Rural Electric Cooperative Inc. | John Rotello, 814-274-7365, johnr@ctenterprises.com | Per initial site visit OH power to far right (looking north) | OH |  |  | 2016-07-06
81c | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | Comm | Frontier Communications | Jan Kapson, Jan.Kapson@FTR.com, 570-673-7107, 19 North Center Street P.O. Box 216, Canton Pa. 17724 | Per initial site visit OH T/CATV rt of bridge (looking north). Not their facility |  |  |  | 2016-07-06
81d | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Per initial site visit OH T/CATV rt of bridge (looking north) | OH |  |  | 2016-07-06
81e | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | Gas | National Fuel Gas Supply Corporation & National Fuel Gas Distribution Corporation (joint partnership with Kinder Morgan) | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | Conflict. Lines Nearby. 16" line. Caution! There are gas transmission lines in the area of the proposed excavation. Do not dig. NATIONAL FUEL must be on site prior to any excavation near those lines. Tennessee Gas Pipeline and National Fuel share ownership on a couple pipelines and gathering lines within close proximity to your proposed bridge project and National Fuel is the operator and the owner of the pipeline data and Right of Way files. Action: Contact Nick Allen 5 days prior to surveying so he can layout the gas pipelines. Per initial visit there is high pressure UG gas and oil cross road approx. 80 ft south of bridge. (per one call) | UG | 16 and 24" |  | 2016-07-06
81f | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | Comm | Verizon Pennsylvania LLC | Susan Hoover, susan.a.hoover@verizon.com, 814-368-8404, 30 E Corydon St, Bradford, PA 16701; Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH T/CATV rt of bridge (looking north). Per Frontier it may be Verizon | OH |  |  | 2016-07-06
82a | -- | 82 | 30162 | 85309 | 52004409500000 | 2 | Potter | CLARA | SR 44-PA 44 | CLARA CREEK | 52/204 - CLARA | 41.9114 | -78.0977 | Comm | Frontier Communications | Jan Kapson, Jan.Kapson@FTR.com, 570-673-7107, 19 North Center Street P.O. Box 216, Canton Pa. 17724 | DID NOT RESPOND per one call |  |  |  | 2017-05-15
82b | -- | 82 | 30162 | 85309 | 52004409500000 | 2 | Potter | CLARA | SR 44-PA 44 | CLARA CREEK | 52/204 - CLARA | 41.9114 | -78.0977 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION (coowned with Tennessee Gas Pipeline but operated by National) | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. (Per one call). Got call on 8/14/15 that they have facilities close to the bridge. | UG |  |  | 2017-05-15
82c | -- | 82 | 30162 | 85309 | 52004409500000 | 2 | Potter | CLARA | SR 44-PA 44 | CLARA CREEK | 52/204 - CLARA | 41.9114 | -78.0977 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-05-15
83a | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | Gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. (Per one call). Confirmed no facilities in the area. |  |  |  | 2016-06-14
83b | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | Gas | Alma Gas Inc | 814-225-3480 | DID NOT RESPOND per one call. Contacted 9/14/15 and no facilities in the area of the project. |  |  |  | 2016-06-14
83c | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | Gas | Maxson Gas Corp | 717-485-5670 | Initially DID NOT RESPOND per one call, but followed up clear. |  |  |  | 2016-06-14
83d | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | sanitary | Sharon TWP | 814-697-7316, 1972 SR 44 South Shinglehouse, PA 16748 | DID NOT RESPOND per one call. Followed up with phone call on 9/14 that they have no facilities at this location |  |  |  | 2016-06-14
83e | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Design Conflict. Please send plans to: Andrew Black UGI Central Penn Gas 225 Morgantown Rd Reading PA 19611 (per one call). Per initial site visit UGI gas. | UG | 4" |  | 2016-06-14
83f | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | Elect | Pennsylvania Electric Company | Edward (Ed) King, 814-726-5054, Eking@firstenergycorp.com, 1500 Pennsylvania Avenue W, Warren, PA 16365 | Per initial site visit OH E/T/CATV 6' rt (looking east). | OH |  |  | 2016-06-14
83g | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | Comm | Frontier Communications | Jan Kapson, Jan.Kapson@FTR.com, 570-673-7107, 19 North Center Street P.O. Box 216, Canton Pa. 17724; Paul Kerswill, paul.kerswill@ftr.com, 814-697-6102 | Per initial site visit OH E/T/CATV 6' rt (looking east). | OH |  |  | 2016-06-14
83h | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | Comm | Time Warner Cable | Jeff Bohne, 607-798-0422, jeff.bohne@twcable.com | Per initial site visit OH E/T/CATV 6' rt (looking east). Not their facilities |  |  |  | 2016-06-14
83i | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Per initial site visit OH E/T/CATV 6' rt (looking east). | OH |  |  | 2016-06-14
84a | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | sanitary | Harrison TWP | Kim Talbett, 814-334-5425, harrisontwp@verizon.net, 205 E. Main Street, Harrison Valley, PA 16927 | Marked per one call. | UG |  |  | 2016-04-04
84b | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | Elect | Pennsylvania Electric Company | Daniel Strein, 570-268-4537, dstrein@firstenergycorp.com; John Forbes, 814-676-7551, jforbes@firstenergycorp.com (manager), 873 S Main Steet, Mansfield, PA 16933 | DID NOT RESPOND per one call. Per initial site visit OH E/T/CATV 8 ft rt (looking east) | OH |  |  | 2016-04-04
84c | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Marked (per one call). Per initial site visit UGI gas right of OH power. | UG |  |  | 2016-04-04
84d | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | Comm | Verizon Pennsylvania LLC | Jason Wagner, 570-327-7891, jason.e.wagner@verizon.com, 404 W 4th Street, Williamsport, PA 17701 | Per initial site visit OH E/T/CATV 8 ft rt (looking east) | OH |  |  | 2016-04-04
84e | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Per initial site visit OH E/T/CATV 8 ft rt (looking east). Facilities attached to poles on north side of bridge. | OH |  |  | 2016-04-04
85a | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | sanitary | Harrison TWP | Kim Talbett, 814-334-5425, harrisontwp@verizon.net, 205 E. Main Street, Harrison Valley, PA 16927 | Marked per one call. | UG |  |  | 2016-06-08
85b | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | Elect | Pennsylvania Electric Company | Daniel Strein, 570-268-4537, dstrein@firstenergycorp.com; John Forbes, 814-676-7551, jforbes@firstenergycorp.com (manager), 873 S Main Steet, Mansfield, PA 16933 | DID NOT RESPOND per one call. Per initial site visit there is OH E/T/CATV. Lines cross bridge from a pole located 100ft west of bridge 10 ft rt of EOP (looking east) to a pole located 60 ft east of bridge 5' left of EOP (looking east). | OH |  |  | 2016-06-08
85c | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Marked per one call. | UG |  |  | 2016-06-08
85d | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | Comm | Verizon Pennsylvania LLC | Jason Wagner, 570-327-7891, jason.e.wagner@verizon.com, 404 W 4th Street, Williamsport, PA 17701 | Per initial site visit there is OH E/T/CATV. Lines cross bridge from a pole located 100ft west of bridge 10 ft rt of EOP (looking east) to a pole located 60 ft east of bridge 5' left of EOP (looking east). | OH |  |  | 2016-06-08
85e | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Per initial site visit there is OH E/T/CATV. Lines cross bridge from a pole located 100ft west of bridge 10 ft rt of EOP (looking east) to a pole located 60 ft east of bridge 5' left of EOP (looking east). | OH |  |  | 2016-06-08
86a | -- | 86 | 30233 | 4899 | 52044900501401 | 2 | Potter | 2 MI N WALTON | SR 449-PA 449 | BUCKSELLER RUN | 52/223 - ULYSSES | 41.8127 | -77.7879 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-06-15
86b | -- | 86 | 30233 | 4899 | 52044900501401 | 2 | Potter | 2 MI N WALTON | SR 449-PA 449 | BUCKSELLER RUN | 52/223 - ULYSSES | 41.8127 | -77.7879 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | DID NOT RESPOND per one call |  |  |  | 2017-06-15
87 | -- | 87 | 30348 | 93373 | 52200201302331 | 2 | Potter | 2 MI SW GERMANIA STATION | SR 2002 | LYMAN RUN | 52/224 - WEST BRANCH | 41.7032 | -77.7375 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-05-23
88a | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 | gas | National Fuel Gas Distribution Corporation | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com, 1100 State Street, Erie, PA 16501; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. (Per one call) | UG |  |  | 2017-05-25
88b | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 |  | Roulette TWP | Terry Meyers, 814-544-7549, roulettetwp@gmail.com, 424 Railroad Ave Roulette, PA 16746 | Field Marked per one call. | UG |  |  | 2017-05-25
88c | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND per one call |  |  |  | 2017-05-25
88d | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | DID NOT RESPOND per one call |  |  |  | 2017-05-25
89a | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | wtr and sanitary | Troy Borough | Daniel (Dan) Close (Mgr), 570-297-2966, danclose@troyborough.com, 49 Elmira Street Troy, Pa. 16947 | DID NOT RESPOND per one call. Per initial site visit there is water and sewer | UG |  |  | 2017-02-13
89b | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Design Conflict. Please send plans to: Andrew Black UGI Central Penn Gas 225 Morgantown Rd Reading PA 19611 (per one call). Per initial site visit there is gas | UG |  |  | 2017-02-13
89c | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | Elect | Pennsylvania Electric Company | Daniel Strein, 570-268-4537, dstrein@firstenergycorp.com; John Forbes, 814-676-7551, jforbes@firstenergycorp.com (manager), 873 S Main Steet, Mansfield, PA 16933 | Per initial site visit there is OH power. Pole is 1' rt (looking north). Power crosses road just north of bridge and heads west along the north bank of creek. | OH |  |  | 2017-02-13
89d | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | Comm | Frontier Communications | John Smithkors, john.smithkors@frontiercorp.com, 570-924-0094 | Per initial site visit there is OH phone. Pole is 1' rt (looking north). Phone and catv cross road just north of bridge to pole located at the "western alliance" building. Have fiber and copper on power poles. | OH |  |  | 2017-02-13
89e | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | Comm | Blue Ridge Communications | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675, PO Box 141, Tunkhannock Pa 18657 | Per initial site visit there is OH catv. Pole is 1' rt (looking north). Phone and catv cross road just north of bridge to pole located at the "western alliance" building. | OH |  |  | 2017-02-13
90a | Y | 90 | 6104 | 99281 | 8018704000000 | 3 | Bradford | 1 MILE SOUTH OF DURELL | SR 0187 | DURELL CREEK | 08/203 - ASYLUM | 41.7171 | -76.3591 | Comm | Frontier Communications | John Smithkors (570) 265-7775 | Station 2021 to Station 2023+75 | OH |  | Coordinated | 2016-03-16
90b | Y | 90 | 6104 | 99281 | 8018704000000 | 3 | Bradford | 1 MILE SOUTH OF DURELL | SR 0187 | DURELL CREEK | 08/203 - ASYLUM | 41.7171 | -76.3591 | Elect | Claverack Rural Electric Cooperative, Inc. | Debbie Allyn (570) 268-1308 | Station 2016 to Station 2024 | OH |  | Not Affected | 2016-03-16
91a | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | wtr | Towanda WTR & SWR/Towanda Borough | Fred Johnson, 570-265-5151, freddj@epix.net | Marked. Received initial plan review info on 5/26/15. | UG |  |  | 2016-06-06
91b | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com; Dan Dieffenbach, ddieffenbach@firstenergycorp.com | DID NOT RESPOND per one call. Per initial site visit there is OH power. Per Penelec this is not their facilities - 5/27/15 |  |  |  | 2016-06-06
91c | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | Comm | Frontier Communications | John Smithkors, john.smithkors@frontiercorp.com, 570-924-0094 | Per initial site visit OH T/CATV. Got contact info from district 3 utility coordinator | OH |  |  | 2016-06-06
91d | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | Comm | Blue Ridge Communications | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675, PO Box 141, Tunkhannock Pa 18657 | Per initial site visit OH T/CATV. Got contact info from district 3 utility coordinator | OH |  |  | 2016-06-06
91e | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | Elect | Claverack Rural Electric Cooperative, Inc. | Debbie Allyn, debbiea@ctenterprises.org, (570) 268-1308; Charles Goodwin (Field Tech), 1-800-326-9799 | Per initial site visit there is OH power. | OH |  |  | 2016-06-06
92a | Y | 92 | 6164 | 5093 | 8036700101794 | 3 | Bradford | 3.5 MI.SOUTH OF SILVARA | SR 0367 | FARGO CREEK | 08/230 - TUSCARORA | 41.6554 | -76.1377 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | Station 18+00 to Station 19+55 | OH |  | Coordinated | 2015-06-01
92b | Y | 92 | 6164 | 5093 | 8036700101794 | 3 | Bradford | 3.5 MI.SOUTH OF SILVARA | SR 0367 | FARGO CREEK | 08/230 - TUSCARORA | 41.6554 | -76.1377 | Comm | Frontier Communications | Jeff Bolton (570) 406-5319 | Station 18+00 to Station 19+55 | OH |  | Coordinated | 2015-06-01
92c | Y | 92 | 6164 | 5093 | 8036700101794 | 3 | Bradford | 3.5 MI.SOUTH OF SILVARA | SR 0367 | FARGO CREEK | 08/230 - TUSCARORA | 41.6554 | -76.1377 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | Station 18+00 to Station 19+55 | OH |  | Coordinated | 2015-06-01
93a | -- | 93 | 6191 | 79247 | 8041403800000 | 3 | Bradford | VILLAGE OF FRANKLINDALE | SR 414 | TRIB.TO TOWANDA CREEK | 08/209 - FRANKLIN | 41.7028 | -76.5568 |  | Franklin TWP | 570-364-5713, franklin.township.bc@gmail.com | DID NOT RESPOND per one call. Confirmed no facilities on 9/23/15 |  |  |  | 2016-06-16
93b | -- | 93 | 6191 | 79247 | 8041403800000 | 3 | Bradford | VILLAGE OF FRANKLINDALE | SR 414 | TRIB.TO TOWANDA CREEK | 08/209 - FRANKLIN | 41.7028 | -76.5568 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com; Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 570-265-1264 | OH power that crosses road west of bridge several hundred feet. | OH |  |  | 2016-06-16
93c | -- | 93 | 6191 | 79247 | 8041403800000 | 3 | Bradford | VILLAGE OF FRANKLINDALE | SR 414 | TRIB.TO TOWANDA CREEK | 08/209 - FRANKLIN | 41.7028 | -76.5568 | comm | Frontier Communications | Jan Kapson, Jan.Kapson@FTR.com, 570-673-7107, 19 North Center Street P.O. Box 216, Canton Pa. 17724 | OH phone crosses east of bridge. | OH |  |  | 2016-06-16
94a | Y | 94 | 6193 | 76863 | 8046700100052 | 3 | Bradford | 2 MILE SOUTH OF ROME BORO | SR 467 | WYSOX CREEK | 08/220 - ROME | 41.8304 | -76.3501 | Comm | Beaver Valley TV | Doug Soden (570) 247-2512 | Station 397+30 LT | OH |  | Prior | 2016-01-08
94b | Y | 94 | 6193 | 76863 | 8046700100052 | 3 | Bradford | 2 MILE SOUTH OF ROME BORO | SR 467 | WYSOX CREEK | 08/220 - ROME | 41.8304 | -76.3501 | Comm | Frontier Communications | Steve Lathrop (570) 278-0036 | Station 397+30 LT | OH |  | Prior | 2016-01-08
94c | Y | 94 | 6193 | 76863 | 8046700100052 | 3 | Bradford | 2 MILE SOUTH OF ROME BORO | SR 467 | WYSOX CREEK | 08/220 - ROME | 41.8304 | -76.3501 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | Station 339+00 LT | OH |  | Coordinated | 2016-01-08
95a | Y | 95 | 6203 | 5210 | 8046702700000 | 3 | Bradford | PIKE TWP .4M S SR 1013 | SR 467 | OVER ROCKWELL CREEK | 08/218 - PIKE | 41.8231 | -76.1839 | Comm | Frontier Communications | Steve Lathrop (570) 278-0036 | Station 646+40 LT | OH |  | Prior | 2015-09-09
95b | Y | 95 | 6203 | 5210 | 8046702700000 | 3 | Bradford | PIKE TWP .4M S SR 1013 | SR 467 | OVER ROCKWELL CREEK | 08/218 - PIKE | 41.8231 | -76.1839 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | Station 650+10 | UG |  | Not Affected | 2015-09-09
96a | Y | 96 | 6216 | 5039 | 8051402000863 | 3 | Bradford | 2.5 MI.N.OF W.FRANKLIN | SR 0514 | N BR TOWANDA CREEK | 08/210 - GRANVILLE | 41.7132 | -76.6387 | Comm | Frontier Communications | Jan Kapson (570) 673-7107 | Station 67+80 to Station 70+00 | OH |  | Prior | 2016-03-28
96b | Y | 96 | 6216 | 5039 | 8051402000863 | 3 | Bradford | 2.5 MI.N.OF W.FRANKLIN | SR 0514 | N BR TOWANDA CREEK | 08/210 - GRANVILLE | 41.7132 | -76.6387 | Elect | Claverack Rural Electric Cooperative, Inc. | Charles Goodwin (570) 406-5992 | Station 69+50 Rt | OH |  | Coordinated | 2016-03-28
96c | Y | 96 | 6216 | 5039 | 8051402000863 | 3 | Bradford | 2.5 MI.N.OF W.FRANKLIN | SR 0514 | N BR TOWANDA CREEK | 08/210 - GRANVILLE | 41.7132 | -76.6387 | Elect | Claverack Rural Electric Cooperative, Inc. | Charles Goodwin (570) 406-5992 | Station 69+50 Rt | OH |  | Coordinated | 2016-03-28
97a | Y | 97 | 6224 | 5208 | 8070601701340 | 3 | Bradford | 2 MI. NE. OF CAMPTOWN | SR 0706 | COLD CREEK | 08/226 - STEVENS | 41.7477 | -76.2075 | Elect | Southwestern Energy Company | Steve Loop (570) 996-4259 | Station 913+00 to Station 916+00 | OH |  | Coordinated | 2015-08-24
97b | Y | 97 | 6224 | 5208 | 8070601701340 | 3 | Bradford | 2 MI. NE. OF CAMPTOWN | SR 0706 | COLD CREEK | 08/226 - STEVENS | 41.7477 | -76.2075 | Water | Southwestern Energy Company | Steve Loop (570) 996-4259 | Station 916+25 | UG |  | Not Affected | 2015-08-24
98a | Y | 98 | 6227 | 5215 | 8070602601160 | 3 | Bradford | STEVENS TWP .1M E LR08034 | SR 0706 | OVER ROSS CREEK | 08/226 - STEVENS | 41.7808 | -76.1399 | Comm | Frontier Communications | Steve Lathrop (570) 278-0036 | Station 1150+00 to Station 1159+47 | UG |  | Not Affected | 2016-02-15
98b | Y | 98 | 6227 | 5215 | 8070602601160 | 3 | Bradford | STEVENS TWP .1M E LR08034 | SR 0706 | OVER ROSS CREEK | 08/226 - STEVENS | 41.7808 | -76.1399 | Elect | Southwestern Energy Company | Steve Loop (570) 996-4259 | Station 1150+00 to Station 1159+47 | UG |  | Not Affected | 2016-02-15
99a | -- | 99 | 6348 | 98535 | 8105900700582 | 3 | Bradford | 1 MI. W. OF WARREN CENTER | SR 1059 | OVER WAPPASENING CREEK | 08/232 - WARREN | 41.9375 | -76.1941 |  | all facilities responded clear per one call | [5 empty] | 2016-08-15
99b | -- | 99 | 6348 | 98535 | 8105900700582 | 3 | Bradford | 1 MI. W. OF WARREN CENTER | SR 1059 | OVER WAPPASENING CREEK | 08/232 - WARREN | 41.9375 | -76.1941 | comm | Frontier Communications | Steven (Steve) Lathrop, 570-278-0036, Steven.Lathrop@FTR.com | Per initial site visit OH phone crosses bridge. | OH |  |  | 2016-08-15
99c | -- | 99 | 6348 | 98535 | 8105900700582 | 3 | Bradford | 1 MI. W. OF WARREN CENTER | SR 1059 | OVER WAPPASENING CREEK | 08/232 - WARREN | 41.9375 | -76.1941 | Elect | Pennsylvania Electric Company | Steve Beers, 570-265-1237, sbeers@firstenergycorp.com; Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 570-265-1264 | Per MOAS plans there is OH electric | OH |  |  | 2016-08-15
99d | -- | 99 | 6348 | 98535 | 8105900700582 | 3 | Bradford | 1 MI. W. OF WARREN CENTER | SR 1059 | OVER WAPPASENING CREEK | 08/232 - WARREN | 41.9375 | -76.1941 | Gas | Talisman Energy USA Inc. | Matt Tice, 607-857-0802, mtice@talismanusa.com, 337 Daniel Zenker Drive, Horseheads, NY 14845 | Clear per one call, however picked up by surveyors. | UG |  |  | 2016-08-15
100a | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 |  | all facilities responded clear per one call | [5 empty] | 2016-09-12
100b | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 | Elect | Pennsylvania Electric Company | John Forbes, 814-676-7551, jforbes@firstenergycorp.com | Per initial site visit OH power 15' right (looking north) and it crosses road just north of bridge at intersection with Mary Hill Rd. | OH |  |  | 2016-09-12
100c | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 | Comm | Blue Ridge Communications | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675, PO Box 141, Tunkhannock Pa 18657 | Per initial site visit OH comm 15' right (looking north) and it crosses road just north of bridge at intersection with Mary Hill Rd. | OH |  |  | 2016-09-12
100d | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 | Gas | UGI | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Clear per one call. However lines were picked up in survey. Own lines but should not be affected. | UG |  |  | 2016-09-12
100e | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 | Comm | North Penn Telephone Company | Cody Morgan, 570-549-7525, CMorgan@etcnpt.com | Per survey there is OH phone | OH |  |  | 2016-09-12
101a | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 |  | all facilities responded clear per one call | [5 empty] | 2016-08-08
101b | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | Per initial site visit OH E/T/CATV 16 ft lt (facing east), Pole tag 4T1199, 31472N34348. PPL katapult and attachers list available. | OH |  |  | 2016-08-08
101c | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 | Comm | Verizon Pennsylvania LLC | Robert (Rob) Jaworski, 570-387-3172, robert.m.jaworski@verizon.com, 11 Ridge Road, Bloomsburg PA 17815 | Per initial site visit OH E/T/CATV 16 ft lt (facing east), Pole tag 4T1199, 31472N34348. fiber and copper cable on PPL poles | OH |  |  | 2016-08-08
101d | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 | Comm | Metrocast Cable | David (Dave) Richards, 570-802-5642, drichards@metrocast.com; Jon Hughes (technical supervisor), jon.hughes@metrocast.com, 570-802-5642 x1199, 911 North Market Street, Berwick, PA 18603 | Per initial site visit OH E/T/CATV 16 ft lt (facing east), Pole tag 4T1199, 31472N34348 |  |  |  | 2016-08-08
102a | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Comm | Metro Cast | Dave Richards (570) 802-5642 | Station 579+15 to Station 583+30 | OH |  | Coordinated | 2016-04-01
102b | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Comm | Metro Cast | Dave Richards (570) 802-5642 | Station 580+70 to Station 583+30 | OH |  | Coordinated | 2016-04-01
102c | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 579+15 to Station 583+50 | OH |  | Coordinated | 2016-04-01
102d | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 580+70 to Station 583+50 | OH |  | Coordinated | 2016-04-01
102e | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Comm | Verizon Pennsylvania LLC | Rob Jaworski (570) 387-3172 | Station 579+15 to Station 583+30 | OH |  | Coordinated | 2016-04-01
102f | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Comm | Verizon Pennsylvania LLC | Rob Jaworski (570) 387-3172 | Station 580+70 to Station 583+30 | OH |  | Coordinated | 2016-04-01
102g | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Comm | Frontier Communications | Rob Januszko (570) 542-7116 | Station 579+15 to Station 583+30 | OH |  | Coordinated | 2016-04-01
102h | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | Comm | Frontier Communications | Rob Januszko (570) 542-7116 | Station 580+70 to Station 583+30 | OH |  | Coordinated | 2016-04-01
103a | Y | 103 | 12592 | 5578 | 19048703700177 | 3 | Columbia | 1 MILE N OF LIGHTSTREET | SR 487 | STONY BROOK CREEK | 19/219 - ORANGE | 41.0524 | -76.4285 | N/A | N/A | N/A | None | N/A |  | Not Affected | 2015-07-27
104a | Y | 104 | 12738 | 78822 | 19403101120000 | 3 | Columbia | 3 MI W OF WALLER | S.R. 4031 | OVER LITTLE FISHING CR. | 19/211 - JACKSON | 41.1988 | -76.4669 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 251+20 to Station 254+50 |  |  | Coordinated | 2015-07-13
104b | Y | 104 | 12738 | 78822 | 19403101120000 | 3 | Columbia | 3 MI W OF WALLER | S.R. 4031 | OVER LITTLE FISHING CR. | 19/211 - JACKSON | 41.1988 | -76.4669 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 | Station 251+20 to Station 254+50 |  |  | Coordinated | 2015-07-13
| R | 105 | 12745 | #REF! | 19403600120000 | 3 | Columbia | TOWN OF BLOOMSBURG | #N/A | OVER HEMLOCK CREEK | 19/211 - JACKSON | 41.1988 | -76.4669 | [7 empty] | 2015-07-13
106a | -- | 106 | 24511 | 91436 | 41001500702198 | 3 | Lycoming | 8 MILES S OF WILLIAMSPORT | SR 0015 | OVER BLACK HOLE CREEK | 41/207 - CLINTON | 41.1781 | -76.9111 | Gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com | One call stated that there was a conflict. Follow up email from UGI stated that they have no facilities in the area. | UG |  |  | 2017-02-21
106b | -- | 106 | 24511 | 91436 | 41001500702198 | 3 | Lycoming | 8 MILES S OF WILLIAMSPORT | SR 0015 | OVER BLACK HOLE CREEK | 41/207 - CLINTON | 41.1781 | -76.9111 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5308 for utility maps.Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. | UG |  |  | 2017-02-21
107a | Y | 107 | 24566 | 6049 | 41004403440880 | 3 | Lycoming | 4.5 MI S OF JERSEY SHORE | SR 44 | OVER ANTES CREEK | 41/218 - LIMESTONE | 41.164 | -77.2209 | Comm | Comcast Cable Communications, Inc. | Tim Creswell (570) 329-9821 | Station 143+95 to Station 153+20 | OH |  | Coordinated | 2015-07-27
107b | Y | 107 | 24566 | 6049 | 41004403440880 | 3 | Lycoming | 4.5 MI S OF JERSEY SHORE | SR 44 | OVER ANTES CREEK | 41/218 - LIMESTONE | 41.164 | -77.2209 | Comm | Pennsylvania Telephone Company | Timothy Reinhard (570) 745-7101 | Station 143+95 to Station 153+20 | OH |  | Coordinated | 2015-07-27
107c | Y | 107 | 24566 | 6049 | 41004403440880 | 3 | Lycoming | 4.5 MI S OF JERSEY SHORE | SR 44 | OVER ANTES CREEK | 41/218 - LIMESTONE | 41.164 | -77.2209 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 143+95 to 153+71 | OH |  | Coordinated | 2015-07-27
108a | -- | 108 | 24591 | 6023 | 41008700600000 | 3 | Lycoming | 0.1 MI N OF FARRAGUT | SR 0087 (LR 291) | OVER TRIB TO LOYALSOCK C | 41/238 - UPPER FAIRFIELD | 41.2972 | -76.906 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message per one call - UG facilities exist in project area. Please call 570-368-5394 for utility maps. Per PPL katapult map there is only OH. Also see pole attachers list. | OH |  |  | 2016-07-25
108b | -- | 108 | 24591 | 6023 | 41008700600000 | 3 | Lycoming | 0.1 MI N OF FARRAGUT | SR 0087 (LR 291) | OVER TRIB TO LOYALSOCK C | 41/238 - UPPER FAIRFIELD | 41.2972 | -76.906 | Comm | Herr Cable CO | RALPH HERR, 570-435-2656 or 570-435-2780, RR 4, Montoursville, PA 17754 | DID NOT RESPOND per one call. On the list of attachers from PPL. | OH |  |  | 2016-07-25
108c | -- | 108 | 24591 | 6023 | 41008700600000 | 3 | Lycoming | 0.1 MI N OF FARRAGUT | SR 0087 (LR 291) | OVER TRIB TO LOYALSOCK C | 41/238 - UPPER FAIRFIELD | 41.2972 | -76.906 | Comm | Frontier Communications | Robert (Rob) Januszko, Robert.Januszko@ftr.com, 570-542-7116, 67 S Main St, Shickshinny, PA 18655 | on the list of attachers from PPL. Have fiber on poles | OH |  |  | 2016-07-25
108d | -- | 108 | 24591 | 6023 | 41008700600000 | 3 | Lycoming | 0.1 MI N OF FARRAGUT | SR 0087 (LR 291) | OVER TRIB TO LOYALSOCK C | 41/238 - UPPER FAIRFIELD | 41.2972 | -76.906 | Comm | Verizon Pennsylvania LLC | Robert (Rob) Jaworski, 570-387-3172, robert.m.jaworski@verizon.com, 11 Ridge Road, Bloomsburg PA 17815 | on the list of attachers from PPL | OH |  |  | 2016-07-25
108e | -- | 108 | 24591 | 6023 | 41008700600000 | 3 | Lycoming | 0.1 MI N OF FARRAGUT | SR 0087 (LR 291) | OVER TRIB TO LOYALSOCK C | 41/238 - UPPER FAIRFIELD | 41.2972 | -76.906 | wtr | Private Water Main | Jeffrey Thomas, 570-435-5871, 2435 Rt 87 Hwy Montoursville, PA 17754 | did not show up on one call. Surveyors picked up a private 4" PVC line feeding a spring house. I spoke to Mrs. Thomas on 9/24/15 about the private line. She lives on the east side of SR 87 and her son lives on the west side. She said that the line is very old and was installed by her father or grandfather. They don’t have any information on depth | UG | 4" |  | 2016-07-25
109a | -- | 109 | 24603 | 6145 | 41011801700622 | 3 | Lycoming | VILLAGE OF LAIRDSVILLE | 118/TWP.RD.INTERS. | OVER BIG RUN | 41/212 - FRANKLIN | 41.2321 | -76.6095 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5308 for utility maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power/comm to far left of bridge (looking east). Comcast and Windstream are on pole according to PPL attachers list. | Both |  |  | 2016-05-31
109b | -- | 109 | 24603 | 6145 | 41011801700622 | 3 | Lycoming | VILLAGE OF LAIRDSVILLE | 118/TWP.RD.INTERS. | OVER BIG RUN | 41/212 - FRANKLIN | 41.2321 | -76.6095 | Comm | Windstream | Ken Stahlnecker, 570-546-9250, Kenneth.Stahlnecker@windstream.com, 690 East Penn Street, Muncy, PA 17756 | DID NOT RESPOND per one call. Per initial site visit OH E/CATV to far left and OH comm that crosses bridge diagonally from comm pole 42ft west of bridge and 22 ft rt of road (looking east) (near south driveway) to pole on east side of Dark Hollow Road 65 ft lt of road (looking east). On their own poles | OH |  |  | 2016-05-31
109c | -- | 109 | 24603 | 6145 | 41011801700622 | 3 | Lycoming | VILLAGE OF LAIRDSVILLE | 118/TWP.RD.INTERS. | OVER BIG RUN | 41/212 - FRANKLIN | 41.2321 | -76.6095 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Per initial site visit OH E/CATV to far left and OH comm that crosses bridge diagonally from comm pole 42ft west of bridge and 22 ft rt of road (looking east) (near south driveway) to pole on east side of Dark Hollow Road 65 ft lt of road (looking east). On power poles | OH |  |  | 2016-05-31
110a | -- | 110 | 24748 | 6045 | 41041400100417 | 3 | Lycoming | 2 MI N OF WATERVILLE | SR 414 | OVER UPPER PINE BOT.R. | 41/209 - CUMMINGS | 41.3207 | -77.3864 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Conflict. Lines Nearby per one call | OH |  |  | 2017-06-01
110b | -- | 110 | 24748 | 6045 | 41041400100417 | 3 | Lycoming | 2 MI N OF WATERVILLE | SR 414 | OVER UPPER PINE BOT.R. | 41/209 - CUMMINGS | 41.3207 | -77.3864 | Elect | West Penn Power | Zach Reedy (engineering supervisor), zreedy@firstenergycorp.com, 724-548-3578 | Conflict. Lines Nearby per pne call | OH |  |  | 2017-06-01
111a | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | Elect | Tri-County Rural Electric Cooperative Inc. | Jess Kipferl, 570-6723-3160 jessk@ctenterprises.com | Conflict. Lines Nearby per one call. Per initial site visit OH E/T 10' rt (looking east). OH power crosses road, heading north, east of bridge from pole 15 ft rt 110 ft east of bridge. Pole tag # WOC MCFC 3212 SIPA 45A 440, and Property of County REC Inc # 612/69/2. Verified that these are their facilities. | OH |  |  | 2016-06-01
111b | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | comm | Verizon Pennsylvania LLC | Jason Wagner, 570-327-7891, jason.e.wagner@verizon.com, 404 W 4th Street, Williamsport, PA 17701 | Per initial site visit OH comm to lt (looking east). Guy wire pole 45 ft west of bridge on right (looking east). Guy wire runs from pole and crosses road perpendicular to comm pole (tag # 276 (BTC of PA) F-27) on left side of road. OH comm 10' rt (looking east). Comm Pole (no #) 12' east of bridge 10' rt (looking east). Comm crosses road perpendicular from pole to comm on lt side of road. Responded that facilities are depicted correctly. | OH |  |  | 2016-06-01
111c | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | Comm | Blue Ridge Communications | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675, PO Box 141, Tunkhannock Pa 18657 | Per initial site visit OH comm to lt (looking east). Guy wire pole 45 ft west of bridge on right (looking east). Guy wire runs from pole and crosses road perpendicular to comm pole (tag # 276 (BTC of PA) F-27) on left side of road. OH comm 10' rt (looking east). Comm Pole (no #) 12' east of bridge 10' rt (looking east). Comm crosses road perpendicular from pole to comm on lt side of road. Verified it isnt their facilities and may be comcast. |  |  |  | 2016-06-01
111d | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com, 1020 Commerce Park Drive, Williamsport, PA 17701 | Per initial site visit OH comm to lt (looking east). Guy wire pole 45 ft west of bridge on right (looking east). Guy wire runs from pole and crosses road perpendicular to comm pole (tag # 276 (BTC of PA) F-27) on left side of road. OH comm 10' rt (looking east). Comm Pole (no #) 12' east of bridge 10' rt (looking east). Comm crosses road perpendicular from pole to comm on lt side of road. Verified it isnt Comcast. |  |  |  | 2016-06-01
111e | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Not comcast or blue ridge. Contacted Zito Media on 7/22. Also called and left VM with Herr Cable on 7/14 and 7/21. Confirmed that this is not Zito |  |  |  | 2016-06-01
112a | Y | 112 | 24850 | 6057 | 41200200320000 | 3 | Lycoming | 3 MI W OF ELIMSPORT | SR 2002 | OVER WHITE DEER HOLE CR | 41/239 - WASHINGTON | 41.1189 | -77.0668 | Comm | Comcast Cable Communications, Inc. | Richard Roberts (570) 329-9818 | Station 375+00 to Station 382+51 | OH |  | Prior | 2015-08-27
112b | Y | 112 | 24850 | 6057 | 41200200320000 | 3 | Lycoming | 3 MI W OF ELIMSPORT | SR 2002 | OVER WHITE DEER HOLE CR | 41/239 - WASHINGTON | 41.1189 | -77.0668 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 375+00 to Station 382+51 | OH |  | Prior | 2015-08-27
112c | Y | 112 | 24850 | 6057 | 41200200320000 | 3 | Lycoming | 3 MI W OF ELIMSPORT | SR 2002 | OVER WHITE DEER HOLE CR | 41/239 - WASHINGTON | 41.1189 | -77.0668 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kenneth C. Stahlnecker (570) 546-9250 | Station 375+00 to Station 382+51 | OH |  | Prior | 2015-08-27
113a | -- | 113 | 24881 | 6052 | 41201501720000 | 3 | Lycoming | 1 MI NORTH OF LAIRDSVILLE | SR 2015 | OVER BIG RUN | 41/212 - FRANKLIN | 41.2445 | -76.6174 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5308 for utility maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. | UG |  |  | 2017-06-27
113b | -- | 113 | 24881 | 6052 | 41201501720000 | 3 | Lycoming | 1 MI NORTH OF LAIRDSVILLE | SR 2015 | OVER BIG RUN | 41/212 - FRANKLIN | 41.2445 | -76.6174 | Gas | Regency Energy Partners (PVR Marcellus) |  | DID NOT RESPOND per one call |  |  |  | 2017-06-27
114a | Y | 114 | 24928 | 74022 | 41205000120000 | 3 | Lycoming | 2.5 MI E OF LAIRDSVILLE | SR 2050 | OVER LITTLE MUNCY CREEK | 41/216 - JORDAN | 41.2428 | -76.561 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 3+65 to 6+25 | OH |  | Coordinated | 2015-07-29
114b | Y | 114 | 24928 | 74022 | 41205000120000 | 3 | Lycoming | 2.5 MI E OF LAIRDSVILLE | SR 2050 | OVER LITTLE MUNCY CREEK | 41/216 - JORDAN | 41.2428 | -76.561 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 | Station 3+65 to 6+00 | OH |  | Coordinated | 2015-07-29
115a | -- | 115 | 24938 | 6144 | 41206101702204 | 3 | Lycoming | 3MI.E OF HUGHESVILLE | SR 2061 | OVER SUGAR RUN | 41/226 - MORELAND | 41.2432 | -76.6833 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | Station 3+65 to 6+00 | UG |  |  | 2017-08-01
115b | -- | 115 | 24938 | 6144 | 41206101702204 | 3 | Lycoming | 3MI.E OF HUGHESVILLE | SR 2061 | OVER SUGAR RUN | 41/226 - MORELAND | 41.2432 | -76.6833 | Comm | Windstream | Aldona (Ann) Pilarczyk, 319-790-6779, Aldona.Pilarczyk@windstream.com | Aerial fiber and copper lines on SR 2061 (Green Valley Rd). Please see utility map located in the one call folder for the bridge on sharepoint. | OH |  |  | 2017-08-01
116a | -- | 116 | 28361 | 6387 | 47025400200000 | 3 | Montour | 4.5 M W OF LIMESTONEVILLE | SR 254 | OVER LIMESTONE RUN | 47/205 - LIMESTONE | 41.0322 | -76.7506 | Comm | Verizon North LLC | Robert (Rob) Jaworski, 570-387-3172, robert.m.jaworski@verizon.com, 11 Ridge Road, Bloomsburg PA 17815 | Verizon does have underground cable at this location. Verizon does not send out prints, however, you can forward any maps/prints to the local Engineering Office at 15 East Montgomery Place, 2nd Floor, Pittsburgh, Pennsylvania 15212 to the attention of the Right of Way Department. Received marked up plans from Verizon on 5/26/15 and placed in share point. They are UG on south side of road and have aerial road crossing. | Both |  |  | 2016-04-06
116b | -- | 116 | 28361 | 6387 | 47025400200000 | 3 | Montour | 4.5 M W OF LIMESTONEVILLE | SR 254 | OVER LIMESTONE RUN | 47/205 - LIMESTONE | 41.0322 | -76.7506 | gas | UGI Penn Natural Gas, Inc. | Sharon Reese, 570-829-8754, sreese1@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | DID NOT RESPOND to one call. Sent map and location information on 6/19/15 | UG |  |  | 2016-04-06
116c | -- | 116 | 28361 | 6387 | 47025400200000 | 3 | Montour | 4.5 M W OF LIMESTONEVILLE | SR 254 | OVER LIMESTONE RUN | 47/205 - LIMESTONE | 41.0322 | -76.7506 |  | Unidentified Conduit Box | Unknown | There was no electric company listed on the one call however during the site visit a a 6”x6” metal conduit box was found located directly behind the guardrail on the left side of the road (facing east) just west of the bridge. Confirned with Verizon that it is not there box. Verified with PPL no facilities on 6/16/15. Verified with gas company not their facility on 6/23/15. | UG |  |  | 2016-04-06
117 | -- | 117 | 28387 | 6381 | 47100600100570 | 3 | Montour | 3 MI.N.WASHINGTONVILLE | SR 1006 | MCKEE CREEK | 47/201 - ANTHONY | 41.0928 | -76.7045 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5308 for utility maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. | UG |  |  | 2017-08-01
118a | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 225+75 Rt | OH |  | Coordinated | 2015-07-08
118b | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 225+75 to Station 228+00 | OH |  | Coordinated | 2015-07-08
118c | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 | Station 225+75 Rt | OH |  | Coordinated | 2015-07-08
118d | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 | Station 225+75 to Station 228+00 | OH |  | Coordinated | 2015-07-08
119a | -- | 119 | 29174 | 97586 | 49102700400616 | 3 | Northumberland | VILLAGE OF POTTSGROVE | SR 1027 | OVER ROSS RUN | 49/203 - EAST CHILLISQUA | 40.9955 | -76.7899 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5394 for utility maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. | UG |  |  | 2017-07-24
119b | -- | 119 | 29174 | 97586 | 49102700400616 | 3 | Northumberland | VILLAGE OF POTTSGROVE | SR 1027 | OVER ROSS RUN | 49/203 - EAST CHILLISQUA | 40.9955 | -76.7899 | sanitary | Milton Regional Sewer Auth | George Myers, 570-742-3424, gmyers@miltonwwtp.org | Marked per one call. | UG |  |  | 2017-07-24
120a | -- | 120 | 29178 | 6669 | 49200100200000 | 3 | Northumberland | 3 MI N OF ELYSBURG BORO | SR 2001 | LITTLE ROARING CREEK | 49/214 - RUSH | 40.8906 | -76.5581 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | Per PPL field map, located in the surveyor data for design folder in sharepoint, there is OH power in vicinity of bridge. Per the attachers list verizon is on the poles. | OH |  |  | 2016-10-27
120b | -- | 120 | 29178 | 6669 | 49200100200000 | 3 | Northumberland | 3 MI N OF ELYSBURG BORO | SR 2001 | LITTLE ROARING CREEK | 49/214 - RUSH | 40.8906 | -76.5581 | Comm | Verizon Pennsylvania LLC | Robert (Rob) Jaworski, 570-387-3172, robert.m.jaworski@verizon.com, 11 Ridge Road, Bloomsburg PA 17815 | Responded Clear to one call. Listed as an attacher to PPL poles | OH |  |  | 2016-10-27
120c | -- | 120 | 29178 | 6669 | 49200100200000 | 3 | Northumberland | 3 MI N OF ELYSBURG BORO | SR 2001 | LITTLE ROARING CREEK | 49/214 - RUSH | 40.8906 | -76.5581 |  | Snydertown Borough | 570-672-2190, 36 S Main Street, Snydertown, PA 17877 | Did Not Respond per one call. Have left 3 vm to confirm facilities with no response as of 10/27/15. Confirmed on 10/28 no facilities in the area. |  |  |  | 2016-10-27
121 | -- | 121 | 29303 | 79230 | 49402000301775 | 3 | Northumberland | 2.5 MI NW OF FISHERS FERRY | SR 4020 | HOLLOWING RUN | 49/208 - LOWER AUGUSTA | 40.7919 | -76.817 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5394 for utility maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list. | UG |  |  | 2017-08-01
122a | -- | 122 | 29306 | 6603 | 49402200101591 | 3 | Northumberland | .25 MI E OF FISHERS FERRY | SR 4022 | OVER BOILE RUN | 49/208 - LOWER AUGUSTA | 40.762 | -76.8353 |  | all facilities responded clear per one call | [5 empty] | 2016-06-14
122b | -- | 122 | 29306 | 6603 | 49402200101591 | 3 | Northumberland | .25 MI E OF FISHERS FERRY | SR 4022 | OVER BOILE RUN | 49/208 - LOWER AUGUSTA | 40.762 | -76.8353 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | Per initial site visit OH E/T 5-10 ft lt (looking north). Tag # 25312N21804 and 25333N21826. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see there are no attachers listed on the pole attachers list but per site visit there is phone attached. Need to verify. | OH |  |  | 2016-06-14
122c | -- | 122 | 29306 | 6603 | 49402200101591 | 3 | Northumberland | .25 MI E OF FISHERS FERRY | SR 4022 | OVER BOILE RUN | 49/208 - LOWER AUGUSTA | 40.762 | -76.8353 | Comm | Verizon Pennsylvania LLC | Robert (Rob) Jaworski, 570-387-3172, robert.m.jaworski@verizon.com, 11 Ridge Road, Bloomsburg PA 17815 | Per initial site visit OH E/T 5-10 ft lt (looking north). Tag # 25312N21804 and 25333N21826 | OH |  |  | 2016-06-14
123a | -- | 123 | 29311 | 88047 | 49402600100165 | 3 | Northumberland | 2 MI S OF AUGUSTAVILLE | SR 4026 | OVER LITTLE SHAMOKIN CR. | 49/213 - ROCKEFELLER | 40.7907 | -76.7248 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5308 for utility maps. Per PPL field map, located in the surveyor data for design folder in sharepoint, there is UG and OH power in vicinity of bridge. Also see pole attachers list | UG |  |  | 2016-07-27
123b | -- | 123 | 29311 | 88047 | 49402600100165 | 3 | Northumberland | 2 MI S OF AUGUSTAVILLE | SR 4026 | OVER LITTLE SHAMOKIN CR. | 49/213 - ROCKEFELLER | 40.7907 | -76.7248 | Comm | Service Electric Cablevision, Inc. | Don Phillips, don.phillips@secv.com, 570-286-9662, 3662 Point Township Drive, Northumberland, PA 17857 | DID NOT RESPOND per one call. Attached to power poles. | OH |  |  | 2016-07-27
123c | -- | 123 | 29311 | 88047 | 49402600100165 | 3 | Northumberland | 2 MI S OF AUGUSTAVILLE | SR 4026 | OVER LITTLE SHAMOKIN CR. | 49/213 - ROCKEFELLER | 40.7907 | -76.7248 | Comm | Verizon Pennsylvania LLC | Robert (Rob) Jaworski, 570-387-3172, robert.m.jaworski@verizon.com, 11 Ridge Road, Bloomsburg PA 17815 | Per initial site visit OH phone attached to power poles | OH |  |  | 2016-07-27
124a | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | wtr | Aqua Pennsylvania | Josh Shoff, 570-443-7099 x55502, jpshoff@aquaamerica.com | Marked per one call. Per initial site visit wm on west side of bridge. Valve north of bridge on west side. | UG |  |  | 2017-03-20
124b | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | sanitary | Eastern Snyder Cnty Reg Auth | Scott Bailey, 570-374-1173, escra@verizon.net | Marked per one call. We have a gravity sanitary sewer line that runs south on the Old Trail, on the north side of the bridge it transitions to the east side of the bridge and back onto the road on the south side of the bridge, this is the exposed DIP line that you see running parallel to the bridge on the east side. Please see the utility prints located in the one call folder for the bridge in sharepoint. The plans are vintage 1980 and there are a couple of corrections. First, Lincoln used to be Elm Street back then so our prints are labeled Elm and our line in the streets is now 15” HDPE pipe instead of 15” ACP. The line around the bridge is still 16” DIP. Per initial site visit 10" and 16" sewer on east side of bridge. | UG | 10 and 16" |  | 2017-03-20
124c | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | sanitary | Hummels Wharf Municipal Auth | Sandi Gill, 570-743-1284, hummelswharfmunauth@hotmail.com, 39 Municipal Drive Sellinsgrove, PA 17870 | Marked per one call. | UG |  |  | 2017-03-20
124d | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com; Scott Stahl, 570-416-5139, 4001 Sawmill Road, Bloomsburg, PA 17815 | left voice message - UG facilities exist in project area. Please call 570-368-5394 for utility maps. Per initial site visit there is OH E/T/CATV on left (looking north) that crosses at bridge heading north to right side. Also OH E/T/CATV 6' lt (looking north) that runs north/south. Also UG power north of bridge on west side headed north. | OH |  |  | 2017-03-20
124e | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | gas | UGI Penn Natural Gas, Inc. | Sharon Reese, 570-829-8754, sreese1@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Marked per one call. Per initial site visit, 3" main runs north/south at EOP on left (looking north) | UG | 3" |  | 2017-03-20
124f | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | Comm | Service Electric Cablevision, Inc. | Don Phillips, don.phillips@secv.com, 570-286-9662, 3662 Point Township Drive, Northumberland, PA 17857 | Design Conflict. Please send plans to: Don Phillips Service Electric Cablevision Inc 3662 Point Township Dr Northumberland PA 17857. (per one call) Per initial site visit there is OH E/T/CATV on left (looking north) that crosses at bridge heading north to right side. Also OH E/T/CATV 6' lt (looking north) that runs north/south. Cable that crosses raod and southern portion of bridge from a pole 76' south of bridge 12' rt (looking north) to power pole on 6' lt behind guard rail (looking north) | OH |  |  | 2017-03-20
124g | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | Comm | Verizon North LLC | Robert (Rob) Jaworski, 570-387-3172, robert.m.jaworski@verizon.com, 11 Ridge Road, Bloomsburg PA 17815 | Per initial site visit there is OH E/T/CATV on left (looking north) that crosses at bridge heading north to right side. Also OH E/T/CATV 6' lt (looking north) that runs north/south. | OH |  |  | 2017-03-20
125a | -- | 125 | 31948 | 89977 | 56008701100148 | 3 | Sullivan | VILLAGE OF HILLSGROVE | SR 0087 | OVER MILL CREEK | 56/207 - HILLSGROVE | 41.4441 | -76.7066 | Comm | Herr Cable CO | RALPH HERR, 570-435-2656 or 570-435-2780, RR 4, Montoursville, PA 17754 | DID NOT RESPOND per one call. OH comm 11'-18' rt (looking east) | OH |  |  | 2016-12-12
125b | -- | 125 | 31948 | 89977 | 56008701100148 | 3 | Sullivan | VILLAGE OF HILLSGROVE | SR 0087 | OVER MILL CREEK | 56/207 - HILLSGROVE | 41.4441 | -76.7066 | Elect | Sullivan County Rural Electric Coop Inc | Walter Tubach, wtubach@epix.net, 570-924-3381 | Design Conflict. Please send plans to: Walter Tubach Sullivan County Rural Electric Coop Inc 5675 Route 87 PO Box 65 Forksville PA 18616. Per initial site visit OH power crosses bridge diagonally from southeast to northwest. | OH |  |  | 2016-12-12
126a | Y | 126 | 31966 | 7021 | 56008705202440 | 3 | Sullivan | 0.25 MI W OF DUSHORE | SR 87 | OVER LITTLE LOYALSOCK CR | 56/201 - CHERRY | 41.5162 | -76.4103 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | Station 4+30 to Station 16+30 | OH |  | Coordinated | 2015-09-10
126b | Y | 126 | 31966 | 7021 | 56008705202440 | 3 | Sullivan | 0.25 MI W OF DUSHORE | SR 87 | OVER LITTLE LOYALSOCK CR | 56/201 - CHERRY | 41.5162 | -76.4103 | Comm | Frontier Communications | John Smithkors (570) 265-7775 | Station 4+30 to Station 16+30 | OH |  | Coordinated | 2015-09-10
126c | Y | 126 | 31966 | 7021 | 56008705202440 | 3 | Sullivan | 0.25 MI W OF DUSHORE | SR 87 | OVER LITTLE LOYALSOCK CR | 56/201 - CHERRY | 41.5162 | -76.4103 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | Station 4+30 to Station 16+30 | OH |  | Coordinated | 2015-09-10
127 | -- | 127 | 31981 | 7009 | 56015401501564 | 3 | Tioga | 4 MI SE OF FORKSVILLE | SR154 | OVER DOUBLE RUN | 56/205 - FORKS | 41.466 | -76.579 |  | all facilities responded clear per one call. No visible OH per initial site visit. | [5 empty] | 2017-03-13
128a | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | gas | UGI Central Penn Gas | Bradley (Brad) Heck, 570-830-1113, bheck@ugi.com, 5877 SR 349 Westfield, PA 16950; Kevin Fenstermacher, kfenstermacher@ugi.com | Marked per one call. | UG |  |  | 2016-05-23
128b | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 |  | Westfield Borough | Tony Darslow, 814-367-2632 | DID NOT RESPOND per one call. Followed up with phone call on 8/14 no facilities in area. |  |  |  | 2016-05-23
128c | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | Elect | Pennsylvania Electric Company | Daniel Strein, 570-268-4537, dstrein@firstenergycorp.com; John Forbes, 814-676-7551, jforbes@firstenergycorp.com (manager), 873 S Main Steet, Mansfield, PA 16933 | Per initial site visit OH power to far left (looking east). Separte poles from cable and phone | OH |  |  | 2016-05-23
128d | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | Comm | Westfield Community Antenna Assoc. Inc. (Westview TV) | Shawn King, wcaa1@verizon.net, 814-367-5190, 121 Strang St, Westfield, PA 16950 | Per initial site visit OH cable on north side of bridge. | OH |  |  | 2016-05-23
128e | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | Comm | Verizon Pennsylvania LLC | Jason Wagner, 570-327-7891, jason.e.wagner@verizon.com, 404 W 4th Street, Williamsport, PA 17701 | Per initial site visit OH phone on south side of bridge | OH |  |  | 2016-05-23
128f | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | Comm | Blue Ridge Communications | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675, PO Box 141, Tunkhannock Pa 18657 | Per Westfield they have fiber on their poles. Confirmed. | OH |  |  | 2016-05-23
129a | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | Comm | Westview TV | Sean, (814) 367-5190 | Station 253+72 to Station 258+60 | OH |  | Prior | 2015-07-15
129b | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | Station 253+72 to Station 261+00 | OH |  | Prior | 2015-07-15
129c | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | Gas | UGI Central Penn Gas, Inc. | Roy Carr (570) 829-8967 | Station 260+75 | UG |  | Not Affected | 2015-07-15
129d | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | Comm | Verizon North LLC | Denny Vicary, 814-857-7613, dennis.m.vicary@one.verizon.com | Station 253+72 to Station 258+60 | OH |  | Prior | 2015-07-15
130a | -- | 130 | 32931 | 87929 | 58054902602539 | 3 | Tioga | 0.5 MI S OF JOBS CORNERS | SR 549 | OVER SEELY CREEK | 58/215 - JACKSON | 41.9301 | -76.9323 |  | all facilities responded clear per one call | [5 empty] | 2016-08-08
130b | -- | 130 | 32931 | 87929 | 58054902602539 | 3 | Tioga | 0.5 MI S OF JOBS CORNERS | SR 549 | OVER SEELY CREEK | 58/215 - JACKSON | 41.9301 | -76.9323 | Elect | Pennsylvania Electric Company | Daniel Strein, 570-268-4537, dstrein@firstenergycorp.com; John Forbes, 814-676-7551, jforbes@firstenergycorp.com (manager), 873 S Main Steet, Mansfield, PA 16933 | Per initial site visit OH E/T pole approx. 70 ft south of bridge 12 ft left (looking north) behind guardrail. Lines cross road perpendicular to the east. Also lines that run northwest from pole. Guy wire from pole runs north towards bridge. | OH |  |  | 2016-08-08
130c | -- | 130 | 32931 | 87929 | 58054902602539 | 3 | Tioga | 0.5 MI S OF JOBS CORNERS | SR 549 | OVER SEELY CREEK | 58/215 - JACKSON | 41.9301 | -76.9323 | Comm | North Penn Telephone Company | Cody Morgan, 570-549-7525, CMorgan@etcnpt.com | Per initial site visit OH E/T pole approx. 70 ft south of bridge 12 ft left (looking north) behind guardrail. Lines cross road perpendicular to the east. Also lines that run northwest from pole. Guy wire from pole runs north towards bridge. | OH |  |  | 2016-08-08
130d | -- | 130 | 32931 | 87929 | 58054902602539 | 3 | Tioga | 0.5 MI S OF JOBS CORNERS | SR 549 | OVER SEELY CREEK | 58/215 - JACKSON | 41.9301 | -76.9323 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Responded clear to one call however there was a gas main picked up by survey crew. | UG |  |  | 2016-08-08
131a | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | Comm | Gaines Watrous TV Company | Melvin Lowrey, 814-435-6578 | Station 1040+95 to Station 1047+50 | OH |  | Prior | 2016-04-21
131b | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | Comm | Verizon Pennsylvania LLC | Denny Vicary, 814-857-7613, dennis.m.vicary@one.verizon.com | Station 1041+80 to Station 1046+10 | OH |  | Not Affected | 2016-04-21
131c | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | Elect | Tri-County Rural Electric Cooperative Inc. | Steve Salada PH; 570-662-8034 steves@ctenterprises.com | Station 1042+70 Rt. to Station 1046+00 Rt | OH |  | Prior | 2016-04-21
131d | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | Elect | Tri-County Rural Electric Cooperative Inc. | Steve Salada PH; 570-662-8034 steves@ctenterprises.com | Station 1042+70 Rt. to Station 1046+00 Rt | OH |  | Coordinated | 2016-04-21
132a | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | ??? | Delmar Township | Shirley W. Borden (570) 724-5482 | Station 126+35 to Station 133+55 | UG |  | Not Affected | 2016-07-12
132b | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | Gas | UGI Central Penn Gas, Inc. | Roy Carr (570) 829-8967 | Station 126+35 to Station 133+55 | UG |  | Not Affected | 2016-07-12
132c | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | Comm | Frontier Communications | Jan Kapson (570) 673-7107 | Station 130+00 to 133+00 | OH |  | Prior | 2016-07-12
132d | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | Station 130+00 to 133+00 | OH |  | Prior | 2016-07-12
132e | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | Elect | Wellsboro Electric Company | Dave Kennedy (570) 724-3516 | Station 131+58 to Station 132+45 | OH |  | Prior | 2016-07-12
133a | Y | 133 | 33180 | 7347 | 58401702800000 | 3 | Tioga | 2 MI NW OF OSCEOLA | SR 4017 | HOLDEN CREEK | 58/221 - OSCEOLA | 41.9921 | -77.3798 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | Station 673+80 to Station 678+50 |  |  | Prior | 2015-08-25
133b | Y | 133 | 33180 | 7347 | 58401702800000 | 3 | Tioga | 2 MI NW OF OSCEOLA | SR 4017 | HOLDEN CREEK | 58/221 - OSCEOLA | 41.9921 | -77.3798 | Comm | Verizon | Denny Vicary, 814-857-7613, dennis.m.vicary@one.verizon.com | SR4017 Segment 270 Offset 594 to Segment 280 Offset 338 |  |  | Prior | 2015-08-25
134a | -- | 134 | 33209 | 83470 | 58403501300426 | 3 | Tioga | 3.5 MI NE OF WELLSBORO | SR 4035 | OVER CATLIN HOLLOW CREEK | 58/203 - CHARLESTON | 41.7979 | -77.2643 | GAS | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com, One UGI Center, Building G2, Wilkes-Barre, PA 18711 | Design Conflict. Please send plans to: Andrew Black UGI Central Penn Gas 225 Morgantown Rd Reading PA 19611 (per one call) | UG |  |  | 2016-08-03
134b | -- | 134 | 33209 | 83470 | 58403501300426 | 3 | Tioga | 3.5 MI NE OF WELLSBORO | SR 4035 | OVER CATLIN HOLLOW CREEK | 58/203 - CHARLESTON | 41.7979 | -77.2643 | Elect | Pennsylvania Electric Company | John Forbes, 814-676-7551, jforbes@firstenergycorp.com | OH Power that crosses road approx. 150 ft south of bridge. Confirmed not their facilities |  |  |  | 2016-08-03
134c | -- | 134 | 33209 | 83470 | 58403501300426 | 3 | Tioga | 3.5 MI NE OF WELLSBORO | SR 4035 | OVER CATLIN HOLLOW CREEK | 58/203 - CHARLESTON | 41.7979 | -77.2643 | Elect | Wellsboro Electric Company | Dave Kennedy, 570-724-3516, davek@ctenterprises.org, 33 Austin St, Wellsboro, PA 16901 | OH Power that crosses road approx. 150 ft south of bridge. | OH |  |  | 2016-08-03
134d | -- | 134 | 33209 | 83470 | 58403501300426 | 3 | Tioga | 3.5 MI NE OF WELLSBORO | SR 4035 | OVER CATLIN HOLLOW CREEK | 58/203 - CHARLESTON | 41.7979 | -77.2643 | Comm | Frontier Communications | Jan Kapson, Jan.Kapson@FTR.com, 570-673-7107, 19 North Center Street P.O. Box 216, Canton Pa. 17724 | OH phone 15' rt (looking north) | OH |  |  | 2016-08-03
135a | -- | 135 | 33469 | 7542 | 59100101101961 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/201 - BUFFALO | 41.0124 | -76.9825 | Comm | Windstream | Anthony "TJ" Seekins, 501-748-4447, anthony.seekins.jr@windstream.com | Aerial fiber and copper lines on SR 1001 (Spruce Run Rd). Please utility map located in the one call folder for the bridge on sharepoint. Per initial site visit OH lines 3' rt (looking east) | OH |  |  | 2016-07-13
135b | -- | 135 | 33469 | 7542 | 59100101101961 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/201 - BUFFALO | 41.0124 | -76.9825 | Elect | Citizens Electric Company of Lewisburg | JOHN KELCHNER, 570-522-6143, KELCHNERJ@CITIZENSELECTRIC.COM | Per initial site visit there is OH power that crosses the bridge from the southwest to a pole located north of bridge on east side behind guardrail. | OH |  |  | 2016-07-13
135c | -- | 135 | 33469 | 7542 | 59100101101961 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/201 - BUFFALO | 41.0124 | -76.9825 | Comm | Service Electric Cablevision, Inc. | Don Phillips, don.phillips@secv.com, 570-286-9662, 3662 Point Township Drive, Northumberland, PA 17857 | Per Citizens Electric they are on the poles. On power poles. | OH |  |  | 2016-07-13
136a | -- | 136 | 33470 | 7542 | 59100101102058 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/205 - KELLY | 41.0124 | -76.9822 | Comm | Windstream | Anthony "TJ" Seekins, 501-748-4447, anthony.seekins.jr@windstream.com | Aerial fiber and copper lines on SR 1001 (Spruce Run Rd), but do not appear to be in conflict with the project per windstream. Please see utility map located in the one call folder for the bridge on sharepoint. Per initial site visit OH comm 4ft right (looking east. Pole tag Buffalo Valley Tel Co 21184 N30898. Crosses road diagonally east of bridge to left. | OH |  |  | 2016-07-13
136b | -- | 136 | 33470 | 7542 | 59100101102058 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/205 - KELLY | 41.0124 | -76.9822 | Elect | Citizens Electric Company of Lewisburg | JOHN KELCHNER, 570- 522-6143, KELCHNERJ@CITIZENSELECTRIC.COM | Per initial site visit OH power 7' left (looking east). Pole tag, Citizens Elec V2429 | OH |  |  | 2016-07-13
136c | -- | 136 | 33470 | 7542 | 59100101102058 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/205 - KELLY | 41.0124 | -76.9822 | Comm | Service Electric Cablevision, Inc. | Don Phillips, don.phillips@secv.com, 570-286-9662, 3662 Point Township Drive, Northumberland, PA 17857 | Per Citizens Electric they are on the poles. On power poles. | OH |  |  | 2016-07-13
137a | Y | 137 | 33478 | 83478 | 59100300200000 | 3 | Union | 2 MI NE BUFFALO CROSS RDS | SR 1003 | OVER BUFFALO CREEK | 59/201 - BUFFALO | 40.9734 | -76.9525 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 12+05 to Station 19+70 | OH |  | Not Affected | 2016-06-22
137b | Y | 137 | 33478 | 83478 | 59100300200000 | 3 | Union | 2 MI NE BUFFALO CROSS RDS | SR 1003 | OVER BUFFALO CREEK | 59/201 - BUFFALO | 40.9734 | -76.9525 | Comm | Windstream | Jeremy Kennedy (570) 522-5707 | Station 12+55 to Station 15+31 | OH |  | Prior | 2016-06-22
137c | Y | 137 | 33478 | 83478 | 59100300200000 | 3 | Union | 2 MI NE BUFFALO CROSS RDS | SR 1003 | OVER BUFFALO CREEK | 59/201 - BUFFALO | 40.9734 | -76.9525 | Elect | Citizens Electric | John Kelchner (570) 522-6143 | Station 12+55 to Station 15+31 | OH | Unk | Prior | 2016-06-22
138a | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | Comm | Atlantic Broadband | Rich Fultz (814) 248-5338 | Station 469+60 to Station 474+50 | OH |  | Coordinated | 2016-06-01
138b | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | Comm | Atlantic Broadband | Rich Fultz (814) 248-5338 | Station 469+60 to Station 470+85 | OH |  | Coordinated | 2016-06-01
138c | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | ??? | Hartley Township Municipal Authority | Norm Strickler (570) 922-1310 | Station 471+00 RT. to Station 472+50 RT | UG |  | Not Affected | 2016-06-01
138d | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 469+60 to Station 474+50 | OH |  | Coordinated | 2016-06-01
138e | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Station 469+60 to Station 470+85 | OH |  | Coordinated | 2016-06-01
138f | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | Comm | Windstream | Jeremy Kennedy (570) 522-5707 | Station 469+60 to Station 474+50 | OH |  | Coordinated | 2016-06-01
138g | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | Comm | Windstream | Jeremy Kennedy (570) 522-5707 | Station 469+60 to Station 470+85 | OH |  | Coordinated | 2016-06-01
139a | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | wtr | Pennsylvania American Water CO | Scott Reiner, Cell #570-840-8395, scott.reiner@amwater.com, JOE GRABOSKI (570) 586-6934 | Marked | UG |  |  | 2016-07-07
139b | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | wtr | PENNSYLVANIA AMERICAN WATER CO Wilkes-Barre | Scott Reiner, Cell #570-840-8395, scott.reiner@amwater.com, PETE SARMONIS (570) 830-6540 | Marked | UG |  |  | 2016-07-07
139c | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | sanitary & wtr | South Abington TWP | David G. O’Neill, #570-587-8717, davido01@comcast.net, MERLE HATFIELD (570) 586-2111 | Marked. 12" CI sanitary line attached to bridge. MH #62 on east side of bridge and MH #61 on west side. The pipe is sloped from MH 62 to MH 61. 12" WM runs under I-81 at the Edella Bridge in a 30" steel casing. 12" valve on each side of bridge before directional. Please see utility map located in the one call folder for the bridge on sharepoint. | UG | 12" san & 12" wtr |  | 2016-07-07
139d | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities exist in the area. Please call 484-634-3756 for field maps. Received plans from PPL, they are located in the one call folder for the bridge on sharepoint. | UG |  |  | 2016-07-07
139e | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com | Responded clear on one-call. After sent in field maps of lines in area. 4" line on Edella running towards I-81 from the Foxrun Circle intersection. Please see utility map located in the one call folder for the bridge on sharepoint. | UG | 4" |  | 2016-07-07
140a | -- | 140 | 23795 | 67364 | 40011501200000 | 4 | Luzerne | BEAR CR TW 1.2M S SR 2038 | SR 0115 TR 115 | SHADES CREEK | 40/201 - BEAR CREEK | 41.1809 | -75.6994 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities exist in the area. Please call 484-634-3756 for field maps. | UG |  |  | 2016-06-09
140b | -- | 140 | 23795 | 67364 | 40011501200000 | 4 | Luzerne | BEAR CR TW 1.2M S SR 2038 | SR 0115 TR 115 | SHADES CREEK | 40/201 - BEAR CREEK | 41.1809 | -75.6994 | Elect | Wind Park Bear Creek | Brandon Nehring, brandon.nehring@infigen-us.com; 570-821-8572; 570-820-7750 | DID NOT RESPOND |  |  |  | 2016-06-09
141 a | -- | 141 | 24493 | 97506 | 40800500201030 | 4 | Luzerne | BUTLER TWP OVER I-80 WB | SR 8005 RAMP E | SR 0080 I-80 WB | 40/204 - BUTLER | 41.0483 | -76.0083 | Gas | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | DID NOT RESPOND | UG |  | NA | 2016-06-03
141 b | -- | 141 | 24493 | 97506 | 40800500201030 | 4 | Luzerne | BUTLER TWP OVER I-80 WB | SR 8005 RAMP E | SR 0080 I-80 WB | 40/204 - BUTLER | 41.0483 | -76.0083 | Gas | Service Electric Cablevision | Robert F. Trently ¦ Field Supervisor 380 Maplewood Dr ¦ Hazle Township PA, 18202 T (570) 454-3841 ext. 812 ¦ F (570) 454-3652 robert.trently@secv.com ¦ www.secv.com | not utilities at the SR 8005 Ramp E, section 217 at the I80 & I-81 interchange in Luzerne County. | OH |  | NA | 2016-06-03
142a | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | Station 71+94 Left 37’ to Station 73+96 Right 60’ | OH |  | Coordinated | 2015-06-29
142b | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | Station Left 38' to Station 72+40 Right 24' | OH |  | Coordinated | 2015-06-29
142c | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | Station 73+45 Right 32' | OH |  | Coordinated | 2015-06-29
142d | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | Station 71+94 Left 37’ to Station 73+96 Right 60’ | OH |  | Coordinated | 2015-06-29
142e | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station 71+94 Left 37', Station 72+12 Left 38', Station 72+98 Left 68' | OH |  | Coordinated | 2015-06-29
142f | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station 73+87 Left 20' | OH |  | Coordinated | 2015-06-29
142g | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station 75+38 Right 30' | OH |  | Coordinated | 2015-06-29
142h | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station 71+94 Left 37' to Station 75+38 Right 60' | OH |  | Coordinated | 2015-06-29
142i | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station 73+70 Left 17' | OH |  | Coordinated | 2015-06-29
142j | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station 71+94 Left 37' to Station 75+38 Right 30' | OH |  | Coordinated | 2015-06-29
142k | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 72+00 to Station 74+00 Right/Left | OH |  | Coordinated | 2015-06-29
142l | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 72+00 to Station 74+00 Right | OH |  | Coordinated | 2015-06-29
142m | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 73+52 Right | OH |  | Coordinated | 2015-06-29
142n | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 72+00 to Station 74+00 Right/Left | OH |  | Coordinated | 2015-06-29
143a | -- | 143 | 29982 | 67514 | 51200600100953 | 4 | Pike | DINGMAN TWP .2 M E TR 739 | SR 2006 | DWARFKILL CREEK | 51/203 - DINGMAN | 41.2992 | -74.9598 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Lynn Morris 610-251-2914 Lmorris@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-04-19
143b | -- | 143 | 29982 | 67514 | 51200600100953 | 4 | Pike | DINGMAN TWP .2 M E TR 739 | SR 2006 | DWARFKILL CREEK | 51/203 - DINGMAN | 41.2992 | -74.9598 | Gas | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | DID NOT RESPOND |  |  |  | 2016-04-19
143c | -- | 143 | 29982 | 67514 | 51200600100953 | 4 | Pike | DINGMAN TWP .2 M E TR 739 | SR 2006 | DWARFKILL CREEK | 51/203 - DINGMAN | 41.2992 | -74.9598 | Comm | PENCOR SERVICES/BLUE RIDGE COMMUNICATION (BK1) | Muniz, Alice <amuniz@brctv.com> Pencor Corporate Office (610) 826-2552 | Blue Ridge Communications does not have any facilities here. |  |  |  | 2016-04-19
143d | -- | 143 | 29982 | 67514 | 51200600100953 | 4 | Pike | DINGMAN TWP .2 M E TR 739 | SR 2006 | DWARFKILL CREEK | 51/203 - DINGMAN | 41.2992 | -74.9598 | Comm | Verizon North (TI) | Daniel J. Blodnikar Dan. Blodnikar@verizon.com Phone 570-253-0048, Fax 570 253-2675 | Will be affected | OH/UG |  |  | 2016-04-19
143e | -- | 143 | 29982 | 67514 | 51200600100953 | 4 | Pike | DINGMAN TWP .2 M E TR 739 | SR 2006 | DWARFKILL CREEK | 51/203 - DINGMAN | 41.2992 | -74.9598 | Elec/Gas | Pike County Light & Power Company | 1-877-434-4100 | Clear no facility | UG |  |  | 2016-04-19
144a | -- | 144 | 32153 | 96737 | 57001104601461 | 4 | Susquehanna | N MILFRD TP .2M S SR 1018 | SR 0011 TR 11 | SALT LICK CREEK | 57/222 - NEW MILFORD | 41.8929 | -75.73 | Comm | Sprint Nextel | (610) 826-2552 | (610) 826-2552 |  |  |  | 2016-05-23
144b | -- | 144 | 32153 | 96737 | 57001104601461 | 4 | Susquehanna | N MILFRD TP .2M S SR 1018 | SR 0011 TR 11 | SALT LICK CREEK | 57/222 - NEW MILFORD | 41.8929 | -75.73 | wtr | New Milford Municipal Auth |  |  | UG |  |  | 2016-05-23
145a | -- | 145 | 32244 | 89023 | 57010601220638 | 4 | Susquehanna | LENOX TWP .1 M E TR 92 | SR 0106 TR 106 | TUNKHANNOCK CREEK | 57/219 - LENOX | 41.7101 | -75.6714 | Elect | Pennsylvania Electric Company | Steve Beers sbeers@firstenergycorp.com O - 570-265-1237 C - 607-738-3120 F – 570-265-1258 | Please be advised that Penelec has no overhead or underground facilities within the limits of this project. |  |  |  | 2016-05-23
145b | -- | 145 | 32244 | 89023 | 57010601220638 | 4 | Susquehanna | LENOX TWP .1 M E TR 92 | SR 0106 TR 106 | TUNKHANNOCK CREEK | 57/219 - LENOX | 41.7101 | -75.6714 | Comm | Northeastern Pennislivania Telephone co(NT1) | Scott Fuller, 570-785-2280 sfuller@nep.net | 2 poles on the north side of the bridge. P.#A1/116 is 24’ off centerline of SR 106 and P.#A1/117 is 27’ off centerline. There is one strand supporting 4 cables, (2) copper cables and (2) fiber optic cables | OH |  |  | 2016-05-23
145c | -- | 145 | 32244 | 89023 | 57010601220638 | 4 | Susquehanna | LENOX TWP .1 M E TR 92 | SR 0106 TR 106 | TUNKHANNOCK CREEK | 57/219 - LENOX | 41.7101 | -75.6714 | Comm | Adams Cable Tv (AF) | Dylan Denike (570)282-6121 Ext.203 Email: Dylandenike@echoes.net | After looking at the job location, Adams CATV does not have any facilities involved in the project area ( Dylan response on 08/18/15) |  |  |  | 2016-05-23
145d | -- | 145 | 32244 | 89023 | 57010601220638 | 4 | Susquehanna | LENOX TWP .1 M E TR 92 | SR 0106 TR 106 | TUNKHANNOCK CREEK | 57/219 - LENOX | 41.7101 | -75.6714 | Gas | Tennessee Gas Pipeline (TK1) | Dewey,Neil F; Neil_Dewey@kindermorgan.com; 570-222-3153 ext.2026 or 716-472-3033 | 2 Tennessee Gas Pipeline’s 24” and 30” pipelines locatetd approximately in 985 ft from Bridge, Facilites will not affect the replacement ( response on 08/17/15) | UG |  |  | 2016-05-23
145e | -- | 145 | 32244 | 89023 | 57010601220638 | 4 | Susquehanna | LENOX TWP .1 M E TR 92 | SR 0106 TR 106 | TUNKHANNOCK CREEK | 57/219 - LENOX | 41.7101 | -75.6714 | Gas | Williams Field Services (WFS) | Leigh Clea ( Operations Manager)570-996-4000 or 360-965-9153 | Clear, No facilities |  |  |  | 2016-05-23
146a | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | Elect | Claverack Rural Electric Cooperative, Inc. | Charlie Goodwin (570) 265-2167 Ext.327, charlieg@ctenterprises.org | Station Entire Project | OH |  | Not Affected | 2016-05-13
146b | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | Comm | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | Station 966+10 to Station 971+40 Left | OH |  | Coordinated | 2016-05-13
146c | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | Comm | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | Station 966+10 to Station 971+40 Left | OH |  | Coordinated | 2016-05-13
146d | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | Pole | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | Station 966+60 Left | OH |  | Coordinated | 2016-05-13
146e | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | Pole | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | Station 968+00 Left | OH |  | Coordinated | 2016-05-13
147a | -- | 147 | 32308 | 79572 | 57026703202704 | 4 | Susquehanna | FRST LK TP 4.5M S SR 4014 | SR 0267 TR 267 | MIDDLE BR WYALUSING CR | 57/209 - FOREST LAKE | 41.8429 | -76.0189 | Elect | Pennsylvania Electric Company | Steve Beers, sbeers@firstenergycorp.com, 607-738-3120, Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 607-738-3120 | Penelec has no overhead or underground facilities within the limits of this project |  |  |  | 2016-04-11
147b | -- | 147 | 32308 | 79572 | 57026703202704 | 4 | Susquehanna | FRST LK TP 4.5M S SR 4014 | SR 0267 TR 267 | MIDDLE BR WYALUSING CR | 57/209 - FOREST LAKE | 41.8429 | -76.0189 | Elect | CLAVERACK RURAL ELECTRIC CO-OP INC. | CHARLES GOODWIN (570) 265-2167 X 327 charlieg@ctenterprises.org | Have Electrical power pole at sta 994+62.20 LT and Sta 996+50, 20ft LT | OH |  |  | 2016-04-11
147c | -- | 147 | 32308 | 79572 | 57026703202704 | 4 | Susquehanna | FRST LK TP 4.5M S SR 4014 | SR 0267 TR 267 | MIDDLE BR WYALUSING CR | 57/209 - FOREST LAKE | 41.8429 | -76.0189 | comm | Frontier | Steve Lathrop, 'Steven.Lathrop@FTR.com', 570-278-0036 | Utility poles labeled CTCO T-147, T-148, T-149, T-150, T-151 and aerial cables attached to them parallel to SR 267. At T-148 aerial wire running north crossing School House Rd. At T-149 aerial wire running north and south to service customers. | OH |  |  | 2016-04-11
148 | -- | 148 | 32327 | 9656 | 57037400502476 | 4 | Susquehanna | LENOX TWP .5 M E SR 2016 | SR 0374 TR 374 | EAST BR TUNKHANNOCK CRK | 57/219 - LENOX | 41.6514 | -75.6917 |  | all facilities responded clear per one call | [5 empty] | 2017-05-30
149a | -- | 149 | 32365 | 96729 | 57070602700000 | 4 | Susquehanna | BRIDGWTR TP 2 M W TR 167 | SR 0706 TR 706 | PETTIS CREEK | 57/204 - BRIDGEWATER | 41.8248 | -75.9123 | Water & SS | Bridgewater TWP | Mike Hester, Cell: 570-396-0275, 570-663-2625, mlhester1@yahoo.com | DID NOT RESPOND | UG |  |  | 2016-06-02
149b | -- | 149 | 32365 | 96729 | 57070602700000 | 4 | Susquehanna | BRIDGWTR TP 2 M W TR 167 | SR 0706 TR 706 | PETTIS CREEK | 57/204 - BRIDGEWATER | 41.8248 | -75.9123 | Comm | FRONTIER COMMUNICATIONS SOLUTIONS (RJ) | James Zionkowski Phone-Leesport 610-926-4747 Phone-Harrisburg 717-938-5555 Cell - 717-574-3058 James.zionkowski@ftr.com | DID NOT RESPOND | OH |  |  | 2016-06-02
149c | -- | 149 | 32365 | 96729 | 57070602700000 | 4 | Susquehanna | BRIDGWTR TP 2 M W TR 167 | SR 0706 TR 706 | PETTIS CREEK | 57/204 - BRIDGEWATER | 41.8248 | -75.9123 | Elect | Pennsylvania Electric Company | Steve Beers, sbeers@firstenergycorp.com, 607-738-3120, Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 607-738-3120 | DID NOT RESPOND | OH |  |  | 2016-06-02
150 | -- | 150 | 32378 | 100550 | 57085800500000 | 4 | Susquehanna | RUSH TWP 2 M N TR 706 | SR 0858 TR 858 | GAYLORD CREEK | 57/224 - RUSH | 41.815 | -76.1057 | Comm | Frontier | Jeffrey Bolton (Auburn TWP), 570-631-6710 | Did Not Respond. |  |  |  | 2017-05-30
151a | Y | 151 | 32401 | 85782 | 57100700500000 | 4 | Susquehanna | THMPSN TWP 1.7M N SR 1004 | SR 1007 | SOUTH BR CANAWACTA CREEK | 57/227 - THOMPSON | 41.9134 | -75.5628 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567 | Station Entire Project | OH |  | Not Affected | 2015-07-09
151b | Y | 151 | 32401 | 85782 | 57100700500000 | 4 | Susquehanna | THMPSN TWP 1.7M N SR 1004 | SR 1007 | SOUTH BR CANAWACTA CREEK | 57/227 - THOMPSON | 41.9134 | -75.5628 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219 | Station Entire Project | OH |  | Not Affected | 2015-07-09
152a | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 |  | New Milford Municipal Auth | Sheila Shibley, munauth@nep.net, 570-465-7089; AMY HINE, 570-465-7089 / (570) 465-3394, nmboro@nep.net; AMY HINE, 570-465-7089 | reviewed the plans and the sewer lines are shown properly. Sewer Line in 23 feet from new structures | UG |  |  | 2016-05-20
152b | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 | Elect | Pennsylvania Electric Company | Steve Beers, sbeers@firstenergycorp.com, 607-738-3120, Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 607-738-3120 | Penelec has marked their facilities on Project Plan ( See the response of 08/11/15 | OH |  |  | 2016-05-20
152c | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 | CTV | Adams cable | DYLAN DENIKE (570) 282-6121 EXT. 203 Dylandenick@echoes.net | Attached on Penelec Poles | OH |  |  | 2016-05-20
152d | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 | Comm | NORTHEASTERN PENNSYLVANIA TELEPHONE CO (NT1 | Scott Fuller 570-785-2280 sfuller@nep.net 720 MAIN STREET PO BOX D FOREST CITY, PA 18421-0150 | Conflict in Area, attached to Penelec Poles | OH |  |  | 2016-05-20
152e | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 | Comm | Sprint Nextel | Mike.brown@sprint.com, 304-283-5668 (Eastern PA); Wes.carpenter@sprint.com 717-404-0899 (Western PA), 1-800-521-0579 | Marked. Excavation should not require monitoring as long as excavation stays consistent with information provided on locate request. See Excavation PA one call | UG |  |  | 2016-05-20
153a | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 65+05 Left to SR0106 Station 443+50 Right | OH |  | Coordinated | 2015-08-04
153b | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 64+85 Right | OH |  | Coordinated | 2015-08-04
153c | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 66+23 Right | OH |  | Coordinated | 2015-08-04
153d | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 64+85 Left to SR0106 Station 442+35 Left | OH |  | Coordinated | 2015-08-04
153e | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 66+96 Left | OH |  | Coordinated | 2015-08-04
153f | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 65+05 Left to SR0106 Station 443+50 Right | OH |  | Coordinated | 2015-08-04
153g | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 67+05 Left | OH |  | Coordinated | 2015-08-04
153h | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 64+85 Left to SR0106 Station 443+50 Right | OH |  | Coordinated | 2015-08-04
153i | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2008 Station 64+85 Left | OH |  | Coordinated | 2015-08-04
153j | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Comm | Adams Cable Service | Dylan DeNike (570) 282-6121 Ext.203, dylandenike@echoes.net | SR2008 Station 64+85 Left 17' to SR0106 Station 442+35 Left 27' | OH |  | Coordinated | 2015-08-04
153k | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Comm | Adams Cable Service | Dylan DeNike (570) 282-6121 Ext.203, dylandenike@echoes.net | SR2008 Station 65+05 Left 17' to SR0106 Station 443+50 Right 20' | OH |  | Coordinated | 2015-08-04
153l | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Comm | Adams Cable Service | Dylan DeNike (570) 282-6121 Ext.203, dylandenike@echoes.net | SR2008 Station 65+05 Left 17' to SR0106 Station 443+50 Right 20' | OH |  | Coordinated | 2015-08-04
153m | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | SR0106 Station 443+50 Right 20' | OH |  | Coordinated | 2015-08-04
153n | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | SR2008 Station 64+85 Left 17' to SR0106 Station 442+35 Left 27' | OH |  | Coordinated | 2015-08-04
153o | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | SR2008 Station 65+05 Left 17' to SR0106 Station 443+50 Right 20' | OH |  | Coordinated | 2015-08-04
153p | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | SR2008 Station 65+05 Left 17' to SR0106 Station 443+50 Right 20' | OH |  | Coordinated | 2015-08-04
154 | -- | 154 | 32507 | 9679 | 57202100501583 | 4 | Susquehanna | LENOX TWP OVER SR 0081 | SR 2021 | SR 0081 I-81 | 57/219 - LENOX | 41.6553 | -75.6602 |  | all facilities responded clear per one call | [5 empty] | 2017-05-30
155 | -- | 155 | 32647 | 96736 | 57400201300000 | 4 | Susquehanna | SILVER LK T 1.2M E SR4001 | SR 4002 | RHINEY CREEK | 57/225 - SILVER LAKE | 41.9715 | -75.9134 |  | all facilities responded clear per one call | [5 empty] | 2016-08-22
156a | -- | 156 | 35471 | 68876 | 63019106701296 | 4 | Wayne | OREGON TWP 1.5M N SR 4019 | SR 0191 TR 191 | BIG BROOK CREEK | 63/214 - OREGON | 41.6681 | -75.2546 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | PPL responded with their facility map in project area | OH | 13.2 kV |  | 2016-05-20
156b | -- | 156 | 35471 | 68876 | 63019106701296 | 4 | Wayne | OREGON TWP 1.5M N SR 4019 | SR 0191 TR 191 | BIG BROOK CREEK | 63/214 - OREGON | 41.6681 | -75.2546 | Gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com; Scott Kinter, 570-893-6600 | DID NOT RESPOND via PA one call | UG |  |  | 2016-05-20
156c | -- | 156 | 35471 | 68876 | 63019106701296 | 4 | Wayne | OREGON TWP 1.5M N SR 4019 | SR 0191 TR 191 | BIG BROOK CREEK | 63/214 - OREGON | 41.6681 | -75.2546 | Comm | VERIZON PENNSYLVANIA LLC (HI) | Deborah D Delia P: 412-633-3810., F :412-633-6927 deborah.d.delia@verizon.com | Clear no facility From PA Call |  |  |  | 2016-05-20
156d | -- | 156 | 35471 | 68876 | 63019106701296 | 4 | Wayne | OREGON TWP 1.5M N SR 4019 | SR 0191 TR 191 | BIG BROOK CREEK | 63/214 - OREGON | 41.6681 | -75.2546 | Comm | Verizon North LLC | Daniel J. Blodnikar Dan.Blodnikar@verizon.com Phone 570-253-0048 Fax 570 253-2675 | Conflict. Lines Nearby ( From PA one call) | OH | 1 fiber and 100 coppers |  | 2016-05-20
157a | -- | 157 | 35508 | 9969 | 63029601800000 | 4 | Wayne | CANAAN TWP 1 M S SR 3028 | TR 296 EASTON TPK | BRANCH OF MIDDLE CREEK | 63/203 - CANAAN | 41.5542 | -75.4081 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities exist in the area. Please call 484-634-3756 for field maps. | UG |  |  | 2016-09-12
157b | -- | 157 | 35508 | 9969 | 63029601800000 | 4 | Wayne | CANAAN TWP 1 M S SR 3028 | TR 296 EASTON TPK | BRANCH OF MIDDLE CREEK | 63/203 - CANAAN | 41.5542 | -75.4081 |  | Western Wayne School District | LaCoe, Clay; clacoe@westernwayne.org | DID NOT RESPOND |  |  |  | 2016-09-12
158a | Y | 158 | 35624 | 68917 | 63101801602046 | 4 | Wayne | MANCHSTR TP 3.7M E TR 191 | SR 1018 | BR LITTLE EQUINUNK CREEK | 63/212 - MANCHESTER | 41.8244 | -75.1497 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | Station 376+66 Offset 45' Right to Station 378+93 Offset 117 Left (T643 Station 1+00 Offset 45' Right) | OH |  | Coordinated | 2016-06-01
158b | Y | 158 | 35624 | 68917 | 63101801602046 | 4 | Wayne | MANCHSTR TP 3.7M E TR 191 | SR 1018 | BR LITTLE EQUINUNK CREEK | 63/212 - MANCHESTER | 41.8244 | -75.1497 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | Station 376+66 Offset 45' Right to Station 378+93 Offset 117 Left (T643 Station 1+00 Offset 45' Right) | OH |  | Coordinated | 2016-06-01
158c | Y | 158 | 35624 | 68917 | 63101801602046 | 4 | Wayne | MANCHSTR TP 3.7M E TR 191 | SR 1018 | BR LITTLE EQUINUNK CREEK | 63/212 - MANCHESTER | 41.8244 | -75.1497 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station Entire Project | OH |  | Not Affected | 2016-06-01
159a | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551, amuniz@pencor.com | Station Entire Project | OH |  | Not Affected | 2016-03-03
159b | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2007 Station 675+25 Right 48' | OH |  | Coordinated | 2016-03-03
159c | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2009 Station 69+75 Right 23' | OH |  | Coordinated | 2016-03-03
159d | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2009 Station 70+97 Right 54' | OH |  | Coordinated | 2016-03-03
159e | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2007 Station 67+25 Right to SR2009 Station 70+97 Right 54' | OH |  | Coordinated | 2016-03-03
159f | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | SR2007 Station 67+25 Right to SR2009 Station 70+97 Right 54' | OH |  | Coordinated | 2016-03-03
159g | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | Station Entire Project | OH |  | Not Affected | 2016-03-03
160a | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities exist in the area. Please call 484-634-3756 for field maps. | UG/OH |  |  | 2016-08-01
160b | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 |  | Western Wayne School District | LaCoe, Clay; clacoe@westernwayne.org | DID NOT RESPOND |  |  |  | 2016-08-01
160c | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 | comm | VERIZON PENNSYLVANIA LLC (HI) | . BRENDA HUFFMAN (570) 424-0076 FAX: (570) 424-0081 Brenda.huffman@verizon.com Deborah D Delia P: 412-633-3810, F:412-633-6927 deborah.d.delia@verizon.com | CLEAR - NO FACILITIES from PA one call |  |  |  | 2016-08-01
160d | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 | comm | ADAMS CABLE TV (AF) | DYLAN DENIKE (570) 282-6121 EXT. 203 Dylandenike@echoes.net | CLEAR - NO FACILITIES. From Pa one call |  |  |  | 2016-08-01
160e | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 | Comm | Verizon North LLC | Daniel J. Blodnikar Dan.Blodnikar@verizon.com Phone 570-253-0048 Fax 570 253-2675 | CLEAR - NO FACILITIES. From Pa one call |  |  |  | 2016-08-01
160f | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 |  | UGI Central Penn Gas | Sharon Reese, 570-829-754, sreese1@ugi.com; Scott Kinter, 570-893-6600 | not in PA one call | UG |  |  | 2016-08-01
161a | Y | 161 | 35765 | 56752 | 63401401300733 | 4 | Wayne | SCOTT TWP .5 M E SR 4037 | SR 4014 | BALLS CREEK | 63/219 - SCOTT | 41.9429 | -75.3848 | Elect | Pennsylvania Electric Company | Scott Kinter, 570-893-6600 | Station Entire Project | OH |  | Not Affected | 2015-08-13
161b | Y | 161 | 35765 | 56752 | 63401401300733 | 4 | Wayne | SCOTT TWP .5 M E SR 4037 | SR 4014 | BALLS CREEK | 63/219 - SCOTT | 41.9429 | -75.3848 | Comm | Verizon North LLC | Dan Blodnikar (570) 253-0048 | Station Entire Project | OH |  | Not Affected | 2015-08-13
162a | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR0370 Station 446+20 Right 22' | OH |  | Coordinated | 2015-07-06
162b | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR0370 Station 448+35 Left 38' | OH |  | Coordinated | 2015-07-06
162c | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR0370 Station 450+15 Left 35' | OH |  | Coordinated | 2015-07-06
162d | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR4033 Station 321+74 Left 52' | OH |  | Coordinated | 2015-07-06
162e | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR0370 Station 445+00 Left 237' to SR0370 451+50 Right 64' | OH |  | Coordinated | 2015-07-06
162f | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR0370 Station 448+35 Left 38' to SR4033 Station 318+90 Left 21' | OH |  | Coordinated | 2015-07-06
162g | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR0370 Station 448+35 Left 38' to SR4033 Station 321+74 Left 52' | OH |  | Coordinated | 2015-07-06
162h | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR0370 Station 445+00 Right 237' to SR4033 Station 321+86 Left 25'; SR4033 Station 321+86 Left 25' to SR0370 Station 450+15 Left 35'; SR4033 Station 321+86 Left 25' to SR4033 Station 318+90 Left 21' | OH |  | Coordinated | 2015-07-06
162i | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | SR4033 Station 321+86 Left 25'; SR4033 Station 321+93 Left 27' | OH |  | Coordinated | 2015-07-06
162j | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Comm | Hancock Telephone Company | Dave Niles (607) 637-9944, dniles@hancock.net | SR0370 Station 445+95 Left 26' to SR0370 Station 451+50 Right 64' | OH |  | Coordinated | 2015-07-06
162k | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Comm | Hancock Telephone Company | Dave Niles (607) 637-9944, dniles@hancock.net | SR4033 Station 318+90 Left 21' to SR4033 Station 321+20 Right 27' | OH |  | Coordinated | 2015-07-06
162l | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Comm | Hancock Telephone Company | Dave Niles (607) 637-9944, dniles@hancock.net | SR4033 Station 321+20 Right 27' to SR4033 Station 321+86 Left 27' | OH |  | Coordinated | 2015-07-06
162m | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Pole | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | SR0370 Station 445+95 Left 26' | OH |  | Coordinated | 2015-07-06
162n | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | SR0370 Station 448+35 Left 38' to SR4033 Station 321+74 Left 52' | OH |  | Coordinated | 2015-07-06
162o | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | SR4033 Station 321+20 Right 27' to SR4033 Station 321+86 Left 25' | OH |  | Coordinated | 2015-07-06
163a | -- | 163 | 35810 | 9978 | 63403703303161 | 4 | Wayne | SCOTT TWP .2 M S SR 4043 | SR 4037 | OQUAGA CREEK | 63/219 - SCOTT | 41.9976 | -75.4019 | Elect | PENNSYLVANIA ELEC CO (MA) | Steve Beers sbeers@firstenergycorp.com O - 570-265-1237 C - 607-738-3120 F – 570-265-1258 | DID NOT RESPOND THROUGH PA ONE CALL. |  |  |  | 2016-06-23
163b | -- | 163 | 35810 | 9978 | 63403703303161 | 4 | Wayne | SCOTT TWP .2 M S SR 4043 | SR 4037 | OQUAGA CREEK | 63/219 - SCOTT | 41.9976 | -75.4019 | Comm | VERIZON PENNSYLVANIA LLC (HI) | Daniel J. Blodnikar@verizon.com Phone 570-253-0048 Fax 570 253-2675 | Out Verizon serving area ( See The response) |  |  |  | 2016-06-23
163c | -- | 163 | 35810 | 9978 | 63403703303161 | 4 | Wayne | SCOTT TWP .2 M S SR 4043 | SR 4037 | OQUAGA CREEK | 63/219 - SCOTT | 41.9976 | -75.4019 |  | HANCOCK TELEPHONE COMPANY (HNC) | Robert Wrighter Jr 607-637-9912 robjr@hancocktelephone.com | the project is outside of our territory. TDS Telecom of Deposit is the Telco utility for that area |  |  |  | 2016-06-23
163d | -- | 163 | 35810 | 9978 | 63403703303161 | 4 | Wayne | SCOTT TWP .2 M S SR 4043 | SR 4037 | OQUAGA CREEK | 63/219 - SCOTT | 41.9976 | -75.4019 |  | TDS Telecom | Yvonne Miller, Gen. Mgr. 570-725-3555 F: 570-725-3811 yvonne.miller@TDSTelecom.com | Not on PA one call |  |  |  | 2016-06-23
164a | -- | 164 | 37163 | 10230 | 65026700100659 | 4 | Wyoming | MESHOPPEN BOR .1 M N TR 6 | SR 0267 TR 267 | LITTLE MESHOPPEN CREEK | 65/403 - MESHOPPEN | 41.6145 | -76.0478 | sanitary | Meshoppen Borough | Carlton Shupp, 570-836-1700 | DID NOT RESPOND | UG |  |  | 2016-08-22
164b | -- | 164 | 37163 | 10230 | 65026700100659 | 4 | Wyoming | MESHOPPEN BOR .1 M N TR 6 | SR 0267 TR 267 | LITTLE MESHOPPEN CREEK | 65/403 - MESHOPPEN | 41.6145 | -76.0478 | Comm | FRONTIER COMMUNICATIONS SOLUTIONS (RJ) | 570-879-2175 | Clear no facilities |  |  |  | 2016-08-22
164c | -- | 164 | 37163 | 10230 | 65026700100659 | 4 | Wyoming | MESHOPPEN BOR .1 M N TR 6 | SR 0267 TR 267 | LITTLE MESHOPPEN CREEK | 65/403 - MESHOPPEN | 41.6145 | -76.0478 | Comm | VERIZON PENNSYLVANIA LLC (HI) | Daniel J. Blodnikar@verizon.com Phone 570-253-0048 Fax 570 253-2675 | Verizon serving area . |  |  |  | 2016-08-22
164d | -- | 164 | 37163 | 10230 | 65026700100659 | 4 | Wyoming | MESHOPPEN BOR .1 M N TR 6 | SR 0267 TR 267 | LITTLE MESHOPPEN CREEK | 65/403 - MESHOPPEN | 41.6145 | -76.0478 | Elect | PENNSYLVANIA ELEC CO (MA) | Steve Beers P sbeers@firstenergycorp.com O - 570-265-1237 C - 607-738-3120 | Conflicts in erea , will need plans to verify |  |  |  | 2016-08-22
164e | -- | 164 | 37163 | 10230 | 65026700100659 | 4 | Wyoming | MESHOPPEN BOR .1 M N TR 6 | SR 0267 TR 267 | LITTLE MESHOPPEN CREEK | 65/403 - MESHOPPEN | 41.6145 | -76.0478 |  | Peoples Financial Services Corp | 570-879-2175 | DID NOT RESPOND |  |  |  | 2016-08-22
165 | -- | 165 | 37172 | 10243 | 65029201500354 | 4 | Wyoming | N MORELND TP .1M W SR2009 | SR 0292 TR 292 | BR WHITELOCK CREEK | 65/213 - NORTHMORELAND | 41.4142 | -75.9074 |  | UGI Energy Services | Kurt Zielaskowski, 610-736-5571, kzielaskowski@ugi.com; 717-795-1180 | Conflict. Lines Nearby. |  |  |  | 2016-08-15
166a | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com; Construction Contact - Gary Cluster (570) 278-5562 | Station 133+10 Right | OH |  | Coordinated | 2015-08-28
166b | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com; Construction Contact - Gary Cluster (570) 278-5562 | Station 132+65 to Station 134+25 Right | OH |  | Coordinated | 2015-08-28
166c | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com; Construction Contact - Gary Cluster (570) 278-5562 | Station 133+10 Right | OH |  | Coordinated | 2015-08-28
166d | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | Comm | Blue Ridge Cable Television Inc. | Rick Hebda (570) 836-0919, rhebda@pencor.com | Station Entire Project | OH |  | Not Affected | 2015-08-28
166e | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | Station Entire Project | OH |  | Not Affected | 2015-08-28
167a | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | Elect | Claverack Rural Electric Cooperative, Inc. | Charles Goodwin (570) 265-2167 Ext.327 | Station Entire Project | OH |  | Not Affected | 2016-03-04
167b | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | Comm | Blue Ridge Cable Television Inc. | Dwight (Skip) M. Hunsicker, Chief Plant Engr (610) 826-2551 Ext.314; Construction Contact - Rick Hebda (570) 836-0919 | Station 110+11 to Station 113+03 Left | OH |  | Coordinated | 2016-03-04
167c | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | Comm | Blue Ridge Cable Television Inc. | Dwight (Skip) M. Hunsicker, Chief Plant Engr (610) 826-2551 Ext.314; Construction Contact - Rick Hebda (570) 836-0919 | Station 110+11 to Station 113+03 Left | OH |  | Coordinated | 2016-03-04
167d | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | Pole | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | Station 111+03 Left | OH |  | Coordinated | 2016-03-04
167e | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | Station 113+03 Left | OH |  | Coordinated | 2016-03-04
167f | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | Station 110+11 Left | OH |  | Coordinated | 2016-03-04
167g | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | Station 110+11 to 113+03 Left | OH |  | Coordinated | 2016-03-04
168a | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Rick Moslen, 412-999-0590 | Conflict. Lines Nearby. |  |  |  | 2016-08-01
168b | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | Comm | Verizon | Jeff Kramer <jeffrey.d.kramer@verizon.com> Cell 610-858-8715 Office 610-371-4344 | There are three copper cables, two 300 pair and one 600 pair, and a 72 fiber optic cable attached to the pole line. |  |  |  | 2016-08-01
168c | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | sanitary | Cumru TWP WW Dept | Jeanne Johnston, jjohnston@cumrutowship.org, 610-777-1343; James Sigworth, 610-777-1343, bocandpc@cumrutownship.com | Marked. | UG |  |  | 2016-08-01
168c | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com, 610-921-6157; Michele Heckman, 610-921-6695, mheckman@gpu.com | Conflict. Lines Nearby ( PA one call) Met-ed has no facilities in the vicinity of this bridge ( See the response) |  |  |  | 2016-08-01
168d | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | wtr | Reading Area Water Auth | Renee S. Watt, Renee.Watt@readingareawater.com, 610-406-6321 | Conflict. Lines Nearby. 8" WM on New Holland Road. Please see utility map located in the one call folder for the bridge in sharepoint. RAWA is clear of any facilities in the area of Bridge MPMS 79078, LR518 (PA625) ( from verificaton Response) | UG | 8" |  | 2016-08-01
168e | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | Comm | Service Electric Cablevision, Inc. | Darryl Reccek, 610-868-0902, rec@sectv.com | Conflict. Lines Nearby. |  |  |  | 2016-08-01
168f | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | gas | UGI Utilities, Inc. | Kurt Zielaskowski, 610-736-5571, kzielaskowski@ugi.com | Design Conflict. Please send plans to: Kurt Zielaskowski UGI Utilities Inc. 225 Morgantown Road Reading PA 19611 | UG |  |  | 2016-08-01
169a | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Rick Moslen, 412-999-0590 | Conflict. Lines Nearby. | OH |  |  | 2016-05-02
169b | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | Comm | Frontier Communication | James Zionkowski, OSP Design Engineer Phone-Leesport 610-926-4747; Phone-Harrisburg 717-938-5555; Cell - 717-574-3058. James.zionkowski@ftr.com | This cable is in the Leesport ILEC and consists of 3 copper cables (600 pr, 200 pr, 50 pr) and 2 each 12 FO cables. These poles also have a Comcast cable and a Verizon fiber on them. We also do not own the poles at the bridge. They are owned by VZ. | OH | 3 copper cables (600 pr, 200 pr, 50 pr) and 2 each 12 FO cables |  | 2016-05-02
169c | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | Comm | AT&T | NANCY SPENCE, nspence@ems.att.com. 404-249-9052 | Clear no facility per PA one call | OH |  |  | 2016-05-02
169d | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | Comm | Verizon Pennsylvania LLC | Jeff Kramer, Telecomm Engineer Office 610-371-4344, Cell 610-858-8715 Fax 610-371-4343, jeffrey.d.kramer@verizon.com | Conflict. Lines Nearby. | OH |  |  | 2016-05-02
169e | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | gas | UGI UTILITIES INC (UK) | Jeffrey Frey Ph.: 610-807-3157 F: 610-807-3758 jfrey@ugi.com Kurt Zielaskowski P: 610-736-5571, F:484-955-1042 kzielaskowski@ugi.com | Clear no facility per PA one call |  |  |  | 2016-05-02
169f | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Lynn D Morris Supervisor Engineering Services 610-250-2914, Fax:330-245-5376 Morris, Lynn D lmorris@firstenergycorp.com | CONFLICT. LINES NEARBY. DIRECT CONTACT TO FOLLOW BY FACILITY OWNER. | OH |  |  | 2016-05-02
169g | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | SS & Water | Ontelaunee TWP Municipal Auth | William Mcmullen, Arrow group 570-366-9534. bill.mcmullen@thearrowgroup.com. 610-916-3445; otmunicipalauthority@comcast.net | Marked. | UG |  |  | 2016-05-02
170a | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Lynn D Morris Supervisor Engineering Services 610-250-2914, Fax:330-245-5376 Morris, Lynn D lmorris@firstenergycorp.com |  |  |  |  | 2016-07-11
170b | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | Sanitary | Richmond TWP Municipal Authority | Gary D. Kraft, PE Township Engineer Gary D. Kraft <kraftengr@aol.com>Phone: 610.944.0348, Fax: 610.944.6461 Email: richtwp@ptd.net | Richmond Township does not have any sewer lines within the project area (Response 08/20/15) |  |  |  | 2016-07-11
170c | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | Comm | Service Electric Cablevision, Inc. | Chris Shunk, birdsborooffice@secv.com ; (610) 582-5317 or wcwillie@ptd.net John Turner, Technical Supervisor P:610-868-0902 F:610-625-8588 tur@sectv.com |  |  |  |  | 2016-07-11
170d | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | Comm | Verizon Pennsylvania LLC | Kramer, Jeffrey D (Jeff) Telecomm Engineer Office 610-371-4344, Cell 610-858-8715 Fax 610-371-4343 jeffrey.d.kramer@verizon.com | Need to survey next week. Response of 08/20/15 |  |  |  | 2016-07-11
171a | -- | 171 | 4957 | 85635 | 6100800300000 | 5 | Berks | .5 MI.SOUTH OF HAMBURG | SR 1008 (LR 06125) | WINDSOR CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325 ; Rick Moslen, 412-999-0590 | Conflict. Lines Nearby. |  |  |  | 2016-08-15
171b | -- | 171 | 4957 | 85635 | 6100800300000 | 5 | Berks | .5 MI.SOUTH OF HAMBURG | SR 1008 (LR 06125) | WINDSOR CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com, 610-921-6157; Michele Heckman, 610-921-6695, mheckman@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-08-15
172a | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Rick Moslen, 412-999-0590 | Conflict. Lines Nearby. |  |  |  | 2016-05-24
172b | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | sanitary | Cumru TWP WW Dept | Robert McNichols, bmcnichols@cumrutownship.org, 610-777-1343; James Sigworth (inactive), bocandpc@cumrutownship.com | Marked. Please see utility map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2016-05-24
172c | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com, 610-921-6157; Michele Heckman, 610-921-6695, mheckman@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-05-24
172d | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | Comm | Service Electric Cablevision, Inc. | Darryl Reccek, 610-868-0902, rec@sectv.com | Conflict. Lines Nearby. |  |  |  | 2016-05-24
172e | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 |  | Shillington Borough | Michael Montz, 610-777-1338, info@shillingtonborough.net; Mark S. Reed, 610-777-1338 | Marked. | UG |  |  | 2016-05-24
172f | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | gas | UGI Utilities, Inc. | Kurt Zielaskowski, 610-736-5571, kzielaskowski@ugi.com | Design Conflict. Please send plans to: Kurt Zielaskowski UGI Utilities Inc. 225 Morgantown Road Reading PA 19611 | UG |  |  | 2016-05-24
173a | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 470+61 Right to Station 476+36 Right | OH |  | Prior | 2016-04-08
173b | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | Sewer | Mahoning Township Municipal Authority | Gregory Haas (570) 645-9545, carbonei@ptd.net | Station 472+25 Left to Station 473+00 Right | UG |  | Not Affected | 2016-04-08
173c | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | Water | Lehighton Water Authority | Nicole Nothstein (610) 377-1912, waterlwa@ptd.net; Armen Galasso (610) 377-5585 | Station 470+90 Left to Station 476+00 Right | UG |  | Not Affected | 2016-04-08
173d | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 470+61 Right to Station 476+36 Right | OH |  | Prior | 2016-04-08
173e | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | Station 470+61 Right to Station 476+36 Right | OH |  | Prior | 2016-04-08
173f | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | Gas | UGI Central Penn Gas | Taylor Bet (610) 807-3140, tbet@ugi.com | Station 470+00 Right to Station 476+00 Right | UG |  | Prior | 2016-04-08
174a | -- | 174 | 9104 | 85762 | 13401000501489 | 5 | Carbon | GERHARDS, QUAKAKE RD. | SR 4010(LR 13025) | QUAKAKE CREEK | 13/210 - PACKER | 40.8892 | -75.9184 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3658 | UG |  |  | 2017-06-05
174b | -- | 174 | 9104 | 85762 | 13401000501489 | 5 | Carbon | GERHARDS, QUAKAKE RD. | SR 4010(LR 13025) | QUAKAKE CREEK | 13/210 - PACKER | 40.8892 | -75.9184 | wtr | Hazleton City Auth Water Dept | 570-454-2401 | DID NOT RESPOND | UG |  |  | 2017-06-05
175a | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | Comm | RCN Telecom Services Inc | Bill Reese, 610-443-2956, bill.reese@rcn.net | Conflict. Lines Nearby |  |  |  | 2017-03-03
175b | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 |  | City of Allentown | Brian Borzak, 610-437-7574 | Marked. | UG |  |  | 2017-03-03
175c | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | comm | AT&T Atlanta | 404-249-9052 | Marked. |  |  |  | 2017-03-03
175d | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 |  | Lehigh Cnty Auth | Frank Leist, 610-398-2503, frankleist@lehighcountyauthority.org | Design Conflict. Please send plans to: Jason Peters Lehigh Cty Auth 1053 Spruce ST PO Box 3348 Allentown PA 18016 | UG |  |  | 2017-03-03
175e | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-4127 | UG |  |  | 2017-03-03
175f | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 |  | South Whitehall TWP | Gerald Gasda, 610-398-0401 | Design Conflict. Please send plans to: James Balliet South Whitehall TWP 4444 Walbert Ave Allentown, PA 18104 | UG |  |  | 2017-03-03
175g | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | Design Conflict. Please send plans to: Luke Lichtenwalner UGI Utilities Inc. 2121 City Line Rd Bethlehem PA 18017 | UG |  |  | 2017-03-03
175h | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | Comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175 | Conflict. Lines Nearby. Verizon does have underground cable at this location. UG cables on Hamilton crossing cedar creek. Please see utility map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-03-03
176a | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 |  | Catasauqua Borough | 610-264-0571, manager@catasauqua.org | DID NOT RESPOND | UG |  |  | 2017-03-09
176b | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3296 | UG |  |  | 2017-03-09
176c | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | Comm | RCN Telecom Services Inc | Bill Reese, 610-443-2956, bill.reese@rcn.net | Conflict. Lines Nearby |  |  |  | 2017-03-09
176d | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | Design Conflict. Please send plans to: Luke Lichtenwalner UGI Utilities Inc. 2121 City Line Rd Bethlehem PA 18017 | UG |  |  | 2017-03-09
176e | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175; Deborah D. Deila, 412-633-3810, deborah.d.deila@verizon.com | Conflict. Lines Nearby. |  |  |  | 2017-03-09
177a | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175 | Conflict. Lines Nearby. Verizon does have underground cable at this location. Please see the utility map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-05-22
177b | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | wtr | Bethlehem City Dept of Wtr/Swr Resources | Robert Taylor, Rtaylor@bethlehem-pa.gov, 610-997-7947 | Marked. 8" CI WM at bridge. Please see utility as-builts in the onecall folder for the bridge in sharepoint | UG |  |  | 2017-05-22
177c | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | Elect | PPL Electric Utilities Corporation | Jennifer Perdick, 1-800-342-5775, jperdick@pplweb.com, Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | PPL Electric Utilities maps indicate there are underground facilities in the area of your request. Please see the utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-05-22
177d | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | Design Conflict. Please send plans to: Luke Lichtenwalner UGI Utilities Inc. 2121 City Line Rd Bethlehem PA 18017 |  |  |  | 2017-05-22
177e | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 |  | Upper Saucon TWP Wtr Swr Dept | 610-694-8680 | Marked. | UG |  |  | 2017-05-22
178a | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | comm | AT&T Atlanta | 404-249-9052 | Marked. |  |  |  | 2017-02-13
178b | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 |  | Lehigh Cnty Auth | Frank Leist, 610-398-2503, frankleist@lehighcountyauthority.org | Conflict. Lines Nearby. Field Marked. | UG |  |  | 2017-02-13
178c | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3296 | UG |  |  | 2017-02-13
178d | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | Design Conflict. Please send plans to: Luke Lichtenwalner UGI Utilities Inc. 2121 City Line Rd Bethlehem PA 18017 | UG |  |  | 2017-02-13
178e | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175; Deborah D. Deila, 412-633-3810, deborah.d.deila@verizon.com | Conflict. Lines Nearby. Verizon does have underground cable at this location. UG cables on rt 222 crosses on north side of bridge. Please see utility map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-02-13
178f | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 |  | LEC TRO | [5 empty] | 2017-02-13
179a | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities exist in the area. Please see field maps located in the one call folder in sharepoint for this bridge. The plans do not show underground service facilities. | OH |  |  | 2017-03-20
179b | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | GAS | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | DID NOT RESPOND |  |  |  | 2017-03-20
179c | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | Comm | Blue Ridge Cable Television Inc. | Dwight “Skip” Hunsicker dhunsicker@brctv.com 400 Little Gap Road Palmerton, PA 18071 610-826-9312 | Conflicts in area , attached to PPL poles | OH |  |  | 2017-03-20
179d | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | comm | Commonwealth Telephone | Steve Lathrop, 570-278-0036 Patrick Galli, 570-208-6458 Patrick.Galli@FTR.com | Not Frontier territory, no facilities in the project area. |  |  |  | 2017-03-20
179e | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | comm | Palmerton Telephone | Jeff Lutz Phone: 610-826-9263, Fax:610-826-9122 jlutz@ptelco.com, 610-826-6650 | Responded with plan showing palmerton telephone facilities | OH |  |  | 2017-03-20
180a | Y | 180 | 26795 | 91680 | 45020903110000 | 5 | Monroe | AT JUNCT. WITH PA33 SB | SR 209 & SR 33SB | APPENZELL CREEK | 45/205 - HAMILTON | 40.9557 | -75.2876 | N/A | N/A | N/A | None | N/A | N/A | Not Affected | 2016-05-23
181a | Y | 181 | 26811 | 79157 | 45031401101750 | 5 | Monroe | 2.5 M. S.OF SWIFTWATER | PA 314(LR45025) | SWIFTWATER CREEK | 45/208 - PARADISE | 41.0911 | -75.288 | N/A | N/A | N/A | None | N/A |  | Not Affected | 2015-07-30
182a | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 646+65 Rt. to Sta. 650+40 Lt. | OH |  | Coordinated | 2015-12-31
182b | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 646+65 Rt. to Sta. 650+40 Lt. | OH |  | Coordinated | 2015-12-31
182c | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | Sta. 646+95 Rt. to Sta. 649+90 Rt./Lt. | OH |  | Coordinated | 2015-12-31
182d | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | Sta. 646+95 Rt. to Sta. 649+90 Rt./Lt. | OH |  | Coordinated | 2015-12-31
182e | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | Sta. 648+69 Lt. | OH |  | Coordinated | 2015-12-31
182f | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | Sta. 649+86 Rt. to Sta. 650+13 Lt. to Sta. 651+27 Lt. | UG |  | Not Affected | 2015-12-31
182g | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Water | Aqua Pennsylvania | Jennifer Cathers (610) 525-1400 jccathers@aquaamerica.com | Sta. 647+25 Rt. to Sta. 649+90 Rt. | UG |  | Not Affected | 2015-12-31
182h | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Sta. 646+95 Rt. to Sta. 651+25 Rt./Lt. | OH |  | Coordinated | 2015-12-31
182i | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | Comm | SUNESYS, INC. | James O’Brien (610) 884-1395, jobrien@sunesys.com | Sta. 646+95 Rt. to Sta. 651+25 Rt./Lt. | OH |  | Coordinated | 2015-12-31
183a | Y | 183 | 26887 | 11649 | 45061105100000 | 5 | Monroe | TOBYHANNA | SR 611(LR 168) | TOBYHANNA CREEK | 45/203 - COOLBAUGH | 41.1732 | -75.4152 | N/A | N/A | N/A | None | N/A |  | Not Affected | 2015-09-01
184a | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 53+00 Lt. to Sta. 57+00 Lt. | OH |  | Coordinated | 2016-05-26
184b | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 53+80 Lt. to Sta. 57+00 Lt./Rt. | OH |  | Coordinated | 2016-05-26
184c | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | Sta. 54+00 Lt. to Sta. 58+00 Lt | OH |  | Coordinated | 2016-05-26
184d | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | Sta. 54+00 Lt. to Sta. 58+00 Lt | OH |  | Concurrent | 2016-05-26
184e | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Sta. 54+00 Lt. to Sta. 58+00 Lt | OH |  | Coordinated | 2016-05-26
184f | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Sta. 54+00 Lt. to Sta. 58+00 Lt | OH |  | Concurrent | 2016-05-26
185a | Y | 185 | 26901 | 96445 | 45090300200000 | 5 | Monroe | 0.33 MI.W.OF PA 115 | SR 903 (LR 550) | TRIB.TO TUNKHANNOCK CK. | 45/216 - TUNKHANNOCK | 41.0528 | -75.5539 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 918+00 Rt. to Sta. 922+50 Lt. | OH |  | Coordinated | 2016-02-29
185b | Y | 185 | 26901 | 96445 | 45090300200000 | 5 | Monroe | 0.33 MI.W.OF PA 115 | SR 903 (LR 550) | TRIB.TO TUNKHANNOCK CK. | 45/216 - TUNKHANNOCK | 41.0528 | -75.5539 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | Sta. 918+15 Lt. to Sta. 922+10 Lt. | OH |  | Coordinated | 2016-02-29
186a | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 281+25 Left to Station 285+75 Left | OH |  | Not Affected | 2015-07-27
186b | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | Station 280+70 Right to Station 285+75 Right | OH |  | Not Affected | 2015-07-27
186c | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 281+25 Left to Station 285+75 Left | OH |  | Not Affected | 2015-07-27
186d | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | Gas | UGI Utilities, Inc. | Luke Lichtenwalner (610) 807-3140, lichtenwalner@ugi.com | Station 283+30 Right to Station 285+30 Right | UG |  | Prior | 2015-07-27
187a | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 456+00 Rt. to Sta. 463+00 Rt. | OH |  | Coordinated | 2016-03-02
187b | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Comm | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 456+00 to Sta. 463+00 Lt. | OH |  | Coordinated | 2016-03-02
187c | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Comm | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 456+00 to Sta. 463+00 Lt. | OH |  | Coordinated | 2016-03-02
187d | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | Sta. 447+70 Lt. to Sta. 456+20 Rt. | OH |  | Coordinated | 2016-03-02
187e | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | Sta. 456+00 Lt. to Sta. 463+30 Rt. | OH |  | Coordinated | 2016-03-02
187f | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | Sta. 456+00 Lt. to Sta. 463+30 Rt. | OH |  | Coordinated | 2016-03-02
187g | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Comm | Level 3 | Kou Yang (570) 300-2910, Kou.yang@Level3.com | Sta. 455+00 Lt. to Sta. 463+00 Rt. | OH |  | Coordinated | 2016-03-02
187h | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 456+20 Left to Station 460+75 Right | OH |  | Coordinated | 2016-03-02
188a | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 1069+50 Rt/Lt to Station 1072+00 Rt/Lt | OH |  | Coordinated | 2016-03-08
188b | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 1069+50 Rt/Lt to Station 1072+00 Rt/Lt | OH |  | Coordinated | 2016-03-08
188c | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 1069+60 Left to Station 1071+85 Right | OH |  | Coordinated | 2016-03-08
188d | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | Comm | Verizon Pennsylvania, Inc. | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | Station 1069+60 Left to Station 1071+85 Right | OH |  | Coordinated | 2016-03-08
189a | Y | 189 | 26924 | 79170 | 45100400300941 | 5 | Monroe | 1.2 M. E. OF PA 314 | SR 1004(LR 45027) | PARADISE CREEK | 45/208 - PARADISE | 41.1018 | -75.2696 | N/A | N/A | N/A | None | N/A |  | Not Affected | 2016-03-14
190a | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 14+35 Right to Station 19+50 Left | OH |  | Prior | 2015-12-15
190b | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | Station 14+35 Right to Station 19+50 Left | OH |  | Prior | 2015-12-15
190c | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 633-3810, deborah.d.delia@verizon.com | Station 14+35 Right to Station 19+50 Left | OH |  | Prior | 2015-12-15
190d | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 14+35 Right to Station 19+50 Left | OH |  | Prior | 2015-12-15
190e | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | Gas | UGI Central Penn Gas | Tom O'Neill (610) 807-3701, to'neill@ugi.com | Station 14+00 Right to Station 20+50 Right | UG |  | Not Affected | 2015-12-15
190f | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | Water | Brodhead Creek Regional Authority | Chris Borger (570) 421-3232, cborger@ptd.net | Station 14+55 to Station 20+50 Right | UG |  | Not Affected | 2015-12-15
191a | Y | 191 | 27011 | 96447 | 45300900220000 | 5 | Monroe | T-939 S.OF MERWINSBURG | SR3009(45066)T-939 | POHOPOCO CREEK | 45/202 - CHESTNUTHILL | 40.951 | -75.4473 | N/A | N/A | N/A | None | N/A |  | Not Affected | 2016-06-09
192a | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 70+50 Lt. to Sta. 74+50 Lt. | OH |  | Coordinated | 2016-03-14
192b | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 70+50 Lt. to Sta. 74+50 Lt. | OH |  | Coordinated | 2016-03-14
192c | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Sta. 73+35 Lt. | OH |  | Coordinated | 2016-03-14
192d | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Sta. 72+60 Lt. to Sta. 73+45 Lt. | OH |  | Coordinated | 2016-03-14
192e | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, e-mail j.anthony.snyder@verizon.com; Bill Wojcik (570) 424-0058, william.wojcik@verizon.com | Sta. 70+70 Lt. to Sta. 73+45 Lt. | OH |  | Coordinated | 2016-03-14
| R | 193 | 27022 | #REF! | 45301500201644 | 5 | Monroe | ROLLING HILLS ROAD | #N/A | AQUASHICOLA CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | [7 empty] | 2016-03-14
194a | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 169+00 Right to Station 172+50 Right | OH |  | Coordinated | 2015-07-14
194b | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 169+00 Right to Station 172+50 Right | OH |  | Coordinated | 2015-07-14
194c | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | Station 169+50 Right to Station 171+90 Right | OH |  | Coordinated | 2015-07-14
194d | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | Station 169+50 Right to Station 171+90 Right | OH |  | Coordinated | 2015-07-14
194e | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 169+50 Right to Station 171+90 Right | OH |  | Coordinated | 2015-07-14
195a | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 153+00 Right to Station 156+00 Left | OH |  | Coordinated | 2016-05-16
195b | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 153+00 Left to Station 156+00 Left | OH |  | Coordinated | 2016-05-16
195c | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 153+00 Right to Station 156+00 Left | OH |  | Coordinated | 2016-05-16
195d | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | Station 153+00 Left to Station 156+00 Left | OH |  | Coordinated | 2016-05-16
195e | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 153+00 Left to Station 155+75 Left | OH |  | Coordinated | 2016-05-16
196a | Y | 196 | 27059 | 79187 | 45400600200000 | 5 | Monroe | .7 M. W.OF LR 45024 | SR 4006(LR45024SP) | POCONO CREEK | 45/209 - POCONO | 41.0538 | -75.3403 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 34+55 Left to Station 38+85 Right | OH |  | Prior | 2016-05-23
196b | Y | 196 | 27059 | 79187 | 45400600200000 | 5 | Monroe | .7 M. W.OF LR 45024 | SR 4006(LR45024SP) | POCONO CREEK | 45/209 - POCONO | 41.0538 | -75.3403 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 231-2285, deborah.d.delia@verizon.com | Station 34+55 Left to Station 38+85 Right | OH |  | Prior | 2016-05-23
196c | Y | 196 | 27059 | 79187 | 45400600200000 | 5 | Monroe | .7 M. W.OF LR 45024 | SR 4006(LR45024SP) | POCONO CREEK | 45/209 - POCONO | 41.0538 | -75.3403 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | Station 34+55 Left to Station 38+85 Right | OH |  | Prior | 2016-05-23
197a | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | GAS | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | DID NOT RESPOND | UG |  |  | 2016-06-16
197b | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 |  | Bethlehem TWP Municipal Auth/Bethlehem TWP | Matthew Dorner, Chief of Engineering, 610-865-7067, mdorner@bethlehem-pa.gov | Conflict. Lines Nearby. | UG |  |  | 2016-06-16
197c | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3231 | UG |  |  | 2016-06-16
197d | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | Comm | RCN Telecom Services Inc | Bill Reese, 610-443-2956, bill.reese@rcn.net | Conflict. Lines Nearby |  |  |  | 2016-06-16
198a | -- | 198 | 28494 | 104632 | 48003300210000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | GAS | Amerigas Propane LP | Gary, 484-426-7265; Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | Did Not Respond. Gary with Amerigas left VM for a return call. 484-426-7265 | UG |  |  | 2016-06-16
198b | -- | 198 | 28494 | 104632 | 48003300210000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | wtr | Bethlehem TWP Municipal Auth/Bethlehem TWP | Steven Hunsberger, steven@bethlehemtwp.com, 610-814-6400 | Did Not Respond | UG |  |  | 2016-06-16
| R | 199 | 42278 | #REF! | 48003301200000 | 5 | Northampton | 0.5 MI S OF PA 191 EXIT | #N/A | BUSHKILL CREEK | 48/101 - BETHLEHEM | 40.6828 | -75.289 | [7 empty] | 2016-06-16
| R | 200 | 42446 | #REF! | 48003301210000 | 5 | Northampton | 0.5MI S OF PA 191 EXIT | #N/A | BUSHKILL CREEK | 48/101 - BETHLEHEM | 40.6828 | -75.289 | [7 empty] | 2016-06-16
201a | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.3658 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com |  |  |  |  | 2017-05-24
201b | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.3658 | Comm | Frontier Communications Solution (RCN) | Galli Patrick 570-208-6458 Patrick.Galli@FTR.com Bill Reese, 610-443-2783, Bill.Reese@rcn.net | Fiber cable that runs from NorBath to Wind Gap may be involved . Out Frontier ILEC territory , The cable is RCN's responsibility |  |  |  | 2017-05-24
201c | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.3658 | Comm | VERIZON PENNSYLVANIA LLC (YJ) | Vince Pawlicki, Engineer Network Services Tel: 215-591-6306, Fax: 215-591-6101, Cell: 215-880-8995 Email: vincent.pawlicki@verizon.com | Verizon has aerial facilities and poles within the project area as shown on plan and Verizon could have an abandon buried cable |  |  |  | 2017-05-24
201d | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.3658 | Comm | SERVICE ELECTRIC CABLE TV INC (SET) | Darryl Reccek, Construction Manager P:610-868-0902 F: 610-865-0633 rec@sectv.com |  |  |  |  | 2017-05-24
201e | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.366 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY (MK) | Lynn D Morris Supervisor Engineering Services 610-250-2914, Fax:330-245-5376 Morris, Lynn D lmorris@firstenergycorp.com | First Energy has no facilities in erea |  |  |  | 2016-07-07
201f | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.3658 | Gas | UGI UTILITIES INC (UJ) | Jeffrey Frey Ph.: 610-807-3157 F: 610-807-3758 jfrey@ugi.com Kurt Zielaskowski P: 610-736-5571, F:484-955-1042 kzielaskowski@ugi.com |  |  |  |  | 2017-05-24
201g | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.366 | Water & SS | WIND GAP MUNICIPAL AUTHORITY (OU1) | Terry L. Miklas, Sr 610-863-7770 Tlmwgma@frontier.com |  |  |  |  | 2016-07-07
202a | -- | 202 | 28660 | 67256 | 48100400601655 | 5 | Northampton | 3 MI.W.OF RIVERTON | SR 1004 (LR 48025) | OUGHOUGHTON CREEK | 48/208 - LOWER MT BETHEL | 40.8027 | -75.126 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-4127 | UG |  |  | 2016-06-21
202b | -- | 202 | 28660 | 67256 | 48100400601655 | 5 | Northampton | 3 MI.W.OF RIVERTON | SR 1004 (LR 48025) | OUGHOUGHTON CREEK | 48/208 - LOWER MT BETHEL | 40.8027 | -75.126 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Brian Stoner, bstoner@firstenergycorp.com, 717-848-7181; Michele Heckman, 610-921-6695, mheckman@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-06-21
203a | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 | GAS | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | DID NOT RESPOND | UG |  |  | 2016-09-12
203b | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 |  | Bangor Borough Auth | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | DID NOT RESPOND | UG |  |  | 2016-09-12
203c | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 |  | East Bangor Municipal Auth | 610-588-4656, info@eastbangorborough.org | DID NOT RESPOND |  |  |  | 2016-09-12
203d | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Brian Stoner, bstoner@firstenergycorp.com, 717-848-7181; Michele Heckman, 610-921-6695, mheckman@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-09-12
203e | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 |  | Washington TWP Northampton | 610-588-1524 | DID NOT RESPOND |  |  |  | 2016-09-12
204a | Y | 204 | 30678 | 12717 | 53033902000276 | 5 | Schuylkill | VILLAGE OF ZIONS GROVE | PA 339 | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9031 | -76.21 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 9+75 Right to Station 10+00 Right | OH |  | Coordinated | 2015-07-21
204b | Y | 204 | 30678 | 12717 | 53033902000276 | 5 | Schuylkill | VILLAGE OF ZIONS GROVE | PA 339 | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9031 | -76.21 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | Station 9+77 Right to Station 11+61 Right | OH |  | Coordinated | 2015-07-21
205a | Y | 205 | 30679 | 99559 | 53033902400902 | 5 | Schuylkill | CATAWISSA CREEK ROAD | PA 339 (LR 53091) | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9212 | -76.2264 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 90+10 Right to Station 95+30 Left | OH |  | Coordinated | 2015-09-25
205b | Y | 205 | 30679 | 99559 | 53033902400902 | 5 | Schuylkill | CATAWISSA CREEK ROAD | PA 339 (LR 53091) | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9212 | -76.2264 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | Station 89+64 Left to Station 95+30 Left | OH |  | Coordinated | 2015-09-25
206a | Y | 206 | 30680 | 12710 | 53033902401098 | 5 | Schuylkill | CATAWISSA CREEK ROAD | SR 339(LR 53091) | TRIB.TO CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9217 | -76.2265 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 90+10 Right to Station 95+35 Left | OH |  | Coordinated | 2015-10-31
206b | Y | 206 | 30680 | 12710 | 53033902401098 | 5 | Schuylkill | CATAWISSA CREEK ROAD | SR 339(LR 53091) | TRIB.TO CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9217 | -76.2265 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | Station 80+64 Left to Station 95+30 Left | OH |  | Coordinated | 2015-10-31
207a | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 110+49 Left to Station 116+15 Right | OH |  | Prior | 2016-02-17
207b | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | Comm | Verizon Pennsylvania LLC | Ronald Silinski (570) 826-4263, ronald.w.silinskie@verizon.com; Kevin Brown (570) 826-4033, kevin.j.brown@verizon.com | Station 110+49 Left to Station 116+15 Right | OH |  | Prior | 2016-02-17
207c | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | Comm | Service Electric Cablevision, Inc. | William Brayford (570) 773-2585, mahanoycity@secv.com | Station 110+49 Left to Station 116+15 Right | OH |  | Prior | 2016-02-17
207d | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | Sewer | Borough of Shenandoah | Joe Palubinsky (570) 462-1918 | Station 113+00 Left to Station 113+50 Right | UG |  | Not Affected | 2016-02-17
207e | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | Water | Shenendoah Municipal Authority | Rich **** (570) 233-5319 | Station 111+75 Left to Station 114+00 Left | UG |  | Not Affected | 2016-02-17
208a | Y | 208 | 30832 | 85724 | 53401600100000 | 5 | Schuylkill | VILLAGE OF KLINGERSTOWN | SR 4016 (LR 53047) | MAHANTANGO CREEK | 53/231 - UPPER MAHANTANG | 40.6616 | -76.6866 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 42+75 Right to Station 47+40 Right | OH |  | Coordinated | 2015-07-27
208b | Y | 208 | 30832 | 85724 | 53401600100000 | 5 | Schuylkill | VILLAGE OF KLINGERSTOWN | SR 4016 (LR 53047) | MAHANTANGO CREEK | 53/231 - UPPER MAHANTANG | 40.6616 | -76.6866 | Comm | Comcast Cable Communications, Inc. | Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com; Gary Kissinger (610) 589-1415, Gary_Kissinger@cable.comcast.com | Station 42+75 Left to Station 47+40 Left | OH |  | Coordinated | 2015-07-27
208c | Y | 208 | 30832 | 85724 | 53401600100000 | 5 | Schuylkill | VILLAGE OF KLINGERSTOWN | SR 4016 (LR 53047) | MAHANTANGO CREEK | 53/231 - UPPER MAHANTANG | 40.6616 | -76.6866 | Comm | TDS Telcom | Stewart Walker (315) 562-0091, stewart.walker@tdstelecom.com | Station 42+75 Left to Station 47+40 Left | OH |  | Coordinated | 2015-07-27
209a | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 11+77 Left to Station 16+70 Left | OH |  | Not Affected | 2016-05-23
209b | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | Sta. 14+50 Lt. to Sta. 15+25 Lt. | OH |  | Coordinated | 2016-05-23
209c | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | Station 11+00 Right to Station 17+50 Left | OH |  | Coordinated | 2016-05-23
209d | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | Comm | Service Electric Cablevision, Inc. | Robert Trently (570) 454-3841, robert.trently@secv.com | Station 11+00 Right to Station 17+50 Left | OH |  | Coordinated | 2016-05-23
210a | Y | 210 | 30862 | 12522 | 53403900200000 | 5 | Schuylkill | VILLAGE OF HAAS | SR 4039 (LR 53055) | MAHANTANGO CREEK | 53/210 - ELDRED | 40.7038 | -76.4901 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | Station 14+00 Left to Station 19+00 Left | OH |  | Restrictive | 2015-07-15
210b | Y | 210 | 30862 | 12522 | 53403900200000 | 5 | Schuylkill | VILLAGE OF HAAS | SR 4039 (LR 53055) | MAHANTANGO CREEK | 53/210 - ELDRED | 40.7038 | -76.4901 | Comm | Verizon Pennsylvania, LLC | Jerry Van Buskirk (570) 374-0412, jerry.vanbuskirk@verizon.com | Station 14+20 Left to Station 16+50 Left | OH |  | Coordinated | 2015-07-15
211a | -- | 211 | 7262 | 56830 | 9203701900000 | 6 | Bucks | BILLBOARD 38C08 (3151E10) | LINCOLN HIGHWAY | EAST BR.QUEEN ANNE CREEK | 09/208 - FALLS | 40.1878 | -74.8468 |  | TWP of Falls Authority | 215-946-6062, info@tofa-pa.com | Marked. | UG |  |  | 2017-04-03
211b | -- | 211 | 7262 | 56830 | 9203701900000 | 6 | Bucks | BILLBOARD 38C08 (3151E10) | LINCOLN HIGHWAY | EAST BR.QUEEN ANNE CREEK | 09/208 - FALLS | 40.1878 | -74.8468 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2017-04-03
212 | -- | 212 | 10497 | 81284 | 15304401300000 | 6 | Chester | NEAR WEST GROVE 45F06 (3799E7) | EWING ROAD | MIDDLE BR WHITE CLAY CR | 15/222 - LONDON GROVE | 39.8326 | -75.8452 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2017-03-06
213 | -- | 213 | 10599 | 86306 | 15400800402407 | 6 | Chester | BRANDYWINE MANOR 19E02 (3360E09) | INDIAN RUN DRIVE | INDIAN RUN | 15/241 - WALLACE | 40.0722 | -75.7863 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2016-09-19
214a | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2016-08-04
214c | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | Comm | Comcast | Rich Kain 610-633-1268 Richard_Kain@cable.comcast.com Delaware County 610-633-1268 | Comcast facilities highlighted in yellow on map ( see response) |  |  |  | 2016-08-04
214c | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | Conflict. Lines Nearby. | UG |  |  | 2016-08-04
214d | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | sanitary | Central Delaware County Auth | Phillip Dossou, Pdossou@cataniaengineering.com | Design Conflict. Please send plans to: Gennifer Guiliano Central Delware County Auth 212B Unity Ter Rutledge PA 19070. 30" rcp sanitary line that follows stoney creek and then crosses Kedron Ave. near bridge. Please utility as-builts located in the one call folder for the bridge in sharepoint. | UG | 30" |  | 2016-08-04
214e | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | wtr | Township of Ridley | Margaret Keegan, 610-534-4806, pkeegan@mail.twp.ridley.pa.us | Marked. | UG |  |  | 2016-08-04
215a | -- | 215 | 27513 | 102315 | 46066302700894 | 6 | Montgomery | PERKIOMEN HEIGHTS 02D13 | LAYFIELD ROAD | BRCH PERKIOMEN CR/2916H1 | 46/219 - UPPER HANOVER | 40.3734 | -75.5184 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2017-03-24
215b | -- | 215 | 27513 | 102315 | 46066302700894 | 6 | Montgomery | PERKIOMEN HEIGHTS 02D13 | LAYFIELD ROAD | BRCH PERKIOMEN CR/2916H1 | 46/219 - UPPER HANOVER | 40.3734 | -75.5184 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3296 | UG |  |  | 2017-03-24
216a | -- | 216 | 27605 | 102218 | 46201300320000 | 6 | Montgomery | 1.5MI.WEST PHILA. 33C07 | PHILMONT AVENUE | VALLEY CR. 3372B1 | 46/105 - LOWER MORELAND | 40.1219 | -75.0515 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | Conflict. Lines Nearby. | UG |  |  | 2017-03-08
216b | -- | 216 | 27605 | 102218 | 46201300320000 | 6 | Montgomery | 1.5MI.WEST PHILA. 33C07 | PHILMONT AVENUE | VALLEY CR. 3372B1 | 46/105 - LOWER MORELAND | 40.1219 | -75.0515 | sanitary | Lower Moreland TWP | 215-947-3100 | Marked. | UG |  |  | 2017-03-08
216c | -- | 216 | 27605 | 102218 | 46201300320000 | 6 | Montgomery | 1.5MI.WEST PHILA. 33C07 | PHILMONT AVENUE | VALLEY CR. 3372B1 | 46/105 - LOWER MORELAND | 40.1219 | -75.0515 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2017-03-08
217a | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | Conflict. Lines Nearby. | UG |  |  | 2017-03-24
217b | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2017-03-24
217c | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | wtr | Philadelphia City Water Dept | Charles H. Sawyer, 215-686-3410 | Conflict. Lines Nearby. | UG |  |  | 2017-03-24
217d | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | sanitary | Bucks County Water and Sewer Auth | James Napoleon, jimnapoleon@bcwsa.net | Did not show up on one-call but has sanitary lines on pennsylvania ave in the area of the project. Please see the utility map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-03-24
218a | -- | 218 | 27757 | 67373 | 46304400500389 | 6 | Montgomery | WYNNEWOOD;WOODSIDE 3478H10 | WYNNWOOD ROAD | BRANCH INDIAN CREEK | 46/412 - NARBERTH | 40.0033 | -75.2683 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | Conflict. Lines Nearby. | UG |  |  | 2016-09-01
218b | -- | 218 | 27757 | 67373 | 46304400500389 | 6 | Montgomery | WYNNEWOOD;WOODSIDE 3478H10 | WYNNWOOD ROAD | BRANCH INDIAN CREEK | 46/412 - NARBERTH | 40.0033 | -75.2683 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Conflict. Lines Nearby. |  |  |  | 2016-09-01
218c | -- | 218 | 27757 | 67373 | 46304400500389 | 6 | Montgomery | WYNNEWOOD;WOODSIDE 3478H10 | WYNNWOOD ROAD | BRANCH INDIAN CREEK | 46/412 - NARBERTH | 40.0033 | -75.2683 | Comm | Verizon Pennsylvania LLC | Cindy Oberholtzer, 570-387-3175, coberholtzer@usceng.com.; Norman Parrish, 610-280-2152, norman.l.parrish@verizon.net | Conflict. Lines Nearby. Verizon does have underground cable at this location. Please see the utility map located in the one call folder for the bridge in sharepoint. It shows their lines at the intersection of e. wynnewood and Woodside. | UG |  |  | 2016-09-01
219a | -- | 219 | 27868 | 81290 | 46404200341011 | 6 | Montgomery | NW POTTSTOWN 11B6/3026C8 | GROSSTOWN ROAD | MANATAWNY CREEK | 46/112 - WEST POTTSGROVE | 40.267 | -75.6728 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 | Please see the utility map located in the one call folder for the bridge in sharepoint. |  |  |  | 2016-07-28
219b | -- | 219 | 27868 | 81290 | 46404200341011 | 6 | Montgomery | NW POTTSTOWN 11B6/3026C8 | GROSSTOWN ROAD | MANATAWNY CREEK | 46/112 - WEST POTTSGROVE | 40.267 | -75.6728 | Comm | Verizon Pennsylvania LLC | Cindy Oberholtzer, coberholtzer@usceng.com , 570-387-3175 | Please see the utility map located in the one call folder for the bridge in sharepoint. Buried cable that crosses Grosstown Rd at Manatawny Creek | UG |  |  | 2016-07-28
220a | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-04-03
220b | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | GAS | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com, rian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-04-03
220c | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2017-04-03
220d | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | sanitary | Gettysburg Borough | 717-334-1160 | Marked. | UG |  |  | 2017-04-03
220e | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | sanitary | Gettysburg Municipal Auth | Mark Guise, 717-334-6738 | Marked. | UG |  |  | 2017-04-03
220f | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-04-03
221a | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby |  |  |  | 2017-05-31
221b | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | sanitary | Bendersville Borough | Andrea Rivera, secretary@bendersvilleborough.net, 717-677-8112. Ken McKee, 717-677-7857 | DID NOT RESPOND | UG |  |  | 2017-05-31
221c | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-05-31
221d | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. Please see utility map located in onecall folder for bridge in sharepoint . | UG |  |  | 2017-05-31
221e | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-05-31
221f | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-05-31
222a | -- | 222 | 75 | 87417 | 1003402700000 | 8 | Adams | IDAVILLE | PA 34; SR 0034 | BERMUDIAN CREEK | 01/220 - TYRONE | 40.0131 | -77.2029 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2016-07-13
222b | -- | 222 | 75 | 87417 | 1003402700000 | 8 | Adams | IDAVILLE | PA 34; SR 0034 | BERMUDIAN CREEK | 01/220 - TYRONE | 40.0131 | -77.2029 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-07-13
222c | -- | 222 | 75 | 87417 | 1003402700000 | 8 | Adams | IDAVILLE | PA 34; SR 0034 | BERMUDIAN CREEK | 01/220 - TYRONE | 40.0131 | -77.2029 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-07-13
223a | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-03-21
223b | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-03-21
223c | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-03-21
223d | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-03-21
224a | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby |  |  |  | 2016-05-23
224b | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | Comm | Centurylink formerly Embarq | Perry Byers (until December 2016), 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com, Matt 814-935-5365 | Conflict. Lines Nearby. |  |  |  | 2016-05-23
224c | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-05-23
224d | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-05-23
224e | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2016-05-23
225a | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | sanitary | Abbottstown Borough | Loreen Greer, abbottstwon@comcast.net, 717-259-0965 | Marked. | UG |  |  | 2016-05-27
225b | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | sanitary | Abbottstown Paradise Joint Sewer Auth | Amy E. Perry, 717-259-9120, aperry@apjsawwtf.comcastbiz.net; P. O. Box 505, Abbottstown, PA 17301 | Marked. | UG |  |  | 2016-05-27
225c | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-92; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby |  |  |  | 2016-05-27
225d | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Centurylink currently has a 48 Aerial fiber/10M strand (marked in red) attached to existing Met-Ed poles. no bridge attachments. |  |  |  | 2016-05-27
225e | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-05-27
225f | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-05-27
225g | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. Pease see utility map located inPA onecall folder for bridge in sharepoint . | UG |  |  | 2016-05-27
225h | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby. |  |  |  | 2016-05-27
225i | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | 8-inch ductile iron main on the east side of the bridge, need to identify potential conflicts | UG | 8" Ductile iron |  | 2016-05-27
226a | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-06-06
226b | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-06-06
226c | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-06-06
226d | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-06-06
226e | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | sanitary | Bendersville Borough | Andrea Rivera, secretary@bendersvilleborough.net, 717-677-8112. Ken McKee, 717-677-7857 | DID NOT RESPOND | UG |  |  | 2017-06-06
227 | -- | 227 | 148 | 87434 | 1023403100000 | 8 | Adams | 2 MI.N.E. OF BIGLERVILLE | PA 234; SR 0234 | OPOSSUM CREEK | 01/202 - BUTLER | 39.9411 | -77.2045 |  | all facilities responded clear per one call | [5 empty] | 2016-09-02
228a | -- | 228 | 160 | 18146 | 1039400600526 | 8 | Adams | VILLAGE OF TABLE ROCK | PA 394; SR 0394 | CONEWAGO CREEK | 01/202 - BUTLER | 39.9154 | -77.2217 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked | UG |  |  | 2017-06-05
228b | -- | 228 | 160 | 18146 | 1039400600526 | 8 | Adams | VILLAGE OF TABLE ROCK | PA 394; SR 0394 | CONEWAGO CREEK | 01/202 - BUTLER | 39.9154 | -77.2217 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby | UG |  |  | 2017-06-05
228c | -- | 228 | 160 | 18146 | 1039400600526 | 8 | Adams | VILLAGE OF TABLE ROCK | PA 394; SR 0394 | CONEWAGO CREEK | 01/202 - BUTLER | 39.9154 | -77.2217 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2017-06-05
229a | -- | 229 | 185 | 87676 | 1101400501701 | 8 | Adams | VILLAGE OF LIMEROCK MILL | SR 1014 | BERMUDIAN CREEK | 01/211 - HUNTINGTON | 39.9825 | -77.1646 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby |  |  |  | 2016-08-01
229b | -- | 229 | 185 | 87676 | 1101400501701 | 8 | Adams | VILLAGE OF LIMEROCK MILL | SR 1014 | BERMUDIAN CREEK | 01/211 - HUNTINGTON | 39.9825 | -77.1646 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2016-08-01
229c | -- | 229 | 185 | 87676 | 1101400501701 | 8 | Adams | VILLAGE OF LIMEROCK MILL | SR 1014 | BERMUDIAN CREEK | 01/211 - HUNTINGTON | 39.9825 | -77.1646 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-01
230 | -- | 230 | 198 | 87671 | 1101601101587 | 8 | Adams | GARDNERS | SR 1016 | UPPER BERMUDIAN CREEK | 01/211 - HUNTINGTON | 40.0031 | -77.1924 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-03-06
231a | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | CenturyLink QS has no facilities in your planned excavation area. |  |  |  | 2017-03-20
231b | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-03-20
231c | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | Gas | Columbia Gas of PA Design | Logan Harper 717-849-0137 "LHarper@nisource.com" Upper case “L”! | Conflict. Lines Nearby. Please see utility map located in onecall folder for bridge in sharepoint . | UG |  |  | 2017-03-20
231d | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Met-Ed is the owner of the poles on the north and south side of the bridge and Comcast is the only foreign attachment at this crossing, 4181 form not affacted has been provided | OH |  |  | 2017-03-20
231e | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | GAS | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | DID NOT RESPOND | UG |  |  | 2017-03-20
232a | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby. |  |  |  | 2016-09-02
232b | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-09-02
232c | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 |  | Highland TWP | 717-642-8410, highlandtownship@comcast.net, hours M-Th 8:30-2:30pm | Did Not Respond |  |  |  | 2016-09-02
232d | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-09-02
233a | -- | 233 | 362 | 87437 | 1400500101339 | 8 | Adams | 1/4 MI.N. OF BENDERSVILLE | SR 4005 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9899 | -77.2529 |  | Bendersville Borough | Andrea Rivera, secretary@bendersvilleborough.net, 717-677-8112. Ken McKee, 717-677-7857 | Did Not Respond |  |  |  | 2017-06-01
233b | -- | 233 | 362 | 87437 | 1400500101339 | 8 | Adams | 1/4 MI.N. OF BENDERSVILLE | SR 4005 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9899 | -77.2529 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2017-06-01
233d | -- | 233 | 362 | 87437 | 1400500101339 | 8 | Adams | 1/4 MI.N. OF BENDERSVILLE | SR 4005 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9899 | -77.2529 |  | Menallen TWP | 717-677-6635, menallentwp@centurylink.net | Did Not Respond |  |  |  | 2017-06-01
234a | -- | 234 | 364 | 87438 | 1400601202897 | 8 | Adams | ASPERS | SR 4006 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.977 | -77.2255 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. Please see utility map located in onecall folder for bridge in sharepoint . | UG |  |  | 2017-05-26
234b | -- | 234 | 364 | 87438 | 1400601202897 | 8 | Adams | ASPERS | SR 4006 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.977 | -77.2255 | S & W | POSSUM VALLEY MUNICIPAL AUTHORITY (PSM) | Jeff Taylor 717-752-6411 possumvalley@embarqmail.com | Responded by utility map of sewer lines and manholes location | UG |  |  | 2017-05-26
234c | -- | 234 | 364 | 87438 | 1400601202897 | 8 | Adams | ASPERS | SR 4006 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.977 | -77.2255 | Elect. | METROPOLITAN EDISON CO/FIRSTENERGY (MJ | Dan Henry 724-838-6126 724-830-7677dhenry2@firstenergycorp.com Steve Ward, 717 848-7147 717-848-7360 sward@gpu.com | Conflict. Lines Nearby. Please see utility map located in onecall folder for bridge in sharepoint . | OH |  |  | 2017-05-26
234c | -- | 234 | 364 | 87438 | 1400601202897 | 8 | Adams | ASPERS | SR 4006 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.977 | -77.2255 | Comm | COMCAST (GS) | Jeff Gilliland, 717-337-1630 717-337-0992 jeffrey_Gilliland@cable.comcast.com | Clear no facility | OH |  |  | 2017-05-26
234d | -- | 234 | 364 | 87438 | 1400601202897 | 8 | Adams | ASPERS | SR 4006 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.977 | -77.2255 | comm | CENTURYLINK FORMERLY EMBARQ (TW) | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Clear no facility but still waiting the response | oH |  |  | 2017-05-26
235a | -- | 235 | 381 | 90784 | 1401100101013 | 8 | Adams | NEAR ADAMS & FRANK.LINE | SR 4011 | CARBAUGH RUN | 01/205 - FRANKLIN | 39.9014 | -77.4676 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-05-30
235b | -- | 235 | 381 | 90784 | 1401100101013 | 8 | Adams | NEAR ADAMS & FRANK.LINE | SR 4011 | CARBAUGH RUN | 01/205 - FRANKLIN | 39.9014 | -77.4676 | Gas | Texas Eastern/Spectra | Michael Beer, 717-709-4201 | Design Conflict. Please send plans to: Ryan Lumbatis Texas Eastern/Spectra 560 Pottstown Pike Chester Springs PA 19425 | UG |  |  | 2017-05-30
236a | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 |  | Carlisle Borough/Carlisle Borough Municipal Auth | Mark Malarich, 717-249-6932, Mmalarich@carlislepa.org | Marked. | UG |  |  | 2017-03-13
236b | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | Comm | Centurylink formerly Embarq | Perry Byers (until December 2016), 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com, Matt 814-935-5365 | Conflict. Lines Nearby. |  |  |  | 2017-03-13
236c | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-03-13
236d | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 |  | Middlesex TWP Municipal Auth | Rory Morrison, 717-243-0674 | Marked. | UG |  |  | 2017-03-13
236d | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3405 | UG |  |  | 2017-03-13
236e | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | Gas | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | Design Confict. Please send plans to: Tom Witt UGI Utilities Inc 1301 AIP Dr Middletown PA 17057 | UG |  |  | 2017-03-13
237a | -- | 237 | 13616 | 87424 | 21003400700827 | 8 | Cumberland | HUNTERS RUN | PA 34; SR 0034 | HUNTERS RUN | 21/213 - SOUTH MIDDLETON | 40.0794 | -77.1932 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-05-15
237b | -- | 237 | 13616 | 87424 | 21003400700827 | 8 | Cumberland | HUNTERS RUN | PA 34; SR 0034 | HUNTERS RUN | 21/213 - SOUTH MIDDLETON | 40.0794 | -77.1932 | Comm | Comcast Cable Communications, Inc. | Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-05-15
237c | -- | 237 | 13616 | 87424 | 21003400700827 | 8 | Cumberland | HUNTERS RUN | PA 34; SR 0034 | HUNTERS RUN | 21/213 - SOUTH MIDDLETON | 40.0794 | -77.1932 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-05-15
238a | -- | 238 | 13735 | 90695 | 21023300900266 | 8 | Cumberland | PINE GROVE FURNACE | PA 233; SR 0233 | TOMS RUN | 21/201 - COOKE | 40.0338 | -77.304 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-08-21
238b | -- | 238 | 13735 | 90695 | 21023300900266 | 8 | Cumberland | PINE GROVE FURNACE | PA 233; SR 0233 | TOMS RUN | 21/201 - COOKE | 40.0338 | -77.304 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked on 6/18/15 |  |  |  | 2017-08-21
239a | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-02-10
239b | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-02-10
239c | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | sanitary | North Newton TWP | 717-532-5372 | DID NOT RESPOND | UG |  |  | 2017-02-10
239d | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3405 | UG |  |  | 2017-02-10
240a | -- | 240 | 13824 | 74054 | 21099702601555 | 8 | Cumberland | MCCREA | PA 997; SR 0997 | DOUBLING GAP CREEK | 21/205 - LOWER MIFFLIN | 40.2381 | -77.4452 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby |  |  |  | 2017-05-11
240b | -- | 240 | 13824 | 74054 | 21099702601555 | 8 | Cumberland | MCCREA | PA 997; SR 0997 | DOUBLING GAP CREEK | 21/205 - LOWER MIFFLIN | 40.2381 | -77.4452 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-05-11
240c | -- | 240 | 13824 | 74054 | 21099702601555 | 8 | Cumberland | MCCREA | PA 997; SR 0997 | DOUBLING GAP CREEK | 21/205 - LOWER MIFFLIN | 40.2381 | -77.4452 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-05-11
241 | -- | 241 | 13896 | 90739 | 21203100100000 | 8 | Cumberland | Spanglers Mill over Yellow Breeches Ck | 2031 Spanglers Mil | YELLOW BREECHES CREEK | 21/102 - LOWER ALLEN | 40.212 | -76.9065 |  | all facilities responded clear per one call | [5 empty] | 2017-05-31
242a | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2016-10-03
242b | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2016-10-03
242c | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | Comm | Sprint Nextel | 1-800-521-0579 | Field Marked. Sprint Nextel Facilities have been marked at this location and may need further monitoring. Sprint Nextel may need to be onsite while excavation takes place. Please contact Sprint Nextel's Call Before You Dig Department one business day prior to excavation to follow up at 1-800-521-0579. | UG |  |  | 2016-10-03
242d | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Gail Schmitz, Gail.Schmitz@windstream.com, 1-800-289-1901 | UG line located on SR 3019. Please see map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2016-10-03
243 | -- | 243 | 13948 | 90769 | 21400100200000 | 8 | Cumberland | 2 MI.N. OF SHIPPENSBURG | SR 4001; TWP. RD. | MIDDLE SPRING CR. | 21/215 - SOUTHAMPTON | 40.0834 | -77.5432 | wtr | Southern Cumberland Water Association | 717-530-0703 | Did Not Respond. | UG |  |  | 2017-05-30
244a | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby. |  |  |  | 2017-08-14
244b | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2017-08-14
244c | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2017-08-14
244d | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | Comm | Kuhn Communications Inc | 717-532-8857 | Did Not Respond |  |  |  | 2017-08-14
245a | -- | 245 | 14441 | 100078 | 22101800101692 | 8 | Dauphin | 3 MI. N W GRATZ | SR 1018 | DEEP CREEK | 22/210 - LYKENS | 40.628 | -76.778 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-10-03
245b | -- | 245 | 14441 | 100078 | 22101800101692 | 8 | Dauphin | 3 MI. N W GRATZ | SR 1018 | DEEP CREEK | 22/210 - LYKENS | 40.628 | -76.778 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3296 | UG |  |  | 2016-10-03
245c | -- | 245 | 14441 | 100078 | 22101800101692 | 8 | Dauphin | 3 MI. N W GRATZ | SR 1018 | DEEP CREEK | 22/210 - LYKENS | 40.628 | -76.778 | Comm | TDS Telcom | Gregory Michael, 570-758-6911, gregory.michael@tdstelecom.com | Conflict. Lines Nearby. |  |  |  | 2016-10-03
246a | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Marked. fiber optic cable would be underground on the Norfolk Southern railroad ROW. Therefore it shouldn't be in conflict for any overhead bridge replacement unless new footers are being placed as part of the bridge replacement that further encroach on the tracks more so than the existing bridge structures (or in different location). If you find that our locates are no longer visable with all the recent snow please feel free to contact either Perry Byers or Tom Chambers of CenturyLink Operations to relocate the area. | UG |  |  | 2017-04-03
246b | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-04-03
246c | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | wtr | Pennsylvania American Water CO | Linda Taflinger, 717-531-3294, linda.taflinger@amwater.com | insufficient info. Do not dig. | UG |  |  | 2017-04-03
246d | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-3231 | UG |  |  | 2017-04-03
246e | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | Gas | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | Design Confict. Please send plans to: Tom Witt UGI Utilities Inc 1301 AIP Dr Middletown PA 17057 | UG |  |  | 2017-04-03
247a | -- | 247 | 14578 | 87457 | 22400400202505 | 8 | Dauphin | 2 MI. W. ENDERS | SR 4004 | ARMSTRONG CREEK | 22/205 - JACKSON | 40.4805 | -76.8825 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-07-07
247b | -- | 247 | 14578 | 87457 | 22400400202505 | 8 | Dauphin | 2 MI. W. ENDERS | SR 4004 | ARMSTRONG CREEK | 22/205 - JACKSON | 40.4805 | -76.8825 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 484-634-4127 | UG |  |  | 2016-07-07
248a | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-08-07
248b | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | GAS | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. 3" MP lines on US HWY 30 that crosses SR 0233. 3" MP on SR 0233. Please see utility map located in onecall folder for bridge in sharepoint. | UG | 3" |  | 2017-08-07
248c | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-08-07
248d | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | Gas | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | Conflict. Lines Nearby. | UG |  |  | 2017-08-07
248e | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-08-07
249 | -- | 249 | 17408 | 63173 | 28027400200000 | 8 | Franklin | 1 ML. N. OF DOYLESBURG | PA 274; SR 0274 | BR. TUSCARORA CREEK | 28/202 - FANNETT | 40.2257 | -77.6928 | Elect | PENNSYLVANIA ELEC CO (OD) | Dan Henry 724-838-6126,724-830-7677 dhenry2@firstenergycorp.com | Clear no Facility |  |  |  | 2016-05-13
249 | -- | 249 | 17408 | 63173 | 28027400200000 | 8 | Franklin | 1 ML. N. OF DOYLESBURG | PA 274; SR 0274 | BR. TUSCARORA CREEK | 28/202 - FANNETT | 40.2257 | -77.6928 | Comm | CENTURYLINK FORMERLY EMBARQ (TW) | Greg Gamble Phone : 717-633-8275 Fax : 717- 633-8160 gregory.g.gamble@centurylink.com | Clear no facility |  |  |  | 2016-05-13
249 | -- | 249 | 17408 | 63173 | 28027400200000 | 8 | Franklin | 1 ML. N. OF DOYLESBURG | PA 274; SR 0274 | BR. TUSCARORA CREEK | 28/202 - FANNETT | 40.2257 | -77.6928 | Comm | Sprint | Mike.brown@sprint.com, 304-283-5668 (Eastern PA); wesley.a.carpenter@sprint.com 717-404-0899 (Western PA), 1-800-521-0579 | Clear no facility |  |  |  | 2016-05-13
250a | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-05-11
250b | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | Elect | Pennsylvania Electric Company | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-05-11
250c | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-05-11
250d | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby |  |  |  | 2017-05-11
250e | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | sanitary | Lurgan TWP | 717-532-7460 | DID NOT RESPOND | UG |  |  | 2017-05-11
251 | -- | 251 | 17592 | 78710 | 28400801900060 | 8 | Franklin | 2 MI. NE OF EDENVILLE | SR 4008 | DENNIS RUN | 28/205 - HAMILTON | 39.9768 | -77.7583 |  | all facilities responded clear per one call | [5 empty] | 2016-08-08
252a | -- | 252 | 17593 | 78708 | 28400802301142 | 8 | Franklin | 3 MI E OF EDENVILLE | SR 4008 | ROCKY SPRING CREEK | 28/205 - HAMILTON | 39.9649 | -77.7302 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2016-06-20
252b | -- | 252 | 17593 | 78708 | 28400802301142 | 8 | Franklin | 3 MI E OF EDENVILLE | SR 4008 | ROCKY SPRING CREEK | 28/205 - HAMILTON | 39.9649 | -77.7302 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2016-06-20
252c | -- | 252 | 17593 | 78708 | 28400802301142 | 8 | Franklin | 3 MI E OF EDENVILLE | SR 4008 | ROCKY SPRING CREEK | 28/205 - HAMILTON | 39.9649 | -77.7302 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-06-20
253a | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. | OH |  |  | 2016-09-02
253b | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | PPL has responded by providing the TSL map location | OH |  |  | 2016-09-02
253c | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | wtr | Columbia Water Company | Dave Lewis, dlewis@pa.net, 717-684-2188 ;Charles Gohn (retired),columbiawater@pa.net | Marked. Send drawings to Dave Lewis. | UG |  |  | 2016-09-02
253d | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | Gas | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | The Columbia Water Company has buried water mains within the proposed work area. The water main is 12-inches in diameter and is DICL class 52 pipe. The water main was installed in the year 2007. The Water Company also has real property interests in the area. | UG | 12" |  | 2016-09-02
253e | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | Gas | Centurylink formerly Embarq | Leon Nailor, 717-248-4561 Leon.Nailor@CenturyLink.com | The utility poles are owned by PPL and both Comcast and Centurylink are attach to them. Telephone cables will be affected | OH
253f | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | Comm | VERIZON PENNSYLVANIA LLC (FG) | Norman Parrish, 610-280-2152 norman.l.parrish@verizon.com | Clear no Facility | OH
253g | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | Gas | UGI UTILITIES INC (UH) | David J. Dean, 717-255-4346 ddean@ugi.com | Clear no facility | OH
254a | -- | 254 | 21043 | 87315 | 36003004802322 | 8 | Lancaster | LEAMAN PLACE | US 30; SR 0030 | ESHELMAN'S RUN | 36/226 - PARADISE | 40.006 | -76.1108 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-03-21
254b | -- | 254 | 21043 | 87315 | 36003004802322 | 8 | Lancaster | LEAMAN PLACE | US 30; SR 0030 | ESHELMAN'S RUN | 36/226 - PARADISE | 40.006 | -76.1108 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5308 | UG |  |  | 2017-03-21
255a | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-05-23
255b | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | PPL rsponded by TSL map location | OH |  |  | 2016-05-23
255c | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com | Windstream Communication owned poles, no other company attached to these poles | OH |  |  | 2016-05-23
255d | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | Elect | Blue Ridge Communications (Cable) | Don Vinson, 717-733-4111,dvinson@brctv.com Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | DID NOT RESPOND through PA one call |  |  |  | 2016-05-23
255e | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | Gas | UGI UTILITIES INC (UK) | David J. Dean, 717-255-4346 ddean@ugi.com | No Facilities in Area | UG |  |  | 2016-05-23
256a | -- | 256 | 21237 | 87536 | 36034003700000 | 8 | Lancaster | 1 MI. W. OF CAIN | PA 340; SR 0340 | PEQUEA CREEK | 36/232 - SALISBURY | 40.0289 | -75.967 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-05-30
256b | -- | 256 | 21237 | 87536 | 36034003700000 | 8 | Lancaster | 1 MI. W. OF CAIN | PA 340; SR 0340 | PEQUEA CREEK | 36/232 - SALISBURY | 40.0289 | -75.967 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5394 | UG |  |  | 2017-05-30
256c | -- | 256 | 21237 | 87536 | 36034003700000 | 8 | Lancaster | 1 MI. W. OF CAIN | PA 340; SR 0340 | PEQUEA CREEK | 36/232 - SALISBURY | 40.0289 | -75.967 |  | Salisbury TWP | 717-768-8059 | DID NOT RESPOND | UG |  |  | 2017-05-30
257a | -- | 257 | 21238 | 87554 | 36034003801674 | 8 | Lancaster | CAINS | PA 340; SR 0340 | MILLER'S RUN | 36/232 - SALISBURY | 40.0249 | -75.9487 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-10-07
257b | -- | 257 | 21238 | 87554 | 36034003801674 | 8 | Lancaster | CAINS | PA 340; SR 0340 | MILLER'S RUN | 36/232 - SALISBURY | 40.0249 | -75.9487 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5394 | UG |  |  | 2016-10-07
258a | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 |  | Christiana Boro/Christiana B W&S Auth | Laverne Rettew (secy), 610-593-5199, christianaboro@comcast.net | Field Marked. | UG |  |  | 2016-08-18
258b | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 | Comm | Comcast Cable Communications, Inc. | Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-18
258c | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 | Elect | PECO Energy | Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com | Conflict. Lines Nearby. |  |  |  | 2016-08-18
258d | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG facilities located in the area of the one call. Please call 484-634-3658 for a map. | UG |  |  | 2016-08-18
259a | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-03-08
259b | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | sanitary | City of Lancaster/Lanc SA/Lanc Auth | Michael Kyle, 717-299-4843 | Marked. | UG |  |  | 2017-03-08
259c | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | wtr | Lancaster TWP | Robert J. Ruth, PE, 717-291-4729, rruth@cityoflancasterpa.com | Marked. 2 water mains on bridge. | UG |  |  | 2017-03-08
259d | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5308 | UG |  |  | 2017-03-08
259e | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | wtr | East Hempfield TWP | Rod Ray, 717-898-8231 | Marked. | UG |  |  | 2017-03-08
259f | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 |  | Manor TWP | 717-397-4769 | Marked. | UG |  |  | 2017-03-08
260 | -- | 260 | 21292 | 91194 | 36062501302573 | 8 | Lancaster | 1 MI. S. OF BOWMANSVILLE | PA 625; SR 0625 | MUDDY CREEK | 36/202 - BRECKNOCK | 40.1893 | -76.0169 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5394 | UG |  |  | 2017-05-31
261a | -- | 261 | 21326 | 78868 | 36077204500174 | 8 | Lancaster | 1.5 MI. S.E. OF LITITZ | PA 772; SR 0772 | LITITZ RUN | 36/235 - WARWICK | 40.1476 | -76.2715 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - could not be retreived through onecall | UG |  |  | 2017-05-22
261b | -- | 261 | 21326 | 78868 | 36077204500174 | 8 | Lancaster | 1.5 MI. S.E. OF LITITZ | PA 772; SR 0772 | LITITZ RUN | 36/235 - WARWICK | 40.1476 | -76.2715 |  | Warwick TWP Municipal Auth | Carl Haws / Claudia Watt, 717-627-2379, chaws@warwicktownship.org | Marked. | UG |  |  | 2017-05-22
261c | -- | 261 | 21326 | 78868 | 36077204500174 | 8 | Lancaster | 1.5 MI. S.E. OF LITITZ | PA 772; SR 0772 | LITITZ RUN | 36/235 - WARWICK | 40.1476 | -76.2715 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David F. Ackerman. David.F.Ackerman@windstream.com, 319-790-1464 | OH lines on rothsville rd and. Send drawings to Glen Esenwein by e-mail or 202 East First Street Birdsboro, PA 19508 | OH |  |  | 2017-05-22
262a | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-04-03
262b | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 |  | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - could not be retreived through onecall | UG |  |  | 2017-04-03
262c | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 | Comm | Service Electric Cablevision, Inc. | Darryl Reccek, 610-868-0902, rec@sectv.com | Conflict. Lines Nearby. |  |  |  | 2017-04-03
262d | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David F. Ackerman. David.F.Ackerman@windstream.com, 319-790-1464 | OH and UG lines near project area. Please see utility map located in the one call folder for the bridge in sharpoint. | UG & OH |  |  | 2017-04-03
263a | -- | 263 | 21409 | 87521 | 36102100420000 | 8 | Lancaster | S. OF UNION GROVE | SR 1021; TWP. RD. | Conestoga River | 36/213 - EAST EARL | 40.1437 | -76.0207 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Did not respond to one call |  |  |  | 2017-05-30
263b | -- | 263 | 21409 | 87521 | 36102100420000 | 8 | Lancaster | S. OF UNION GROVE | SR 1021; TWP. RD. | Conestoga River | 36/213 - EAST EARL | 40.1437 | -76.0207 | Comm | Frontier Communications | James Zionkowski, 610-926-4747, james.zionkowski@frontiercorp.com | Did not respond to one call |  |  |  | 2017-05-30
263c | -- | 263 | 21409 | 87521 | 36102100420000 | 8 | Lancaster | S. OF UNION GROVE | SR 1021; TWP. RD. | Conestoga River | 36/213 - EAST EARL | 40.1437 | -76.0207 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5394 | UG |  |  | 2017-05-30
264 | -- | 264 | 21415 | 74958 | 36102402100000 | 8 | Lancaster | WEST OF SPRINGVILLE | SR 1024 | INDIAN RUN | 36/218 - EPHRATA | 40.2039 | -76.1822 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5394 | UG |  |  | 2016-09-02
265a | -- | 265 | 21417 | 19927 | 36102500801639 | 8 | Lancaster | 0.75 mi NW of Farmersville | N Farmersville Rd | Conestoga River | 36/238 - WEST EARL | 40.1348 | -76.1741 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-10-03
265b | -- | 265 | 21417 | 19927 | 36102500801639 | 8 | Lancaster | 0.75 mi NW of Farmersville | N Farmersville Rd | Conestoga River | 36/238 - WEST EARL | 40.1348 | -76.1741 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5394 | UG |  |  | 2016-10-03
265c | -- | 265 | 21417 | 19927 | 36102500801639 | 8 | Lancaster | 0.75 mi NW of Farmersville | N Farmersville Rd | Conestoga River | 36/238 - WEST EARL | 40.1348 | -76.1741 | sanitary | West Earl TWP | James Houser, 717-859-3201 | marked. | UG |  |  | 2016-10-03
266a | -- | 266 | 21439 | 100523 | 36103400200000 | 8 | Lancaster | 1MI NE DENVER | S.R. 1034 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.2441 | -76.1136 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities exist in the area of the one call. Please call 484-634-4217 for a map. | UG |  |  | 2017-07-10
266b | -- | 266 | 21439 | 100523 | 36103400200000 | 8 | Lancaster | 1MI NE DENVER | S.R. 1034 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.2441 | -76.1136 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | Aerial lines on Smokestown Road. Please see maps located in the one call folder for the bridge in sharepoint. | OH |  |  | 2017-07-10
267a | -- | 267 | 21446 | 63230 | 36103501500846 | 8 | Lancaster | 0.75 MILE N. OF NEWTOWN | SR 1035 | MIDDLE CREEK | 36/204 - CLAY | 40.2452 | -76.2489 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2016-08-31
267b | -- | 267 | 21446 | 63230 | 36103501500846 | 8 | Lancaster | 0.75 MILE N. OF NEWTOWN | SR 1035 | MIDDLE CREEK | 36/204 - CLAY | 40.2452 | -76.2489 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities exist in the area of the one call. Please call 484-634-4217 for a map. | UG |  |  | 2016-08-31
268a | -- | 268 | 21454 | 20124 | 36103702100000 | 8 | Lancaster | Speedwell Forge Rd/Hammer Creek | SR 1037 | HAMMER CREEK | 36/217 - ELIZABETH | 40.2276 | -76.335 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Joseph Green, Joseph.Green@windstream.com, 319-790-7510 | OH lines near project area but appear to not be in conflict. Please see the utility map located in the onecall folder for the bridge in sharepoint. | OH |  |  | 2016-08-18
269a | -- | 269 | 21459 | 87706 | 36103900500000 | 8 | Lancaster | 1.5 MI.N. OF MILLWAY | SR 1039 | MIDDLE CREEK | 36/218 - EPHRATA | 40.1772 | -76.2417 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities exist in the area of the one call. Please call 484-634-4217 for a map. | UG |  |  | 2016-10-07
269b | -- | 269 | 21459 | 87706 | 36103900500000 | 8 | Lancaster | 1.5 MI.N. OF MILLWAY | SR 1039 | MIDDLE CREEK | 36/218 - EPHRATA | 40.1772 | -76.2417 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com; gesenwein@decommunications.com; | Did Not Respond |  |  |  | 2016-10-07
270 | -- | 270 | 21474 | 91323 | 36104800500000 | 8 | Lancaster | 1.25 MI.E. OF TERRE HILL | SR 1048 | BLACK CREEK | 36/213 - EAST EARL | 40.1656 | -76.0222 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2017-08-01
271a | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
271b | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - UG facilities located in project area. Please call 570-368-5394 | UG |  |  | 2016-08-03
271c | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | GAS | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | Design Conflict. Please send plans to: Kurt Zielaskowski UGI Utilities Inc. 225 Morgantown Road Reading PA 19611 | UG |  |  | 2016-08-03
271d | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
271e | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com; gesenwein@decommunications.com; | UG copper on Greenville Rd that crosses turnpike. Also UG copper on Poplar St that ends east of cocalico creek. Please see plans located in the onecall folder for the bridge on sharepoint. | UG |  |  | 2016-08-03
272a | -- | 272 | 21487 | 87566 | 36105500202673 | 8 | Lancaster | Reinholds Rd over Swamp Ck (N of i76) | SR 1055 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.243 | -76.123 | wtr and sanitary | Ephrata Borough/Ephrata Joint Auth | David Burkholder, dburkholder@ephrataboro.org, 717-738-9202 (x135) ; Ryan Coulson, 717-738-9222 | The Borough of Ephrata and the Ephrata Borough Authority (SEWER) and the Ephrata Area Joint Authority (WATER) do not have any facilities in this area. |  |  |  | 2016-05-09
272b | -- | 272 | 21487 | 87566 | 36105500202673 | 8 | Lancaster | Reinholds Rd over Swamp Ck (N of i76) | SR 1055 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.243 | -76.123 | Comm | Blue Ridge Communications (Cable); | Don Vinson, Phone 717-733-4111 in Ephrata office. dvinson@brctv.com Richard (Rick) Hebda, rhebda@brctv.com, 610-826-967 | Blue ridge rent space on the poles from PPL and windstream |  |  |  | 2016-05-09
272c | -- | 272 | 21487 | 87566 | 36105500202673 | 8 | Lancaster | Reinholds Rd over Swamp Ck (N of i76) | SR 1055 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.243 | -76.123 | Comm | Windstream (Formerly Denver & Ephrata | SHANE D. MENTZER , Outside Plant Engineer office: (717) 738-8390 Shane.Mentzer@windstream.com | Was not on PA one call, Windstream Communication owned poles are annotated, no other company attached to these poles |  |  |  | 2016-05-09
272d | -- | 272 | 21487 | 87566 | 36105500202673 | 8 | Lancaster | Reinholds Rd over Swamp Ck (N of i76) | SR 1055 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.243 | -76.123 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Left voice message but it has expired. |  |  |  | 2016-05-09
273a | -- | 273 | 21514 | 91324 | 36200200602329 | 8 | Lancaster | KIRKS MILL | Twp Road | REYNOLDS RUN | 36/222 - LITTLE BRITAIN | 39.7552 | -76.1071 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2017-06-12
273b | -- | 273 | 21514 | 91324 | 36200200602329 | 8 | Lancaster | KIRKS MILL | Twp Road | REYNOLDS RUN | 36/222 - LITTLE BRITAIN | 39.7552 | -76.1071 | Comm | Neon Transcom | Brian Loucks, 508-439-2406 | Marked. |  |  |  | 2017-06-12
273c | -- | 273 | 21514 | 91324 | 36200200602329 | 8 | Lancaster | KIRKS MILL | Twp Road | REYNOLDS RUN | 36/222 - LITTLE BRITAIN | 39.7552 | -76.1071 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities exist within the area of the one call. Please call 570-368-5394 for maps. | UG |  |  | 2017-06-12
274a | -- | 274 | 21518 | 87516 | 36200500300000 | 8 | Lancaster | 1MI NOF NEW TEXAS | SR 2005; TWP ROAD | LITTLE CONOWINGO CRK | 36/219 - FULTON | 39.7625 | -76.1542 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
274b | -- | 274 | 21518 | 87516 | 36200500300000 | 8 | Lancaster | 1MI NOF NEW TEXAS | SR 2005; TWP ROAD | LITTLE CONOWINGO CRK | 36/219 - FULTON | 39.7625 | -76.1542 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities exist within the area of the one call. Please call 570-368-5308 for maps. | UG |  |  | 2016-08-03
275a | -- | 275 | 21533 | 20123 | 36201000560000 | 8 | Lancaster | PUSEYVILLE | SR 2010 | W BR OCTORARO | 36/205 - COLERAIN | 39.8481 | -76.1136 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities exist within the area of the one call. Please call 570-368-5394 for maps. | UG |  |  | 2017-07-31
276 | -- | 276 | 21536 | 87562 | 36201200320000 | 8 | Lancaster | 1 MI.N. OF UNION | SR 2012; TWP RD | TRIB W.BR.OCTORARO | 36/205 - COLERAIN | 39.8517 | -76.0433 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities exist in the area of the one call. Please call 484-634-4217 for a map. | UG |  |  | 2016-08-22
277 | -- | 277 | 21545 | 91108 | 36201500400000 | 8 | Lancaster | 2 MI E OF COLLINS | SR 2015 | WEST BRANCH OCTORARO CR | 36/205 - COLERAIN | 39.8806 | -76.1047 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG facilities located in the area of the one call. Please call 484-634-3658 for a map. | UG |  |  | 2016-07-11
278a | -- | 278 | 21558 | 19964 | 36202000100000 | 8 | Lancaster | CAMARGO | SR 2020 | BEAVER CREEK | 36/216 - EDEN | 39.9171 | -76.1749 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-05-23
278b | -- | 278 | 21558 | 19964 | 36202000100000 | 8 | Lancaster | CAMARGO | SR 2020 | BEAVER CREEK | 36/216 - EDEN | 39.9171 | -76.1749 | Comm | Commonwealth Telephone Co. dba Frontier Comm | Joe Witt Network Engineer joseph.witt@ftr.com 717-786-2525 office , 717-575-1952 cell | Frontier does have aerial cables on the West side of Stoneyhill Rd. We also own pole EB-2 that needs relocated at the Southwest corner of the bridge. | OH |  |  | 2016-05-23
278c | -- | 278 | 21558 | 19964 | 36202000100000 | 8 | Lancaster | CAMARGO | SR 2020 | BEAVER CREEK | 36/216 - EDEN | 39.9171 | -76.1749 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 570-368-5394 | OH |  |  | 2016-05-23
279a | -- | 279 | 21559 | 87518 | 36202000200000 | 8 | Lancaster | 1 MI.N. CAMARGO | SR 2020 | BOWEY RUN | 36/216 - EDEN | 39.9172 | -76.1748 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
279b | -- | 279 | 21559 | 87518 | 36202000200000 | 8 | Lancaster | 1 MI.N. CAMARGO | SR 2020 | BOWEY RUN | 36/216 - EDEN | 39.9172 | -76.1748 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 570-368-5308 | UG |  |  | 2016-08-03
280 | -- | 280 | 21595 | 87501 | 36204500700000 | 8 | Lancaster | North of Bird In Hand | 2045 Monterrey Rd | Mill Creek | 36/234 - UPPER LEACOCK | 40.0549 | -76.1706 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-10-03
281a | -- | 281 | 21601 | 19812 | 36300400200000 | 8 | Lancaster | DRUMORE | SR 3004; (TWP RD) | FISHING CREEK | 36/208 - DRUMORE | 39.7943 | -76.2593 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-06-26
281b | -- | 281 | 21601 | 19812 | 36300400200000 | 8 | Lancaster | DRUMORE | SR 3004; (TWP RD) | FISHING CREEK | 36/208 - DRUMORE | 39.7943 | -76.2593 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 570-368-5394 | UG |  |  | 2017-06-26
281c | -- | 281 | 21601 | 19812 | 36300400200000 | 8 | Lancaster | DRUMORE | SR 3004; (TWP RD) | FISHING CREEK | 36/208 - DRUMORE | 39.7943 | -76.2593 | GAS | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | DID NOT RESPOND | UG |  |  | 2017-06-26
282a | -- | 282 | 21637 | 63229 | 36301702401388 | 8 | Lancaster | 0.5 MI.NORTH OF LETORT | SR 3017 | W.BR.CONESTOGA CREEK | 36/233 - STRASBURG | 39.9843 | -76.4059 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
282b | -- | 282 | 21637 | 63229 | 36301702401388 | 8 | Lancaster | 0.5 MI.NORTH OF LETORT | SR 3017 | W.BR.CONESTOGA CREEK | 36/233 - STRASBURG | 39.9843 | -76.4059 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 570-368-5394 | UG |  |  | 2016-08-03
282c | -- | 282 | 21637 | 63229 | 36301702401388 | 8 | Lancaster | 0.5 MI.NORTH OF LETORT | SR 3017 | W.BR.CONESTOGA CREEK | 36/233 - STRASBURG | 39.9843 | -76.4059 | sanitary | Lancaster Area Sewer Auth | John Vilga, 717-344-5819, Jvilga@lasa.org | sanitary lines should not be in conflict. Please see utility map located in the onecall folder for the bridge on sharepoint | UG |  |  | 2016-08-03
283a | -- | 283 | 21662 | 20151 | 36303201100000 | 8 | Lancaster | Letort Road over Little Conestoga Creek | 3032 LeTort Rd | LITTLE CONESTOGA CREEK | 36/223 - MANOR | 39.9922 | -76.3802 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-06-08
283b | -- | 283 | 21662 | 20151 | 36303201100000 | 8 | Lancaster | Letort Road over Little Conestoga Creek | 3032 LeTort Rd | LITTLE CONESTOGA CREEK | 36/223 - MANOR | 39.9922 | -76.3802 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 570-368-5394 | UG |  |  | 2017-06-08
284 | -- | 284 | 22812 | 91352 | 38402000800000 | 8 | Lebanon | INDIANTOWN GAP | SR 4020 | AIRE RUN | 38/215 - UNION | 40.4373 | -76.542 |  | all facilities responded clear per one call | [5 empty] | 2017-04-03
285a | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | Comm | AT&T Atlanta | 404-249-9052 | DID NOT RESPOND |  |  |  | 2017-04-14
285b | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-04-14
285c | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 |  | Marysville Borough | 717-957-3110, boro17053@comcast.net | Conflict. Lines Nearby. |  |  |  | 2017-04-14
285d | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 484-634-4127 | UG |  |  | 2017-04-14
285e | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com; gesenwein@decommunications.com; | DID NOT RESPOND |  |  |  | 2017-04-14
286 | -- | 286 | 29451 | 93582 | 50001701101051 | 8 | Perry | 2 MILES WEST OF KISTLER | PA 17; SR 0017 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.3821 | -77.4535 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2017-05-26
287a | -- | 287 | 29468 | 79054 | 50001707600000 | 8 | Perry | LIVERPOOL BORO | PA 17; SR 0017 | TRIB TO SUSQUEHANNA | 50/405 - LIVERPOOL | 40.5752 | -76.9961 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2017-05-26
287b | -- | 287 | 29468 | 79054 | 50001707600000 | 8 | Perry | LIVERPOOL BORO | PA 17; SR 0017 | TRIB TO SUSQUEHANNA | 50/405 - LIVERPOOL | 40.5752 | -76.9961 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG facilities located in the area of the one call. Please call 484-634-3231 for a map. | UG |  |  | 2017-05-26
287c | -- | 287 | 29468 | 79054 | 50001707600000 | 8 | Perry | LIVERPOOL BORO | PA 17; SR 0017 | TRIB TO SUSQUEHANNA | 50/405 - LIVERPOOL | 40.5752 | -76.9961 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net | Did Not Respond. |  |  |  | 2017-05-26
288a | -- | 288 | 29518 | 73961 | 50007401900530 | 8 | Perry | GREEN PARK | PA 74; SR 0074 | MONTOUR CREEK | 50/219 - TYRONE | 40.3831 | -77.3077 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-05-25
288b | -- | 288 | 29518 | 73961 | 50007401900530 | 8 | Perry | GREEN PARK | PA 74; SR 0074 | MONTOUR CREEK | 50/219 - TYRONE | 40.3831 | -77.3077 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 484-634-3231 | UG |  |  | 2017-05-25
289a | -- | 289 | 29565 | 87465 | 50085002201839 | 8 | Perry | 1MI NO OF FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.371 | -77.4011 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2017-05-30
289b | -- | 289 | 29565 | 87465 | 50085002201839 | 8 | Perry | 1MI NO OF FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.371 | -77.4011 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG facilities located in the area of the one call. Please call 484-634-3231 for a map. | UG |  |  | 2017-05-30
290a | -- | 290 | 29566 | 90716 | 50085002501777 | 8 | Perry | FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.3591 | -77.381 | Comm | Centurylink formerly Embarq | Robert W. Fogelsonger Robert.W.Fogelsonger2@centurylink.com 3989 William Penn Highway Mifflintown, Pa. 17059 (717)436-5210 | identifying cables in that area. All are copper cables except where noted as fiber. See Response | OH |  |  | 2016-05-31
290b | -- | 290 | 29566 | 90716 | 50085002501777 | 8 | Perry | FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.3591 | -77.381 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 484-634-3231 | OH |  |  | 2016-05-31
291a | -- | 291 | 29605 | 87491 | 50101502002360 | 8 | Perry | 2 MI.S. OF MILLERSTOWN | W.JUNIATA PARKWAY | WILD CAT RUN | 50/204 - GREENWOOD | 40.5142 | -77.1297 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
291b | -- | 291 | 29605 | 87491 | 50101502002360 | 8 | Perry | 2 MI.S. OF MILLERSTOWN | W.JUNIATA PARKWAY | WILD CAT RUN | 50/204 - GREENWOOD | 40.5142 | -77.1297 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 484-634-3231 | UG |  |  | 2016-08-03
292 | -- | 292 | 29651 | 101098 | 50300600100014 | 8 | Perry | 4 MI SW OF BLAIN | SR 3006 | SHAEFFER'S RUN | 50/206 - JACKSON | 40.2982 | -77.5129 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2017-07-24
293a | -- | 293 | 29673 | 79042 | 50301700100000 | 8 | Perry | AT BRIDGEPORT | SR 3017; TWP RD | TRIB SHERMANS CREEK | 50/216 - SPRING | 40.3291 | -77.2846 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
293b | -- | 293 | 29673 | 79042 | 50301700100000 | 8 | Perry | AT BRIDGEPORT | SR 3017; TWP RD | TRIB SHERMANS CREEK | 50/216 - SPRING | 40.3291 | -77.2846 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 484-634-3231 | UG |  |  | 2016-08-03
293c | -- | 293 | 29673 | 79042 | 50301700100000 | 8 | Perry | AT BRIDGEPORT | SR 3017; TWP RD | TRIB SHERMANS CREEK | 50/216 - SPRING | 40.3291 | -77.2846 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
294a | -- | 294 | 29693 | 79047 | 50400701001472 | 8 | Perry | DONNALLY'S MILLS | CREEK RD. | RACCOON CREEK | 50/218 - TUSCARORA | 40.5159 | -77.2365 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Field Marked. | UG |  |  | 2016-08-11
294b | -- | 294 | 29693 | 79047 | 50400701001472 | 8 | Perry | DONNALLY'S MILLS | CREEK RD. | RACCOON CREEK | 50/218 - TUSCARORA | 40.5159 | -77.2365 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG facilities located in the area of the one call. Please call 484-634-3405 for a map. | UG |  |  | 2016-08-11
295a | -- | 295 | 37488 | 91353 | 66012401400000 | 8 | York | 1.5 W OF DELROY | PA 124; SR 0124 | KREUTZ CREEK | 66/233 - WINDSOR | 39.9677 | -76.5979 | gas | Columbia Gas of PA Design | Brian K. Shomper, 717-849-0137, bshomper@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-03-20
295b | -- | 295 | 37488 | 91353 | 66012401400000 | 8 | York | 1.5 W OF DELROY | PA 124; SR 0124 | KREUTZ CREEK | 66/233 - WINDSOR | 39.9677 | -76.5979 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-03-20
295c | -- | 295 | 37488 | 91353 | 66012401400000 | 8 | York | 1.5 W OF DELROY | PA 124; SR 0124 | KREUTZ CREEK | 66/233 - WINDSOR | 39.9677 | -76.5979 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-03-20
296a | -- | 296 | 37491 | 87693 | 66012402502532 | 8 | York | 1 MILE N OF CRALEY | PA 124; SR 0124 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9621 | -76.5144 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | Conflict. Lines Nearby ( PA one call) Comcast has no facilities near or attached to bridge (response) |  |  |  | 2016-04-12
296b | -- | 296 | 37491 | 87693 | 66012402502532 | 8 | York | 1 MILE N OF CRALEY | PA 124; SR 0124 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9621 | -76.5144 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Met-Ed does not have any facilities in the area of this project. Please contact PPL. |  |  |  | 2016-04-12
296c | -- | 296 | 37491 | 87693 | 66012402502532 | 8 | York | 1 MILE N OF CRALEY | PA 124; SR 0124 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9621 | -76.5144 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | voice message - could not be retreived through onecall | UG |  |  | 2016-04-12
297a | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | Conflict. Lines Nearby. |  |  |  | 2016-09-27
297b | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 |  | Lower Windsor TWP | 717-244-6813, GeneraLInfo@LowerWindsor.com | Did Not Respond |  |  |  | 2016-09-27
297c | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-09-27
297d | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice Message. UG Facilities in area of one call. Please call 484-634-3658 for maps | UG |  |  | 2016-09-27
297e | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby. |  |  |  | 2016-09-27
297f | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 | Conflict. Lines Nearby. |  |  |  | 2016-09-27
297g | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | Elect | PECO Energy | Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com | Conflict. Lines Nearby. |  |  |  | 2016-09-27
298a | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | Comm | ARMSTRONG | Aaron Dierdorff, 800-762-0592, aarondierdorff@usicinc.com; Mike Greer, 800-572-1038 | Conflict. Lines Nearby. |  |  |  | 2017-05-25
298b | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-05-25
298c | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 |  | Glen Rock Water and Sewer Auth | DALE GETZ, 717-235-2082; Garth Green, 717-235-2082, grwsa@nfdc.net | DID NOT RESPOND | UG |  |  | 2017-05-25
298d | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-05-25
298e | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby. |  |  |  | 2017-05-25
299a | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 | Comm | ARMSTRONG | Aaron Dierdorff, 800-762-0592, aarondierdorff@usicinc.com; Mike Greer, 800-572-1038 | Conflict. Lines Nearby. |  |  |  | 2017-07-24
299b | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-07-24
299c | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 |  | Glen Rock Water and Sewer Auth | Garth Green, 717-235-2082, grwsa@nfdc.net | DID NOT RESPOND | UG |  |  | 2017-07-24
299d | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-07-24
300a | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | gas | Columbia Gas of PA Design | Logan Harper 1600 Colony Rd. York, PA 17408 Phone: (717) 849-0137 LHarper@nisource.com | CONFLICT. LINES NEARBY. Please see field maps located in the one call folder in sharepoint for this bridge. 2" line on SR 0921 connected to a 2" line on Hickory Ridge Cir | UG |  |  | 2016-06-02
300b | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | sanitary | Conewago TWP Sewer Auth | Caroline Kern, Admin Asst. 717-266-5518, Fax: 717-266-0474; 600 Locust Point Rd , York PA 17406 | Marked | UG |  |  | 2016-06-02
300c | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | comm | Comcast cable Inc | John O'Keefe, Jr. P: 717-324-6044 F: 717-843-5400 John_OkeefeJr@cable.comcast.com Boll, Baron <Baron_Boll@cable.comcast.com> | two aerial cables. There may be an abandoned (dead) buried cable – note the yellow x’s. | OH |  |  | 2016-06-02
300d | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | two aerial cables. There may be an abandoned (dead) buried cable – note the yellow x’s. | OH |  |  | 2016-06-02
300e | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | Marked | UG |  |  | 2016-06-02
300f | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147 | . The poles at sta 757+53 rt, #29654-25673 & sta 760+05 rt, #26966-25693 are Met-Ed poles and Comcast & Verizon are attached. The pole at sta 757+25 rt, Met-Ed #226956C25642 is owned by Verizon with Met-Ed attached | OH |  |  | 2016-06-02
301a | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | Comm | ARMSTRONG | Aaron Dierdorff, 800-762-0592, aarondierdorff@usicinc.com; Mike Greer, 800-572-1038 | Conflict. Lines Nearby. |  |  |  | 2016-07-11
301b | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | wtr | Delta Borough | Sam Maiter, waterman3989@gmail.com, 717-405-0663. Patricia Koehler, deltabilling@yahoo.com, 717-456-6248. EDNA JANE CROTHERS, 717-456-6248. Cindy Dennis Singh Operations Services Inc 8 Rees Drive Willow Street PA 17584 | Design Conflict. Please send plans to: Cindy Dennis Singh Operations Services Inc 8 Rees Drive Willow Street PA 17584. 8" water main crossing at creek. Please see utility plans located in the onecall folder for the bridge in sharepoint | UG |  |  | 2016-07-11
301c | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ; Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com | Conflict. Lines Nearby. |  |  |  | 2016-07-11
301d | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby. |  |  |  | 2016-07-11
302a | -- | 302 | 37726 | 87695 | 66202900902536 | 8 | York | 5 MILE NE OF RED LION | SR 2029 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9603 | -76.5536 | comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | Conflict. Lines Nearby. |  |  |  | 2016-07-08
302b | -- | 302 | 37726 | 87695 | 66202900902536 | 8 | York | 5 MILE NE OF RED LION | SR 2029 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9603 | -76.5536 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-07-08
303a | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby. |  |  |  | 2017-08-04
303b | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | Conflict. Lines Nearby. |  |  |  | 2017-08-04
303c | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | Conflict. Lines Nearby. |  |  |  | 2017-08-04
303d | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2017-08-04
304a | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Attached onPole's no 25572679 and 25572384 but owned by Verizon , Verizon not on PA one call, need to be verified |  |  |  | 2016-05-31
304b | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | no facilities in area of bridge, see the response |  |  |  | 2016-05-31
304c | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | no facilities in area of bridge, see the response |  |  |  | 2016-05-31
304d | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | Elect | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby, Sharing poles with Adams Electrical coop inc |  |  |  | 2016-05-31
304e | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY (MJ) | Steve Ward, P: 717 848-7147 F: 717-848-7360 sward@gpu.com | Clear no facilities |  |  |  | 2016-05-31
305a | -- | 305 | 37921 | 87595 | 66307100100000 | 8 | York | 1 MILE S.W. OF PA 94 | SR 3071; T-513 | SOUTH BR CONEWAGO CREEK | 66/232 - WEST MANHEIM | 39.731 | -76.9479 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | Conflict. Lines Nearby. |  |  |  | 2016-10-10
305b | -- | 305 | 37921 | 87595 | 66307100100000 | 8 | York | 1 MILE S.W. OF PA 94 | SR 3071; T-513 | SOUTH BR CONEWAGO CREEK | 66/232 - WEST MANHEIM | 39.731 | -76.9479 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-10-10
305c | -- | 305 | 37921 | 87595 | 66307100100000 | 8 | York | 1 MILE S.W. OF PA 94 | SR 3071; T-513 | SOUTH BR CONEWAGO CREEK | 66/232 - WEST MANHEIM | 39.731 | -76.9479 | Wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | Conflict. Lines Nearby. | UG |  |  | 2016-10-10
306a | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby. 8" MP lines on SR 4001. Please see utility map located in onecall folder for bridge in sharepoint . | UG | 8" |  | 2016-06-30
306b | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-06-30
306c | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-06-30
306d | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby. |  |  |  | 2016-06-30
306e | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | sanitary | Dover TWP | Chuck Farley, 717-292-3634, cfarley@dovertownship.org | Marked. Sanitary lines that cross bull road to the north and to the south of the bridge. Please see utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2016-06-30
306f | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | Conflict. Lines Nearby. |  |  |  | 2016-06-30
306g | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | sanitary | Conewago TWP Sewer Auth | Caroline Kern, Admin Asst. ,ctsa600@comcast.net; 717-266-5518; 717-533-6643 | Marked. | UG |  |  | 2016-06-30
306h | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | Conflict. Lines Nearby. | UG |  |  | 2016-06-30
307a | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com | Conflict. Lines Nearby |  |  |  | 2016-08-03
307b | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
307c | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
307d | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby. |  |  |  | 2016-08-03
308a | -- | 308 | 38007 | 90222 | 66403300403136 | 8 | York | 1.0 MI.N.E. ANDERSONTOWN | SR 4033 | YELLOW BREECHES CREEK | 66/208 - FAIRVIEW | 40.162 | -76.9218 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Dave McLuckie, Dave_McLuckie@cable.comcast.co, | Design Conflict. Please send plans to: Dave McLuckie Comcast Cablevision 4601 Smith St Harrisburg, PA 17109. Aerial lines on sawmill and lisburn road. Please see the utility map located in the one call folder for the bridge on sharepoint. | OH |  |  | 2016-08-29
308b | -- | 308 | 38007 | 90222 | 66403300403136 | 8 | York | 1.0 MI.N.E. ANDERSONTOWN | SR 4033 | YELLOW BREECHES CREEK | 66/208 - FAIRVIEW | 40.162 | -76.9218 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-08-29
308c | -- | 308 | 38007 | 90222 | 66403300403136 | 8 | York | 1.0 MI.N.E. ANDERSONTOWN | SR 4033 | YELLOW BREECHES CREEK | 66/208 - FAIRVIEW | 40.162 | -76.9218 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Voice messge - UG facilities located in area. Please call 484-634-4127 | UG |  |  | 2016-08-29
309a | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2016-07-28
309b | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 | Conflict. Lines Nearby. |  |  |  | 2016-07-28
309c | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com | Conflict. Lines Nearby. |  |  |  | 2016-07-28
309d | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com | Conflict. Lines Nearby. |  |  |  | 2016-07-28
310a | -- | 310 | 3954 | 88114 | 5003001000907 | 9 | Bedford | 2.8 MI.W. OF SHELLSBURG | US 30 | BURNS CREEK | 05/210 - JUNIATA | 40.0394 | -78.6882 | Comm | Centurylink formerly Embarq | John Reynolds, 814-623-3677, john.d.reynolds@centurylink.com, 317 South Richard Street, Bedford, PA 15522 | Conflict. Lines Nearby per one call. Per initial site visit there are poles 7' to the rt (looking east). Pole markings are S/UTE 327, "property of centurylink" 71150 526TL328. Pole owners | OH |  |  | 2016-06-20
310b | -- | 310 | 3954 | 88114 | 5003001000907 | 9 | Bedford | 2.8 MI.W. OF SHELLSBURG | US 30 | BURNS CREEK | 05/210 - JUNIATA | 40.0394 | -78.6882 | Elect | Pennsylvania Electric Company | Allison Oulton, 330-761-4487, oultona@firstenergycorp.com, 76 South Main Street, Akron, OH 44308-1890; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com (Manager) | DID NOT RESPOND per one call. Per initial site visit there is high tension that crosses road approx 150' to east (ahead). Per Penelec they have no distribution in this area only transmission (115,000 Volts Nominal (120,750 Maximum Voltage)). | OH |  |  | 2016-06-20
310c | -- | 310 | 3954 | 88114 | 5003001000907 | 9 | Bedford | 2.8 MI.W. OF SHELLSBURG | US 30 | BURNS CREEK | 05/210 - JUNIATA | 40.0394 | -78.6882 | Comm | Comcast Cable Communications, Inc. | Brian Woller, Brian_Woller@cable.comcast.com, 724-221-6479, 201 N Tremont Avenue, Greensburg, PA 15601 | Per CenturyLink they think there is cable on their poles. | OH |  |  | 2016-06-20
311a | -- | 311 | 3955 | 21558 | 5003001100000 | 9 | Bedford | 2.3 MI.W.OF SHELLSBURG | US 30 | SHAWNEE CREEK | 05/218 - NAPIER | 40.0418 | -78.6799 | Comm | Centurylink formerly Embarq | John Reynolds, 814-623-3677, john.d.reynolds@centurylink.com, 317 South Richard Street, Bedford, PA 15522 | Marked per one call. Per initial site visit OH T/F with poles 16' rt (looking east) running parallel. Pole marked "property of centurylink" 449 526tl 05. Pole Owners | OH |  |  | 2016-07-08
311b | -- | 311 | 3955 | 21558 | 5003001100000 | 9 | Bedford | 2.3 MI.W.OF SHELLSBURG | US 30 | SHAWNEE CREEK | 05/218 - NAPIER | 40.0418 | -78.6799 | Comm | Comcast Cable Communications, Inc. | Brian Woller, Brian_Woller@cable.comcast.com, 724-221-6479, 201 N Tremont Avenue, Greensburg, PA 15601 | Per CenturyLink they think there is cable on their poles. | OH |  |  | 2016-07-08
312a | -- | 312 | 4010 | 21563 | 5005600901305 | 9 | Bedford | 1.68 MILE WEST FROM PA 96 | PA 56 | BAREFOOT RUN | 05/227 - WEST ST CLAIR | 40.1906 | -78.6379 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | DID NOT RESPOND through one call. Verified with them that it wasn’t there facilities. They thought it was Bedford REC - 4/30/15 KE |  |  | NA | 2016-03-25
312b | -- | 312 | 4010 | 21563 | 5005600901305 | 9 | Bedford | 1.68 MILE WEST FROM PA 96 | PA 56 | BAREFOOT RUN | 05/227 - WEST ST CLAIR | 40.1906 | -78.6379 | Elect | Bedford Rural Electric Cooperative, Inc. | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com; Brooks Shoemaker, bshoemaker@bedfordrec.com; Ed Sell, esell845252@aol.com; 8846 Lincoln Hwy, Bedford PA 15522 | responded clear through one call. Verifying if power in area is there facilities - 4/30/15 KE. They do have power there but don’t own the poles - 5/7/15 KE I spoke to them that they will need to review any relocation plans that we develop and will need to complete a D4181. - KE 5/11/15 | OH |  | NOT AFFECTED | 2016-03-25
312c | -- | 312 | 4010 | 21563 | 5005600901305 | 9 | Bedford | 1.68 MILE WEST FROM PA 96 | PA 56 | BAREFOOT RUN | 05/227 - WEST ST CLAIR | 40.1906 | -78.6379 | Comm | Centurylink formerly Embarq | June Smith, june.i.smith@centurylink.com, 814-623-3624, 317 South Richard Street, Bedford, PA 15522 | RESPONDED CLEAR to one call. Found out through research that they are the pole owners. Pole tag is S/UTE 624 | OH |  | NOT AFFECTED | 2016-03-25
313a | -- | 313 | 4044 | 21455 | 5009602600000 | 9 | Bedford | MADLEY | PA 96 | WOLF CAMP RUN | 05/215 - LONDONDERRY | 39.8966 | -78.672 | comm | Centurylink formerly Embarq | June Smith, june.i.smith@centurylink.com, 814-623-3624; John Reynolds, 814-623-3677, john.d.reynolds@centurylink.com, 317 South Richard Street, Bedford, PA 15522 | CONFLICT. LINES NEARBY per one call. Per initial site visit there are poles on both side of the bridge. OH E/T on right (looking north) and OH phone on left (looking north). OH phone crossing road perpendicular approx. 60 feet north of bridge Pole tag is S/UTE 549, PE System W11782 25A, 557 H S/UTE 550. | OH |  |  | 2016-04-07
313b | -- | 313 | 4044 | 21455 | 5009602600000 | 9 | Bedford | MADLEY | PA 96 | WOLF CAMP RUN | 05/215 - LONDONDERRY | 39.8966 | -78.672 | Elect | West Penn Power | Alexander (Alex) Gebrosky, 724-830-2945, agebrosky@firstenergycorp.com; William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233 | CONFLICT. LINES NEARBY per one call. Per initial site visit there are poles on both side of the bridge. OH E/T on right (looking north) and OH phone on left (looking north). OH phone crossing road perpendicular approx. 60 feet north of bridge Pole tag is S/UTE 549, PE System W11782 25A, 557 H S/UTE 550. | OH |  |  | 2016-04-07
313c | -- | 313 | 4044 | 21455 | 5009602600000 | 9 | Bedford | MADLEY | PA 96 | WOLF CAMP RUN | 05/215 - LONDONDERRY | 39.8966 | -78.672 | Comm | Comcast Cable Communications, Inc. | Brian Woller, Brian_Woller@cable.comcast.com, 724-221-6479, 201 N Tremont Avenue, Greensburg, PA 15601 | Per design there is OH catv as well. This is comcast and they don’t own any poles. | OH |  |  | 2016-04-07
314a | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 |  | Pavia TWP | George Porle, 814-276-9345, 1850 Birdshouse Rd. Imler, PA 16655 | DID NOT RESPOND through one call. Waiting on return call to get contact so I can email the DFV 4/29/15. Sent out plans in mail on 5/5/15 for review. Spoke on the phone on 6/22 and they do not have any facilities in the area of the bridge replacement. |  |  |  | 2016-09-20
314b | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | DID NOT RESPOND through one call. Verified with them that it wasn’t there facilities. They thought it was Bedford REC - 4/30/15 KE |  |  |  | 2016-09-20
314c | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | Comm | Sprint | Wesley Carpenter, wesley.a.carpenter@sprint.com | picture of pole from the original site visit shows a sprint id tag. Did not show up as a utility contacted on onecall. Received response back from DFV package on 4/30/15 and they are clear and have no utilities in area. |  |  |  | 2016-09-20
314d | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | Elect | Bedford Rural Electric Cooperative, Inc. | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com; Brooks Shoemaker, bshoemaker@bedfordrec.com; Ed Sell, esell845252@aol.com; 8846 Lincoln Hwy, Bedford PA 15522 | responded clear through one call. Verifying if power in area is there facilities - 4/30/15 KE. They do have power there but don’t own the poles - 5/7/15 KE I sent them an email that they will need to review any relocation plans that we develop and will need to complete a D4181. - KE 5/11/15 | OH |  |  | 2016-09-20
314e | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | Comm | Centurylink formerly Embarq | June Smith, june.i.smith@centurylink.com, 814-623-3624, 317 South Richard Street, Bedford, PA 15522 | RESPONDED CLEAR to one call. Found out through research that they are the pole owners. Pole tag 119, F10 120. Poles are 6' rt (looking north). Sent plans over on 5/15. | OH |  |  | 2016-09-20
315a | -- | 315 | 4174 | 21596 | 5101100400000 | 9 | Bedford | 2 MI.N.OF BREEZEWOOD | SR 1011 | TUB MILL RUN | 05/206 - EAST PROVIDENCE | 40.0192 | -78.2589 |  | all facilities responded clear per one call | [5 empty] | 2017-05-30
315b | -- | 315 | 4174 | 21596 | 5101100400000 | 9 | Bedford | 2 MI.N.OF BREEZEWOOD | SR 1011 | TUB MILL RUN | 05/206 - EAST PROVIDENCE | 40.0192 | -78.2589 | Elect | Bedford Rural Electric Cooperative, Inc. | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com; Brooks Shoemaker, bshoemaker@bedfordrec.com; Ed Sell, esell845252@aol.com; 8846 Lincoln Hwy, Bedford PA 15522 | per initial site visit there is power that crosses the bridge on the west side from a pole just south of bridge (5' to left looking north) to a pole 60' to the north of the bridge. Pole tag BT Co 62S, 62 OSMOSE 2009, 63 OSMOSE 2009. Has comm on it as well. | OH |  |  | 2017-05-30
316a | -- | 316 | 4177 | 21552 | 5101200400000 | 9 | Bedford | 1.73 MILE EAST FROM SR 1009 | SR 1012 | RAYSTOWN BR JUNIATA RIV. | 05/226 - WEST PROVIDENCE | 40.0528 | -78.3252 | Comm | Centurylink formerly Embarq | John Reynolds, 814-623-3677, john.d.reynolds@centurylink.com, 317 South Richard Street, Bedford, PA 15522 | CONFLICT. LINES NEARBY per one call. Per initial site visit OH phone. Poles are located adjacent 24' left (looking east). Pole tags 27 H472, sprint 28. | OH |  |  | 2016-10-07
316b | -- | 316 | 4177 | 21552 | 5101200400000 | 9 | Bedford | 1.73 MILE EAST FROM SR 1009 | SR 1012 | RAYSTOWN BR JUNIATA RIV. | 05/226 - WEST PROVIDENCE | 40.0528 | -78.3252 | Elect | Bedford Rural Electric Cooperative, Inc. | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com; Brooks Shoemaker, bshoemaker@bedfordrec.com; Ed Sell, esell845252@aol.com; 8846 Lincoln Hwy, Bedford PA 15522 | Per initial site visit OH power. Poles are located adjacent 24' left (looking east). Pole tags 27 H472, sprint 28. | OH |  |  | 2016-10-07
317a | -- | 317 | 4196 | 21600 | 5102000500880 | 9 | Bedford | 0.16 MILE EAST FROM SR 1009 | SR 1020 | PIPERS RUN | 05/209 - HOPEWELL | 40.0978 | -78.3167 | comm | Centurylink formerly Embarq | John D. Reynolds, 814-623-3677, john.d.reynolds@centurylink.com | CONFLICT. LINES NEARBY per one call. Per initial site visit Buried phone line on west side approx. 45' south of bridge (tag H75 150) | UG |  |  | 2016-09-29
317b | -- | 317 | 4196 | 21600 | 5102000500880 | 9 | Bedford | 0.16 MILE EAST FROM SR 1009 | SR 1020 | PIPERS RUN | 05/209 - HOPEWELL | 40.0978 | -78.3167 | Elect | Bedford Rural Electric Cooperative, Inc. | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com; Brooks Shoemaker, bshoemaker@bedfordrec.com; Ed Sell, esell845252@aol.com; 8846 Lincoln Hwy, Bedford PA 15522 | per initial site visit high tension line crosses road approx. 90' south of bridge. Not their facilities |  |  |  | 2016-09-29
317c | -- | 317 | 4196 | 21600 | 5102000500880 | 9 | Bedford | 0.16 MILE EAST FROM SR 1009 | SR 1020 | PIPERS RUN | 05/209 - HOPEWELL | 40.0978 | -78.3167 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | per initial site visit high tension line crosses road approx. 90' south of bridge. Not their facilities |  |  |  | 2016-09-29
317d | -- | 317 | 4196 | 21600 | 5102000500880 | 9 | Bedford | 0.16 MILE EAST FROM SR 1009 | SR 1020 | PIPERS RUN | 05/209 - HOPEWELL | 40.0978 | -78.3167 | Elect | New Enterprise Rural Electric Coop | Ron Houck (Technical Services Manager), rhouck@newenterprisesrec.com, 814 766-4610; Rodney Decker (Outside Operations Manager), rdecker@newenterprisesrec.com, 814-766-3221 | per initial site visit high tension line crosses road approx. 90' south of bridge. | Both |  |  | 2016-09-29
318a | -- | 318 | 4386 | 74424 | 5403101601407 | 9 | Bedford | VILLAGE OF QUEEN | SR 4031 | BEAVERDAM CREEK | 05/211 - KIMMEL | 40.2599 | -78.4888 |  | all facilities responded clear per one call | [5 empty] | 2017-05-30
318b | -- | 318 | 4386 | 74424 | 5403101601407 | 9 | Bedford | VILLAGE OF QUEEN | SR 4031 | BEAVERDAM CREEK | 05/211 - KIMMEL | 40.2599 | -78.4888 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | per initial site visit there is OH power. The poles are near 12' lt and far 25' lt (looking east). Pole tags are UT CO of PA 78 3-15950 and 77 3-15949. | OH |  |  | 2017-05-30
318c | -- | 318 | 4386 | 74424 | 5403101601407 | 9 | Bedford | VILLAGE OF QUEEN | SR 4031 | BEAVERDAM CREEK | 05/211 - KIMMEL | 40.2599 | -78.4888 | Comm | Centurylink formerly Embarq | John Reynolds, 814-623-3677, john.d.reynolds@centurylink.com, 317 South Richard Street, Bedford, PA 15522 | per initial site visit there is OH comm. The poles are near 12' lt and far 25' lt (looking east). Pole tags are UT CO of PA 78 3-15950 and 77 3-15949. | OH |  |  | 2017-05-30
319a | -- | 319 | 5699 | 22107 | 7101302400000 | 9 | Blair | .75 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5864 | -78.2457 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. | OH |  |  | 2017-07-11
319b | -- | 319 | 5699 | 22107 | 7101302400000 | 9 | Blair | .75 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5864 | -78.2457 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | per initial site visit, OH phone. Line is right behind parapet. Will need to relocate temp easement for equip. clearance. | OH |  |  | 2017-07-11
320a | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | DID NOT RESPOND per one call. Not their facilities. It could be REA or Valley REC. |  |  |  | 2016-06-22
320b | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. | OH |  |  | 2016-06-22
320c | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | Comm | Verizon Pennsylvania LLC | Richard (Rich) Lampenfeld, richard.m.lampenfeld@verizon.com, 814-946-5909, 1119 16th Street Altoona, PA 16601 | per initial site visit there is OH phone. The pole is 8' to the rt (looking east) behind guardrail and 35 yds east from end of bridge | OH |  |  | 2016-06-22
320d | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | Elect | REA Energy Coop | Chris Yahner, cyahner@reaenergy.com, 814-472-8570 | OH facilities. Not their facilities |  |  |  | 2016-06-22
320e | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | Comm | Zayo Group (Allegheny Communications Connect) | John Lynch, john.lynch@zayo.com, 724-972-5667; Ricci Blakeley, ricci.blakeley@zayo.com, 800 Cabin Hill Dr., Room M213, Greensburg, PA 15601 | Verizon indicated that they are on the poles (fiber). They do have fiber on the north side of bridge on verizon poles | OH |  |  | 2016-06-22
321a | -- | 321 | 5709 | 21957 | 7101303601234 | 9 | Blair | 0.23 MILE NORTH FROM PA 453 | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.616 | -78.1704 |  | all facilities responded clear per one call | [5 empty] | 2017-03-20
321b | -- | 321 | 5709 | 21957 | 7101303601234 | 9 | Blair | 0.23 MILE NORTH FROM PA 453 | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.616 | -78.1704 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | per initial site visit OH power. Pole is 8' to left (looking north) and then crosses road over bridge to pole 10' rt (looking north). Not their facility may be Penelec |  |  |  | 2017-03-20
321c | -- | 321 | 5709 | 21957 | 7101303601234 | 9 | Blair | 0.23 MILE NORTH FROM PA 453 | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.616 | -78.1704 | Comm | Verizon Pennsylvania LLC | Richard (Rich) Lampenfeld, richard.m.lampenfeld@verizon.com, 814-946-5909, 1119 16th Street Altoona, PA 16601 | per initial site visit OH phone. Pole is 8' to left (looking north) and then crosses road over bridge to pole 10' rt (looking north). There is also a phone line that runs from the original pole on the left and runs north adjacent to bridge to a pole across from the intersection with union furnace road. | OH |  |  | 2017-03-20
321d | -- | 321 | 5709 | 21957 | 7101303601234 | 9 | Blair | 0.23 MILE NORTH FROM PA 453 | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.616 | -78.1704 | Elect | Pennsylvania Electric Company | Richard (Rick) Fink, rfink@firstenergycorp.com, 814-949-4641, 405 west plank road, Altoona, PA, 16601 | Per Valley REC the OH elec is Penelec. They own two poles and have 3 phase in this area. | OH |  |  | 2017-03-20
322 | -- | 322 | 5763 | 21961 | 7300500100050 | 9 | Blair | .5 MI.W.OF SPROUL | SR 3005 | BEAVERDAM CREEK | 07/207 - GREENFIELD | 40.2673 | -78.4716 | Comm | Centurylink formerly Embarq | John Reynolds, 814-623-3677, john.d.reynolds@centurylink.com, 317 South Richard Street, Bedford, PA 15522 | CONFLICT. LINES NEARBY per one call. | OH |  |  | 2017-07-13
323a | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | CONFLICT. LINES NEARBY (Per one call). Per initial site visit there is OH phone and CATV with poles located 5' left (looking north). | OH |  |  | 2016-06-14
323b | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com (manager), 820 S. 4th Street, Clearfield, PA 16830 | Design Conflict. Please send plans to: Michael Kephart Pennsylvania Elec Co 820 S Fourth St Clearfield PA 16830. Per initial site visit there is OH power with poles located 5' left (looking north). Pole tags 5171 40T, Also high tension. Have private rights for pole #5864GP | Both |  |  | 2016-06-14
323c | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | gas | Peoples Gas Altoona Division | Justin Haupt, 814-941-4075, justin.r.haupt@peoples-gas.com | Conflict. Lines Nearby (Per one call). | UG | 4" |  | 2016-06-14
323d | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | gas | Peoples Gas Design Altoona | Justin Haupt, 814-941-4075, justin.r.haupt@peoples-gas.com | DID NOT RESPOND per one call. See 323c information. |  |  |  | 2016-06-14
323e | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | wtr | Tyrone Borough Auth Water | Ardene Latchford, 814-684-1330, alatchford@tyroneboropa.com | Marked. Per initial site visit the WM crosses creek downstream from bridge and turns left. 100' from bridge it goes under SR4013 to creekside drive. | UG |  |  | 2016-06-14
323f | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | sanitary | Tyrone Borough Auth Sewer | Tim Nulton, 814-684-2110, tnulton@tyroneboropa.com | Marked. Per initial site visit there is a MH in intersection with Decker Hollow Rd. | UG | 10 & 12" |  | 2016-06-14
323g | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | Comm | Verizon Pennsylvania LLC | Richard (Rich) Lampenfeld, richard.m.lampenfeld@verizon.com, 814-946-5909, 1119 16th Street Altoona, PA 16601 | Per initial site visit there is OH T/CATV with poles located 5' left (looking north). | OH |  |  | 2016-06-14
323h | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | Comm | Zayo Group (Allegheny Communications Connect) | John Lynch, john.lynch@zayo.com, 724-972-5667; Ricci Blakeley, ricci.blakeley@zayo.com, 800 Cabin Hill Dr., Room M213, Greensburg, PA 15601 | Per initial site visit there is OH T/CATV with poles located 5' left (looking north). Also fiber. Confirmed that they are the Fiber company | OH |  |  | 2016-06-14
324a | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | gas | Amerigas Propane LP | Ray Veroli, 814-445-6591 | DID NOT RESPOND per one call. Per phone call on 8/5/15 they do not have any facilities in public ROW only propane tanks on private properties. |  |  |  | 2016-06-01
324b | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | Elect | Pennsylvania Electric Company | Keith Gardner, kgardner@firstenergycorp.com, 814-269-6678; Marty Kerch (manager), 814-269-6773, mkerch@firstenergycorp.com, 311 Industrial Park Road, Johnstown, PA 15904 | DID NOT RESPOND per one call. Per initial site visit there is OH power on left (facing east). | OH |  |  | 2016-06-01
324c | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | Comm | Verizon Pennsylvania LLC | Barbara Witkowski, barb.witkowski@verizon.com, 814-871-2275; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999, 20 East 10th St., Erie, Pa 16501 | Per initial site visit there is OH phone running adjacent to bridge 5' right (looking east). It crosses road 60' east of bridge to pole 20' left of road. VZ 5 134, 1210 6 | OH |  |  | 2016-06-01
324d | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | Elect | REA Energy Coop | Chris Yahner, cyahner@reaenergy.com, 814-472-8570 | Per initial site visit there is OH phone running adjacent to bridge 5' right (looking east). It crosses road 60' east of bridge to pole 20' left of road. VZ 5 134, 1210 6. No facilities near bridge |  |  |  | 2016-06-01
324e | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | Comm | Comcast Cable Communications, Inc. | John Radeshak, John_Radeshak@cable.comcast.com, 412-352-5769, 1250 Greensburg Rd., Lower Burrell, Pa. 15068 | May have fiber on verizon poles. Have UG fiber. Confirming if they have OH. | Both |  |  | 2016-06-01
325a | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | GAS | Amerigas Propane LP | Ray Veroli, 814-445-6591 | DID NOT RESPOND per one call. Called several times left vm and no response. Spoke to a rep on 8/5 and they do not have any facilities near the bridge. They said that they do not have any facilities in public ROW only propane tanks on private properties. |  |  |  | 2016-06-02
325b | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | DID NOT RESPOND to one call. Per initial site visit there is OH E/T on same pole right of road (looking north). No pole markings visible. Not Penelec. |  |  |  | 2016-06-02
325c | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | Comm | Verizon Pennsylvania LLC | Barbara Witkowski, barb.witkowski@verizon.com, 814-871-2275; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999, 20 East 10th St., Erie, Pa 16501 | Per initial site visit there is OH E/T on same pole right of road (looking north). No pole markings visible. Verification confirmed that verizon owns the poles and there is OH fiber (comcast) on them only, no power. | Poles Only |  |  | 2016-06-02
325d | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | wtr | Tri-Township Water Auth | Janet, 814-487-7056 | per initial site visit there are blue flags at creek crossing right of bridge (looking north). Need to investigate. Responded clear through one call. Janet with WA left voicemail that they don’t have facilities in this area on 7/9. |  |  |  | 2016-06-02
325e | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | Elect | REA Energy Coop | Chris Yahner, cyahner@reaenergy.com, 814-472-8570 | Per initial site visit there is OH E/T on same pole right of road (looking north). No pole markings visible. No facilities near bridge. The poles only have fiber (comcast) no power |  |  |  | 2016-06-02
325f | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | Comm | Comcast Cable Communications, Inc. | John Radeshak, John_Radeshak@cable.comcast.com, 412-352-5769, 1250 Greensburg Rd., Lower Burrell, Pa. 15068 | Has fiber on poles. | OH |  |  | 2016-06-02
326a | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 |  | all facilities responded clear per one call | [5 empty] | 2016-07-13
326b | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com (manager), 820 S. 4th Street, Clearfield, PA 16830 | Per initial site visit OH E/T/CATV. Pole is 10' rt nearside and 6' rt far side (looking east). There were orange and pink flag markers near pole with control panel box. Label on box says "State Park" | OH |  |  | 2016-07-13
326c | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | Comm | Verizon Pennsylvania LLC | Richard (Rich) Lampenfeld, richard.m.lampenfeld@verizon.com, 814-946-5909, 1119 16th Street Altoona, PA 16601 | Per initial site visit OH E/T/CATV. Pole is 10' rt nearside and 6' rt far side (looking east). Has OH copper and fiber lines | OH |  |  | 2016-07-13
326d | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | Comm | Comcast Cable Communications, Inc. | Doug Olszewski, douglas_olszewski@cable.comcast.com, 724-459-9042 x72661 | Per initial site visit OH E/T/CATV. Pole is 10' rt nearside and 6' rt far side (looking east). Confirmed no facilities on 8/31/15 |  |  |  | 2016-07-13
326e | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | Comm | Windstream | Jay Knight, Jay.Knight@windstream.com, 814-272-2648, 441 Science Park Road, State College, PA 16827 | Per initial site visit OH E/T/CATV. Pole is 10' rt nearside and 6' rt far side (looking east). No facilities |  |  |  | 2016-07-13
327a | -- | 327 | 17813 | 22797 | 29048400101102 | 9 | Fulton | 0.2 MILE EAST OF TR 26 | PA 484 | SIDELING HILL CREEK | 29/210 - UNION | 39.743 | -78.3593 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com, Nelson White (Manager) nwhite@nisource.com, 150 Hillside Drive, Bethel Park, PA 15102 | Conflict. Lines Nearby per one call. | UG |  |  | 2017-05-11
327b | -- | 327 | 17813 | 22797 | 29048400101102 | 9 | Fulton | 0.2 MILE EAST OF TR 26 | PA 484 | SIDELING HILL CREEK | 29/210 - UNION | 39.743 | -78.3593 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby per one call. | OH |  |  | 2017-05-11
328a | -- | 328 | 17826 | 22798 | 29052201401573 | 9 | Fulton | NEEDMORE | US 522 | BARNETT RUN | 29/202 - BELFAST | 39.8439 | -78.1487 | wtr | Needmore Water Supply Co Inc | Donny Gordon, 717-816-6460, 1230 Everetts Road, Needmore, PA 17238 | insufficient info. Do not dig per one call. Water main runs adjacent to and crosses existing bridge UG. Also artesian well near bridge. | UG |  |  | 2016-07-25
328b | -- | 328 | 17826 | 22798 | 29052201401573 | 9 | Fulton | NEEDMORE | US 522 | BARNETT RUN | 29/202 - BELFAST | 39.8439 | -78.1487 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby per one call. Per initial site visit OH power is greater than 50' away right (looking east). | OH |  |  | 2016-07-25
328c | -- | 328 | 17826 | 22798 | 29052201401573 | 9 | Fulton | NEEDMORE | US 522 | BARNETT RUN | 29/202 - BELFAST | 39.8439 | -78.1487 | Comm | Frontier Communications | Craig (Kip) Pletz, Craig.Pletz@ftr.com, 717-587-9740, 37 Diller Avenue, New Holland, PA 17557 | Per initial site visit OH T/catv. Pole offset 8' left (looking east) | OH |  |  | 2016-07-25
329a | -- | 329 | 17827 | 22825 | 29052201600330 | 9 | Fulton | 3/4 MILE N. OF NEEDMORE | US 522 | PALMER RUN | 29/202 - BELFAST | 39.854 | -78.1398 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY per one call. Per initial site visit OH power is greater than 30' left (looking east) | OH |  |  | 2016-04-11
329b | -- | 329 | 17827 | 22825 | 29052201600330 | 9 | Fulton | 3/4 MILE N. OF NEEDMORE | US 522 | PALMER RUN | 29/202 - BELFAST | 39.854 | -78.1398 | Comm | Frontier Communications | Craig (Kip) Pletz, Craig.Pletz@ftr.com, 717-587-9740, 37 Diller Avenue, New Holland, PA 17557 | Per initial site visit OH phone. Pole offset is 8' rt (looking east). Confirmed it is frontier due to its close proximity to JV330. Meeting with them in field on 6/4 | OH |  |  | 2016-04-11
330a | -- | 330 | 17828 | 22826 | 29052201601370 | 9 | Fulton | 1 MILE NORTH OF NEEDMORE | US 522 | LITTLE TONOLOWAY CREEK | 29/202 - BELFAST | 39.8549 | -78.1363 | Comm | Frontier Communications | Craig (Kip) Pletz, Craig.Pletz@ftr.com, 717-587-9740, 37 Diller Avenue, New Holland, PA 17557 | telephone pole at Sta 664+68.71, 18 FT LT is a Potential conflict with Guide Rail installation. May need to be temporary supported during construction. May also be a permanent conflict. This did not come from onecall but through design. Determined that it is Frontier - KE 5/11/15 | OH |  |  | 2016-04-11
330b | -- | 330 | 17828 | 22826 | 29052201601370 | 9 | Fulton | 1 MILE NORTH OF NEEDMORE | US 522 | LITTLE TONOLOWAY CREEK | 29/202 - BELFAST | 39.8549 | -78.1363 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY per one call. Responded to DFV that they arent affected. | OH |  |  | 2016-04-11
330c | -- | 330 | 17828 | 22826 | 29052201601370 | 9 | Fulton | 1 MILE NORTH OF NEEDMORE | US 522 | LITTLE TONOLOWAY CREEK | 29/202 - BELFAST | 39.8549 | -78.1363 | Elect | Valley Rural Electric Coop Inc | Patrick Lichner, 814-793-2609, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. Spoke to Patrick Lichner with Valley Rural on 4/30/15 and he verified that they do not have lines on this bridge. This is a west penn area only. |  |  |  | 2016-04-11
331a | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | Comm | Centurylink formerly Embarq | Bradley (Brad) Benson, Bradley.J.Benson1@centurylink.com, 717-267-4724, 250 Lincoln Way East, Chambersburg, PA 17201 | CONFLICT. LINES NEARBY per one call. Received marked up plans on 5/14/15. They are the pole owners. OH T/catv lines. Pole offset right 4' (looking east) | OH |  |  | 2016-05-23
331b | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | Comm | Comcast Cable Communications, Inc. | Jeffrey (Jeff) Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com; Dennis Thomas, Dennis_Thomas@cable.comcast.com | CONFLICT. LINES NEARBY per one call. Comcast confirmed on 5/1/15 after receiving the DFV submittle that they don’t have any utilities in the area. |  |  |  | 2016-05-23
331c | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | sanitary | McConnellsburg Sewerage Auth | Craig Strait, 717-485-4728, 20789 Great Cove Road McConnellsburg, PA 17233 | DID NOT RESPOND to one call. Responded to DFV that they are in the work area but arent affected. | UG |  |  | 2016-05-23
331d | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | Elect | Valley Rural Electric Coop Inc | Patrick Lichner, 814-793-2609, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. Spoke to Patrick Lichner with Valley Rural on 4/30/15 and he verified that they do not have lines on this bridge. This is a west penn area only. |  |  |  | 2016-05-23
331e | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby per one call. Response back from DFV is not affected. Per initial site visit there is OH power. Pole offset left 6'. Pole tags PE System W59184; G 192, UT Company of PA, G106; PE System W59184 | OH |  |  | 2016-05-23
332a | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 | Comm | Centurylink formerly Embarq | Bradley (Brad) Benson, Bradley.J.Benson1@centurylink.com, 717-267-4724, 250 Lincoln Way East, Chambersburg, PA 17201 | CONFLICT. LINES NEARBY per one call. Per initial site visit OH comm 12' right looking north | OH |  |  | 2016-07-13
332b | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 |  | Licking Creek TWP | 717-573-2822, 13064 Timber Ridge Rd Needmore, PA 17238 | DID NOT RESPOND per one call. Confirmed no facilities on 10/22/15 |  |  |  | 2016-07-13
332c | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | CONFLICT. LINES NEARBY per one call. Per initial site visit Valley Rural electric substation north of bridge on right looking north. The lines and station are not in the limits of work for the project. OH phone only per google earth. |  |  |  | 2016-07-13
332d | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY per one call. Per initial site visit electric substation north of bridge on right looking north. OH phone only per google earth. |  |  |  | 2016-07-13
333a | -- | 333 | 17853 | 88142 | 29065504501203 | 9 | Fulton | 1.4 MI. SOUTH OF TURNPIKE | PA 655 | FORTUNE TELLER CREEK | 29/205 - DUBLIN | 40.0275 | -78.0282 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. Per initial site visit OH power and phone. Pole offset >50 ft right (looking east). Pole tag 87132 2 E147 33N 531 | OH |  |  | 2016-08-08
333b | -- | 333 | 17853 | 88142 | 29065504501203 | 9 | Fulton | 1.4 MI. SOUTH OF TURNPIKE | PA 655 | FORTUNE TELLER CREEK | 29/205 - DUBLIN | 40.0275 | -78.0282 | Comm | Comcast Cable Communications, Inc. | Jeffrey (Jeff) Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com; Dennis Thomas, Dennis_Thomas@cable.comcast.com | CONFLICT. LINES NEARBY per one call. Per initial site visit OH comm. Pole offset 35 ft left (looking east). Pole tag 87132 2 E147 33N 53 1 |  |  |  | 2016-08-08
333c | -- | 333 | 17853 | 88142 | 29065504501203 | 9 | Fulton | 1.4 MI. SOUTH OF TURNPIKE | PA 655 | FORTUNE TELLER CREEK | 29/205 - DUBLIN | 40.0275 | -78.0282 | sanitary | Hustontown Sewage Auth | 717-485-4665, 171 Spring Dr, Hustontown, PA 17229 | DID NOT RESPOND per one call. Did not note any sewer in initial site visit. Confirmed no facilities on 9/14/15 |  |  |  | 2016-08-08
333d | -- | 333 | 17853 | 88142 | 29065504501203 | 9 | Fulton | 1.4 MI. SOUTH OF TURNPIKE | PA 655 | FORTUNE TELLER CREEK | 29/205 - DUBLIN | 40.0275 | -78.0282 | Comm | Centurylink formerly Embarq | Bradley (Brad) Benson, Bradley.J.Benson1@centurylink.com, 717-267-4724, 250 Lincoln Way East, Chambersburg, PA 17201 | OH Phone per site visit | OH |  |  | 2016-08-08
334a | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | Elect | Valley Rural Electric Coop Inc | Rick Poleck, 814-643-2650 x1656, rpoleck@valleyrec.com, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. No OH power indicated in initial site visit. No facilities in the area. |  |  |  | 2016-10-17
334b | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby per one call. No OH power indicated in initial site visit. Confirmed no facilities within the work area of this project |  |  |  | 2016-10-17
334c | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | Comm | Centurylink formerly Embarq | Bradley (Brad) Benson, Bradley.J.Benson1@centurylink.com, 717-267-4724, 250 Lincoln Way East, Chambersburg, PA 17201 | CONFLICT. LINES NEARBY per one call. Per initial site visit OH phone 3' rt (looking north) Pole tag, UTCo of PA, G19, Pole Inventory #A2779733 | OH |  |  | 2016-10-17
334d | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | Comm | Comcast Cable Communications, Inc. | Jeffrey (Jeff) Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com; Dennis Thomas, Dennis_Thomas@cable.comcast.com | CONFLICT. LINES NEARBY per one call. Per initial site visit OH phone 3' rt (looking north) Pole tag, UTCo of PA, G19, Pole Inventory #A2779733. No facilities in area. |  |  |  | 2016-10-17
335a | -- | 335 | 18576 | 74433 | 31002202300000 | 9 | Huntingdon | OVER TR 26 | US 22 | PA 0026 | 31/221 - SMITHFIELD | 40.4912 | -78.0388 | Gas | UGI Central Penn Gas | Andrew Black, ablack@ugi.com, 570-829-8967; Dave Fisher, 570-473-7464, dfisher@ugipng.com | Design Conflict. Please send plans to: Andrew Black UGI Central Penn Gas 225 Morgantown Rd Reading PA 19611 (per one call | UG |  |  | 2017-03-21
335b | -- | 335 | 18576 | 74433 | 31002202300000 | 9 | Huntingdon | OVER TR 26 | US 22 | PA 0026 | 31/221 - SMITHFIELD | 40.4912 | -78.0388 |  | Huntingdon B/H Area Water & Sewer Auth | Karen Brown (secy), 814-643-2644, kbrown@huntingdonboro.com | DID NOT RESPOND per one call. |  |  |  | 2017-03-21
335c | -- | 335 | 18576 | 74433 | 31002202300000 | 9 | Huntingdon | OVER TR 26 | US 22 | PA 0026 | 31/221 - SMITHFIELD | 40.4912 | -78.0388 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | Per initial site visit OH E/T/CATV approx 40' south of existing abutment | OH |  |  | 2017-03-21
335d | -- | 335 | 18576 | 74433 | 31002202300000 | 9 | Huntingdon | OVER TR 26 | US 22 | PA 0026 | 31/221 - SMITHFIELD | 40.4912 | -78.0388 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH E/T/CATV approx 40' south of existing abutment | OH |  |  | 2017-03-21
335e | -- | 335 | 18576 | 74433 | 31002202300000 | 9 | Huntingdon | OVER TR 26 | US 22 | PA 0026 | 31/221 - SMITHFIELD | 40.4912 | -78.0388 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH E/T/CATV approx 40' south of existing abutment | OH |  |  | 2017-03-21
336a | -- | 336 | 18601 | 23030 | 31002604900654 | 9 | Huntingdon | .1 MI N SR1011,CNTR UNION | PA 26 | MURRAY RUN | 31/217 - ONEIDA | 40.5401 | -77.9603 | Elect | Pennsylvania Electric Company | Richard (Rick) Fink, rfink@firstenergycorp.com, 814-949-4641, 405 west plank road, Altoona, PA, 16601 | DID NOT RESPOND per one call. Per initial site visit Penelec Substation approx. 50' south of bridge 20' left (looking north). High tension electric crosses road south of bridge from substation to poles east of bridge and creek. | OH |  |  | 2016-04-11
336b | -- | 336 | 18601 | 23030 | 31002604900654 | 9 | Huntingdon | .1 MI N SR1011,CNTR UNION | PA 26 | MURRAY RUN | 31/217 - ONEIDA | 40.5401 | -77.9603 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | CONFLICT. LINES NEARBY per one call. Valley Rural REC substation just south of Penelec Substation | OH |  |  | 2016-04-11
336c | -- | 336 | 18601 | 23030 | 31002604900654 | 9 | Huntingdon | .1 MI N SR1011,CNTR UNION | PA 26 | MURRAY RUN | 31/217 - ONEIDA | 40.5401 | -77.9603 | Comm | Verizon Pennsylvania LLC | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com, 250 S ALLEN ST, STATE COLLEGE, PA 16801 | Clear No Facilities per one call. Per initial site visit OH T/F/CATV approx. 10 ft rt (looking north). Own OH T/F. | OH |  |  | 2016-04-11
336d | -- | 336 | 18601 | 23030 | 31002604900654 | 9 | Huntingdon | .1 MI N SR1011,CNTR UNION | PA 26 | MURRAY RUN | 31/217 - ONEIDA | 40.5401 | -77.9603 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH T/F/CATV approx. 10 ft rt (looking north). Own CATV | OH |  |  | 2016-04-11
337a | -- | 337 | 18603 | 22980 | 31002605100972 | 9 | Huntingdon | 0.2 MILE NORTH OF SR 1009 | PA 26 | HORN RUN | 31/217 - ONEIDA | 40.5574 | -77.9527 | comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | CONFLICT. LINES NEARBY per one call. | OH |  |  | 2017-03-21
337b | -- | 337 | 18603 | 22980 | 31002605100972 | 9 | Huntingdon | 0.2 MILE NORTH OF SR 1009 | PA 26 | HORN RUN | 31/217 - ONEIDA | 40.5574 | -77.9527 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | CONFLICT. LINES NEARBY per one call. | OH |  |  | 2017-03-21
337c | -- | 337 | 18603 | 22980 | 31002605100972 | 9 | Huntingdon | 0.2 MILE NORTH OF SR 1009 | PA 26 | HORN RUN | 31/217 - ONEIDA | 40.5574 | -77.9527 | Comm | Verizon Pennsylvania LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | Per initial site visit OH E/T/CATV on north side of bridge | OH |  |  | 2017-03-21
338a | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. Per initial site visit there is OH power to the far south of bridge. OH E/CATV. | OH |  | NOT AFFECTED | 2016-05-23
338b | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | wtr and sanitary | Mill Creek Area Municipal Auth | 814-643-5666 (main office); Keith Bollinger (operator), 814-386-4167, Main Street Mill Creek, PA 17060 (verified that address has no number), only open until noon M-F | DID NOT RESPOND per one call. Per initial site visit water main crosses road west of bridge and then runs east crossing creek south of bridge and OH poles. Valve located west of bridge and fire hydrant located north of bridge both on south side. Sanitary sewer crosses road west of bridge. One MH north of road and one manhole south of road. WIll need to confirm with Mill Creek since they did not respond to one call. Called on 6/10/15 to get contact info for plan reviews. Verified that they dont have plans that they can send but will review the D4181 submittal package | UG |  | NOT AFFECTED | 2016-05-23
338c | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | Comm | Verizon Pennsylvania LLC | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com, 250 S ALLEN ST, STATE COLLEGE, PA 16801 | Per initial site visit there is OH T/F approx. 22' to the right (looking east). Have lines but aren't pole owner. On centurylink poles | OH |  | NOT AFFECTED | 2016-05-23
338d | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com, 3989 William Penn Hwy., Mifflintown, PA 17059 | was not on one call but verizon thought they were the pole owners. Verified that they do have facilities in the area. Pole Owners | OH |  | NOT AFFECTED | 2016-05-23
338e | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | may be catv on power poles. Confirmed that they are on the power poles which are out of the work area. | OH |  | NOT AFFECTED | 2016-05-23
338f | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | Comm | Sunesys | Dave Hayward, 267-927-2000, dhayward@sunesys.com, 185 Titus Avenue, Warrington, PA 18976 | fiber on centurylink poles | OH |  | NOT AFFECTED | 2016-05-23
339a | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | Elect | Pennsylvania Electric Company | Timothy (Tim) Frye, 814-949-4652, tfrye@firstenergycorp.com; Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com | DID NOT RESPOND per one call. Per initial site visit OH power/phone/cable. Pole is approx. 40 ft north of bridge and 8 ft lt (looking north). Power/phone/cable crosses road north to post office. Power/phone comes from pole and crosses bridge to pole at the intersection of Lincoln St. | OH |  |  | 2017-04-03
339b | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | wtr and sanitary | Wood Broad Top Wells JT Muni Auth | Fred Myers, 814-635-2354, watera1@comcast.net, Ann Reynolds with GHD Engineering (consultant), ann.reynolds@ghd.com | DID NOT RESPOND per one call. Per initial site visit there is a fire hydrant at intersection with Lincoln St. south of bridge. | UG |  |  | 2017-04-03
339c | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 |  | Wood TWP | Norman L. McClain (secy), 814-635-2440 | DID NOT RESPOND. Per Wood Broad MA they only have storm and that it is marked out by them. |  |  |  | 2017-04-03
339d | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | Comm | Verizon Pennsylvania LLC | Richard (Rich) Lampenfeld, richard.m.lampenfeld@verizon.com, 814-946-5909, 1119 16th Street Altoona, PA 16601 | Per initial site visit OH power/phone/cable. Pole is approx. 40 ft north of bridge and 8 ft lt (looking north). Power/phone/cable crosses road north to post office. Power/phone comes from pole and crosses bridge to pole at the intersection of Lincoln St. | OH |  |  | 2017-04-03
339e | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621, 250 Reese Rd. State College PA. 16801 | Per initial site visit OH power/phone/cable. Pole is approx. 40 ft north of bridge and 8 ft lt (looking north). Power/phone/cable crosses road north to post office. | OH |  |  | 2017-04-03
340 | -- | 340 | 18773 | 23058 | 31100800400000 | 9 | Huntingdon | 1 MI.E.OF COTTAGE | SR 1008 | SHAVERS CREEK | 31/229 - WEST | 40.6178 | -77.9684 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. | OH |  |  | 2017-05-31
341a | -- | 341 | 18784 | 23114 | 31101900100185 | 9 | Huntingdon | 0.03 MILE NORTH FROM PA 26 | SR 1019 | STANDING STONE CREEK | 31/215 - MILLER | 40.5957 | -77.862 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. Per initial site visit OH E not near work. | OH |  |  | 2016-07-11
341b | -- | 341 | 18784 | 23114 | 31101900100185 | 9 | Huntingdon | 0.03 MILE NORTH FROM PA 26 | SR 1019 | STANDING STONE CREEK | 31/215 - MILLER | 40.5957 | -77.862 | Comm | Verizon Pennsylvania LLC | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com, 250 S ALLEN ST, STATE COLLEGE, PA 16801 | Per initial site visit OH T running adjacent to bridge approx. 15 ft rt (looking north). Pole located adjacent to west abutement rt. OH T crosses road diagonally from pole north to pole on west side of road. | OH |  |  | 2016-07-11
342 | -- | 342 | 18785 | 74449 | 31101900600000 | 9 | Huntingdon | 1.75 MILE NORTH FROM PA 26 | SR 1019 | E BR STANDING STONE CRK | 31/211 - JACKSON | 40.6009 | -77.8322 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667, 10787 Station Road, Huntingdon, PA 16652-0477 | Conflict. Lines Nearby per one call. | OH |  |  | 2017-05-11
343 | -- | 343 | 18881 | 23116 | 31400900200000 | 9 | Huntingdon | 0.24 MILE NORTH FROM PA 305 | SR 4009 | SHAVERS CREEK | 31/214 - LOGAN | 40.5824 | -78.0459 |  | all facilities responded clear per one call | [5 empty] | 2017-05-11
344a | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 |  | Shade TWP | Lillian Feathers (secy), 814-754-4622 | DID NOT RESPOND per one call. Verified no facilities |  |  |  | 2016-05-12
344b | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | Elect | West Penn Power | Don Morchesky, dmorche@firstenergycorp.com, 724-838-6047 | Per initial site visit OH E/T 5 ft left (looking east). Pole tag PECO 33895; PECO 33894. Not their facilities and suggested Somerset REC. Going to check with Penelec first since the poles are labeled PECO. |  |  |  | 2016-05-12
344c | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | Comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | Per initial site visit OH E/T 5 ft left (looking east). Pole tag PECO 33895; PECO 33894 | OH |  |  | 2016-05-12
344d | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 |  | Upper Stonycreek JT Muni Auth | 814-893-5668, Randy Yunken, 814-442-4446 | DID NOT RESPOND per one call. Verified no facilities over the phone with Randy Yunken |  |  |  | 2016-05-12
344e | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | Elect | Pennsylvania Electric Company | Keith Gardner, kgardner@firstenergycorp.com, 814-269-6678; Marty Kerch (manager), 814-269-6773, mkerch@firstenergycorp.com, 311 Industrial Park Road, Johnstown, PA 15904 | Per initial site visit OH E/T 5 ft left (looking east). Pole tag PECO 33895; PECO 33894. | OH |  |  | 2016-05-12
344f | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | Comm | Comcast Cable Communications, Inc. | Brian Woller, Brian_Woller@cable.comcast.com, 724-221-6479, 201 N Tremont Avenue, Greensburg, PA 15601 | Verizon thought that Comcast was also on pole | OH |  |  | 2016-05-12
344g | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | Comm | Salsgiver (CLEC) | Amy Lightner, amyb@salsgiver.com, 714-295-1970 x102, 301 Fifth Street, Freeport, PA 16229 | Confirm if CLEC is on poles and owned by Salsgiver. | OH |  |  | 2016-05-12
345a | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | Elect | Pennsylvania Electric Company | Keith Gardner, kgardner@firstenergycorp.com, 814-269-6678; Marty Kerch (manager), 814-269-6773, mkerch@firstenergycorp.com, 311 Industrial Park Road, Johnstown, PA 15904 | CONFLICT. LINES NEARBY per one call. Per initial site visit OH E/T 3ft left (looking east). Pole tag GTE 16201 432 | OH |  |  | 2016-05-25
345b | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 |  | Shade TWP | Lillian Feathers (secy), 814-754-4622 | DID NOT RESPOND per one call. Verified no facilities |  |  |  | 2016-05-25
345c | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 |  | Upper Stonycreek JT Muni Auth | 814-893-5668, Randy Yunken, 814-442-4446 | DID NOT RESPOND per one call. Verified no facilities over the phone with Randy Yunken |  |  |  | 2016-05-25
345d | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | Comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | Per initial site visit OH E/T 3ft left (looking east). Pole tag GTE 16201 432 | OH |  |  | 2016-05-25
345e | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | Comm | Comcast Cable Communications, Inc. | Brian Woller, Brian_Woller@cable.comcast.com, 724-221-6479, 201 N Tremont Avenue, Greensburg, PA 15601 | Verizon thought that Comcast was also on pole | OH |  |  | 2016-05-25
345f | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | Comm | Zito Media LP (CLEC) | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com; Tony Luna, tony.luna@zitomedia.com; 102 S Main Street, 2nd Floor, Coudersport, PA 16915 | Verizon though that CLEC may be on poles and it could be owned by Zito, Synesus, or Salsgiver |  |  |  | 2016-05-25
345g | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | Comm | Salsgiver (CLEC) | Amy Lightner, amyb@salsgiver.com, 714-295-1970 x102, 301 Fifth Street, Freeport, PA 16229 | Confirm if CLEC is on poles and owned by Salsgiver. | OH |  |  | 2016-05-25
346a | -- | 346 | 31343 | 23517 | 55003104200000 | 9 | Somerset | 0.5 MILE EAST OF SR 1005 | PA 31 | SANDY HOLLOW CREEK | 55/223 - STONYCREEK | 39.9649 | -78.9481 |  | all facilities responded clear per one call | [5 empty] | 2017-03-21
346b | -- | 346 | 31343 | 23517 | 55003104200000 | 9 | Somerset | 0.5 MILE EAST OF SR 1005 | PA 31 | SANDY HOLLOW CREEK | 55/223 - STONYCREEK | 39.9649 | -78.9481 | Elect | Pennsylvania Electric Company | Martin (Marty) Kerch, mkerch@firstenergycorp.com, 814-269-6773 | Per initial site visit OH E crosses road diagonally north of bridge. OH is 3-phase. Pole # 37589 | OH |  |  | 2017-03-21
347a | -- | 347 | 31469 | 23586 | 55052300301840 | 9 | Somerset | LISTONBURG | PA 523 | WHITES CREEK | 55/201 - ADDISON | 39.7544 | -79.3142 |  | all facilities responded clear per one call | [5 empty] | 2016-05-31
347b | -- | 347 | 31469 | 23586 | 55052300301840 | 9 | Somerset | LISTONBURG | PA 523 | WHITES CREEK | 55/201 - ADDISON | 39.7544 | -79.3142 | Elect | Pennsylvania Electric Company | Keith Gardner, kgardner@firstenergycorp.com, 814-269-6678; Marty Kerch (manager), 814-269-6773, mkerch@firstenergycorp.com, 311 Industrial Park Road, Johnstown, PA 15904 | Per initial site visit there is OH E/P/CATV approx. 10' rt (looking north). Crossing from pole at northeast corner of bridge directly behind guard rail across road to pole far west of road. Pole tags 70143-141, 156026, B014646; 70143-140, 9911-s | OH |  |  | 2016-05-31
347c | -- | 347 | 31469 | 23586 | 55052300301840 | 9 | Somerset | LISTONBURG | PA 523 | WHITES CREEK | 55/201 - ADDISON | 39.7544 | -79.3142 | Comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | Per initial site visit there is OH E/P/CATV approx. 10' rt (looking north). Crossing from pole at northeast corner of bridge directly behind guard rail across road to pole far west of road. Pole tags 70143-141, 70143-140, 9911-s | OH |  |  | 2016-05-31
347d | -- | 347 | 31469 | 23586 | 55052300301840 | 9 | Somerset | LISTONBURG | PA 523 | WHITES CREEK | 55/201 - ADDISON | 39.7544 | -79.3142 | Comm | Comcast Cable Communications, Inc. | Christopher McKahan, Christopher_McKahan@cable.comcast.com, 412-491-3798, 15 Summer School Road, Morgantown, WV 26508 | Per initial site visit there is OH E/P/CATV approx. 10' rt (looking north). Crossing from pole at northeast corner of bridge directly behind guard rail across road to pole far west of road. Pole tags 70143-141, 70143-140, 9911-s | OH |  |  | 2016-05-31
348a | -- | 348 | 31470 | 23410 | 55052300701200 | 9 | Somerset | BEACHLY | PA 523 | LAUREL RUN | 55/201 - ADDISON | 39.7766 | -79.3107 | comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | CONFLICT. LINES NEARBY per one call. Per initial site visit OH phone is out of work area. Pole tag GTE 014391 | OH |  |  | 2016-05-31
348b | -- | 348 | 31470 | 23410 | 55052300701200 | 9 | Somerset | BEACHLY | PA 523 | LAUREL RUN | 55/201 - ADDISON | 39.7766 | -79.3107 | Elect | Pennsylvania Electric Company | Keith Gardner, kgardner@firstenergycorp.com, 814-269-6678; Marty Kerch (manager), 814-269-6773, mkerch@firstenergycorp.com, 311 Industrial Park Road, Johnstown, PA 15904 | Per initial site visit OH power crossing bridge diagonally from pole (# 0143 91GTE) located west of bridge 13' left (looking east) to pole (70J6J) located east of bridge 13' right (looking east) | OH |  |  | 2016-05-31
348c | -- | 348 | 31470 | 23410 | 55052300701200 | 9 | Somerset | BEACHLY | PA 523 | LAUREL RUN | 55/201 - ADDISON | 39.7766 | -79.3107 | Comm | Comcast Cable Communications, Inc. | Christopher McKahan, Christopher_McKahan@cable.comcast.com, 412-491-3798, 15 Summer School Road, Morgantown, WV 26508 | Have CATV attached to OH power poles. | OH |  |  | 2016-05-31
349a | -- | 349 | 31471 | 74446 | 55052300801065 | 9 | Somerset | DUMAS | PA 523 | TRIB TO WHITES CREEK | 55/201 - ADDISON | 39.7817 | -79.3174 | Elect | Pennsylvania Electric Company | Keith Gardner, kgardner@firstenergycorp.com, 814-269-6678; Marty Kerch (manager), 814-269-6773, mkerch@firstenergycorp.com, 311 Industrial Park Road, Johnstown, PA 15904 | CONFLICT. LINES NEARBY per one call. Please see field maps located in the one call folder in sharepoint for this bridge. Per initial site visit OH E/T 9' rt (looking north). Crosses road north of bridge at pole VZ76-70143, 9407S. Guy wires from this pole run south east across creek. Guy pole west of bridge just north of creek. | OH |  |  | 2016-04-15
349b | -- | 349 | 31471 | 74446 | 55052300801065 | 9 | Somerset | DUMAS | PA 523 | TRIB TO WHITES CREEK | 55/201 - ADDISON | 39.7817 | -79.3174 | comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | CONFLICT. LINES NEARBY per one call. Per initial site visit OH E/T 9' rt (looking north). Crosses road north of bridge at pole VZ76-70143, 9407S. Guy wires from this pole run south east across creek. Guy pole west of bridge just north of creek. | Both |  |  | 2016-04-15
349c | -- | 349 | 31471 | 74446 | 55052300801065 | 9 | Somerset | DUMAS | PA 523 | TRIB TO WHITES CREEK | 55/201 - ADDISON | 39.7817 | -79.3174 | Comm | Comcast Cable Communications, Inc. | Christopher McKahan, Christopher_McKahan@cable.comcast.com, 412-491-3798, 15 Summer School Road, Morgantown, WV 26508 | May have CATV attached to OH power poles based on survey. | OH |  |  | 2016-04-15
350 | -- | 350 | 31521 | 23516 | 55100400101850 | 9 | Somerset | SHANKSVILLE BORO. | SR 1004 | RHOADS CREEK | 55/417 - SHANKSVILLE | 40.0153 | -78.9019 |  | Shanksville Borough | Kimberly Belsterling (secy), 814-267-6421 | DID NOT RESPOND per one call. |  |  |  | 2017-05-22
351 | -- | 351 | 31528 | 23571 | 55100700300000 | 9 | Somerset | 0.99 MILE NORTH FROM PA 160 | SR 1007 | TRIB STONYCREEK RIVER | 55/223 - STONYCREEK | 39.97 | -78.9029 | comm | Verizon North LLC | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126 | CONFLICT. LINES NEARBY per one call. |  |  |  | 2017-05-30
352 | -- | 352 | 31532 | 23588 | 55100701800000 | 9 | Somerset | LAMBERTSVILLE | SR 1007 | LAMBERT RUN | 55/223 - STONYCREEK | 40.0705 | -78.9142 |  | all facilities responded clear per one call | [5 empty] | 2017-06-05
353 | -- | 353 | 31588 | 74467 | 55200500300000 | 9 | Somerset | 1.95 MILE SO.FROM SR 2004 @ SUMMIT MILLS | SR 2005 | ELK LICK CREEK | 55/224 - SUMMIT | 39.8089 | -79.1065 | Comm | Comcast Cable of Garrett County MD | 814-201-6274 | DID NOT RESPOND per one call. |  |  |  | 2017-08-01
354a | -- | 354 | 31608 | 23428 | 55201301000000 | 9 | Somerset | 0.46 MILE SOUTH FROM SR 3002 | SR 2013 | POWDER RUN | 55/222 - SOUTHAMPTON | 39.7733 | -78.7894 | gas | Columbia Gas of PA Design | Nicholas Seese (field engineer), 724-415-9210, nseese@nisource.com; Nelson White (Manager) nwhite@nisource.com, 150 Hillside Drive, Bethel Park, PA 15102 | CONFLICT. LINES NEARBY per one call. No facilities per D4181. |  |  | NA | 2016-04-15
354b | -- | 354 | 31608 | 23428 | 55201301000000 | 9 | Somerset | 0.46 MILE SOUTH FROM SR 3002 | SR 2013 | POWDER RUN | 55/222 - SOUTHAMPTON | 39.7733 | -78.7894 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com, 634 Lincoln Way, McConnellsburg, PA 17233; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Responded clear to one call. Determined during design that there is OH power that is West Penn over 50 ft (looking east). | OH |  | Coordinated | 2016-04-15
354c | -- | 354 | 31608 | 23428 | 55201301000000 | 9 | Somerset | 0.46 MILE SOUTH FROM SR 3002 | SR 2013 | POWDER RUN | 55/222 - SOUTHAMPTON | 39.7733 | -78.7894 | Comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | Per initial site visit pole id is GTE 12 1112 and it is 10 ft rt (looking east) | OH |  | Coordinated | 2016-04-15
355a | -- | 355 | 31630 | 23549 | 55201800600000 | 9 | Somerset | BEECHDALE | SR 2018 | BUFFALO CREEK | 55/204 - BROTHERS VALLEY | 39.8996 | -79.0119 |  | all facilities responded clear per one call | [5 empty] | 2016-08-22
355b | -- | 355 | 31630 | 23549 | 55201800600000 | 9 | Somerset | BEECHDALE | SR 2018 | BUFFALO CREEK | 55/204 - BROTHERS VALLEY | 39.8996 | -79.0119 | Elect | Pennsylvania Electric Company | Keith Gardner, kgardner@firstenergycorp.com, 814-269-6678; Marti Kerch (manager), 814-269-6773, mkerch@firstenergycorp.com, 311 Industrial Park Road, Johnstown, PA 15904 | Per initial site visit OH power 3'-6' lt (looking north). Pole tag 12081-S | OH |  |  | 2016-08-22
355c | -- | 355 | 31630 | 23549 | 55201800600000 | 9 | Somerset | BEECHDALE | SR 2018 | BUFFALO CREEK | 55/204 - BROTHERS VALLEY | 39.8996 | -79.0119 | Comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176, 250 S Allen St, State College, PA 16801; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | Penelec said verizon is at site | OH |  |  | 2016-08-22
355d | -- | 355 | 31630 | 23549 | 55201800600000 | 9 | Somerset | BEECHDALE | SR 2018 | BUFFALO CREEK | 55/204 - BROTHERS VALLEY | 39.8996 | -79.0119 | Comm | Comcast Cable of Garrett County MD | Christopher McKahan, Christopher_McKahan@cable.comcast.com, 412-491-3798, 15 Summer School Road, Morgantown, WV 26508 | May be on poles based on site photos | OH |  |  | 2016-08-22
356 | -- | 356 | 31651 | 23454 | 55202600300000 | 9 | Somerset | 2 MI.NE.OF MEYERSDALE | SR 2026 | BLUE LICK CREEK | 55/224 - SUMMIT | 39.8461 | -79.0011 | Comm | Comcast Cable of Garrett County MD | 814-201-6274 | DID NOT RESPOND per one call. |  |  |  | 2017-08-01
357a | -- | 357 | 31758 | 23601 | 55401900700000 | 9 | Somerset | OVER US 30 | SR 4019 | US 30 | 55/219 - QUEMAHONING | 40.1007 | -78.9565 |  | Somerset TWP Municipal Auth | Carolyn Zambanini (secy) 814-445-5842 | Marked per one call | UG |  |  | 2017-08-01
357b | -- | 357 | 31758 | 23601 | 55401900700000 | 9 | Somerset | OVER US 30 | SR 4019 | US 30 | 55/219 - QUEMAHONING | 40.1007 | -78.9565 |  | Upper Stonycreek JT Muni Auth | 814-893-5668, Randy Yunken, 814-442-4446 | DID NOT RESPOND per one call. |  |  |  | 2017-08-01
358a | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | wtr | Kiski Valley Water Pollution Control Auth | Gene Burns, eburns@kvwpca.com | Did Not Respond | UG |  |  | 2016-06-09
358b | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | wtr | Parks TWP | Peter Massetto, 724-567-7301, ptma@verizon.net Mary Ralston, parkstwp@kiski.net | Did Not Respond | UG |  |  | 2016-06-09
358c | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | SS | Parks Twp Municipal Auth | Peter Massetto, 724-567-7301, ptma@verizon.net Michael S. Moore, P.E, Bankson Engineering, 412-767-5100, mmoore@banksonengineers.com | Conflict. Lines Nearby | UG |  |  | 2016-06-09
358d | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | Elect | West Penn Power Company | Dennis Preus, dpreus@firstenergycorp.com Zach Reedy, (724) 548-3578, zreedy@firstenergycorp.com | Conflict. Lines Nearby |  |  |  | 2016-06-09
358e | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | Comm | Verizon North LLC | Robert Preston, (304) 670-9999, robert.preston@cyient.com Barbara Witkowski, barb.witkowski@verizon.com | Verizon listed facilities as not affected during verification. May change based on relocating poles if required |  |  |  | 2016-06-09
358f | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | Comm | Comcast | John Radeshak, O: 724-212-7236, C: 412-352-5769, John_Radeshak@cable.comcast.com Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | Did Not Respond |  |  |  | 2016-06-09
358g | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | Conflict. Lines Nearby |  |  |  | 2016-06-09
359a | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 | Elect | WEST PENN POWER COMPANY | Kevin Baker, 724-548-3538, kbaker2@firstenergycorp.com | SR 839, Sta. 274+33.6. to Sta. 281+68.8 Rt. | OH |  | RESTRICTIVE | 2015-07-13
359b | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 | TV | COMCAST CABLE CORPORATION | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com | SR 839, Sta. 274+33.6. to Sta. 281+68.8 Rt. | OH |  | RESTRICTIVE | 2015-07-13
359b | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 | TV | Salsgiver communications | Loren Salsgiver, 724-295-1970 x102, loren@salsgiver.com Construction Contact: Adam Nulph, 724-295-1970 x104, adamnulph@salsgiver.com | SR 839, Sta. 274+33.6. to Sta. 281+68.8 Rt. | OH |  | RESTRICTIVE | 2015-07-13
359c | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Tom Gerg, 814-849-3552, tom.gerg@windstream.com | SR 839, Sta. 274+33.6. to Sta. 281+68.8 Rt. | OH |  | RESTRICTIVE | 2015-07-13
360a | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | Elect | WEST PENN POWER COMPANY | Kevin Baker, 724-548-3538, kbaker2@firstenergycorp.com | S.R. 1039, Sta. 141+76.1, Rt. to Sta. 142+49.30 Lt | OH |  | Coordinated | 2015-07-29
360b | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kirk Myers, 724-543-7285, Kirk.Myers@windstream.com | S.R. 1039, Sta. 140+84.2 to Sta. 145+16.5 Lt | OH |  | Coordinated | 2015-07-29
360c | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kirk Myers, 724-543-7285, Kirk.Myers@windstream.com | S.R. 1039, Sta. 140+84.2 to Sta. 145+16.5 Lt | OH |  | Coordinated | 2015-07-29
360d | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | Gas | PEOPLES TWP, LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | SR 1039, Sta. 141+75 Lt. to Sta. 142+75 Lt | UG |  | Protect-In-Place | 2015-07-29
360e | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | Gas | PEOPLES TWP, LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | SR 1039, Sta. 141+75 Lt. to Sta. 142+75 Lt | UG |  | Coordinated | 2015-07-29
361a | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | Elect | Energy Corporation of America | Troy Medrich, 724-463-8400 | Conflict. Lines Nearby. |  |  |  | 2017-05-01
361b | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | Gas | Peoples Gas Valley Division | Michelle Saxion, 412-208-7239 | Marked. A follow up letter from Peoples gas states that they are not in conflict of area in onecall | UG |  |  | 2017-05-01
361c | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | wtr | Rural Valley Borough Water Works | Vince Tonkin, foreman, vtonkin@eca.com | Design Conflict. Please send plans to: Kevin Nelson Rural Valley Borough Water Works 300 W Parkwood Dr PO Box Rural Valley PA 16249. 4” steel pipeline is beyond 50 feet from centerline. The pipeline is exposed and visible where it crosses over Cowanshannock Creek. It crosses PA-85 east of water st. PLease see utility map located in the onecall folder for the bridge in sharepoint. | UG | 4" |  | 2017-05-01
361d | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | sanitary | Shannock Valley General Services Auth | 724-783-2454 | Not Marked due to no access | UG |  |  | 2017-05-01
361e | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 |  | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-05-01
361f | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Chad Shepherd, 724-733-3295, chad.e.shepherd@windstream.com | DID NOT RESPOND |  |  |  | 2017-05-01
362a | -- | 362 | 3176 | 83252 | 3200500500000 | 10 | Armstrong | BURRELL TWP-E OF BRICK CH | SR2005 | TRIB TO CHERRY RUN | 03/204 - BURRELL | 40.6885 | -79.4279 | sanitary | Burrell TWP | David J. Semsick, 724-248-7272 | DID NOT RESPOND | UG |  |  | 2017-08-14
362b | -- | 362 | 3176 | 83252 | 3200500500000 | 10 | Armstrong | BURRELL TWP-E OF BRICK CH | SR2005 | TRIB TO CHERRY RUN | 03/204 - BURRELL | 40.6885 | -79.4279 | Gas | EQT Production (Carnegie Natural Gas Co) | George Pozzuto, 412-395-3127, gpozzuto@eqt.com | Marked. 3" and 2" near the project area. Please see the utility map located in the onecall folder for the bridge in sharepoint | UG | 2" and 3" |  | 2017-08-14
362c | -- | 362 | 3176 | 83252 | 3200500500000 | 10 | Armstrong | BURRELL TWP-E OF BRICK CH | SR2005 | TRIB TO CHERRY RUN | 03/204 - BURRELL | 40.6885 | -79.4279 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-08-14
363a | -- | 363 | 3232 | 74202 | 3204701200000 | 10 | Armstrong | ROARING RUN | SR2047 | ROARING RUN | 03/210 - KISKIMINETAS | 40.5769 | -79.5012 | Comm | Comcast Cable Communications, Inc. | Gary Barnett, gary_barnett@cable.comcast.com | Field Marked. | UG |  |  | 2017-05-30
363b | -- | 363 | 3232 | 74202 | 3204701200000 | 10 | Armstrong | ROARING RUN | SR2047 | ROARING RUN | 03/210 - KISKIMINETAS | 40.5769 | -79.5012 | Gas | KRIEBEL MINERALS INC | Barbara Flinspach, Bflinspach@kriebelgas.com, 814-226-4160 x130 | Conflict. Lines Nearby. we do have natural gas lines in the area you are working in. However, I do not believe your work will affect our lines. Please see the map located In the one call folder for the bridge in sharepoint. | UG |  |  | 2017-05-30
363c | -- | 363 | 3232 | 74202 | 3204701200000 | 10 | Armstrong | ROARING RUN | SR2047 | ROARING RUN | 03/210 - KISKIMINETAS | 40.5769 | -79.5012 | Gas | PEOPLES NATURAL GAS COMPANY LLC | Michelle Saxion, 412-208-7239 | Field Marked. Please see map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-05-30
364a | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | gas | Peoples Gas Company | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Clear No Conflict. Marked on 12/30/14. Nearest facility is an Equitable Gas pipeline that crosses Airport Road approximately 280’ north west of Carnahan Run. Based on this information we are not involved with the above project | UG |  |  | 2016-05-20
364b | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | sanitary | Parks Twp Municipal Auth | Peter Massetto, 724-567-7301, ptma@verizon.net | Clear No Conflict | UG |  |  | 2016-05-20
364c | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | wtr | Parks Twp Municipal Auth | Peter Massetto, 724-567-7301, ptma@verizon.net | Marked 12/29/14. 8" Duct Iron, concrete encased in stream | UG |  |  | 2016-05-20
364d | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | Elect | West Penn Power Company | Dennis Preus, dpreus@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-05-20
364e | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | Comm | Verizon North LLC | Barbara Witkowski, barb.witkowski@verizon.com | Not Affected | OH |  |  | 2016-05-20
364f | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | Comm | Comcast | John Radeshak, O: 724-212-7236, C: 412-352-5769, John_Radeshak@cable.comcast.com Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | Possible conflict | OH |  |  | 2016-05-20
365a | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | Comm | WINDSTREAM | Daniel Lingenfelter, (724)543-7286, Daniel.Lingenfelter@windstream.com | DID NOT RESPOND | OH |  |  | 2016-05-20
365b | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | Comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com | Clear No Conflict | OH |  |  | 2016-05-20
365c | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | Elect | West Penn Power Company | Troy Bruner, 724-548-3547, tbruner@firstenergycorp.com Zach Reedy, (724) 548-3578, zreedy@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-05-20
365d | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | Gas | Peoples TWP LLC/TW Phillips | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked. 12/26/14 | UG |  |  | 2016-05-20
365f | -- | 365 | [11 empty] | Comm | Comcast | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com |  | OH |  |  | 2016-05-20
365g | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | sanitary | West Franklin TWP | Dave Johns, 724-297-5312, westfranklinwo@aim.com | Marked. 1/6/15 | UG |  |  | 2016-05-20
365h | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | wtr | Worthington W Franklin JT Muni Auth | Dave Johns, 724-297-5630, westfranklin@aol.com | Marked. 12/29/14 | UG |  |  | 2016-05-20
366a | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | S.R. 3013 Sta. 145+00 to 147+35 Rt | UG |  | NOT AFFECTED | 2015-07-27
366b | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | S.R. 3013 Sta. 147+35 to Sta. 147+45 Lt | UG |  | NOT AFFECTED | 2015-07-27
366c | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | S.R. 3013 Sta. 147+45 to Sta. 148+80 Lt | UG |  | CONDITIONAL RESTRICTION | 2015-07-27
366d | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | S.R. 3013 Sta. 148+80 to 154+00 Rt./Lt | UG |  | NOT AFFECTED | 2015-07-27
366e | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chris Robinson, 1-800-521-0570 x 2181, crobinson@central.coop | S.R. 3013, Sta. 144+21 to Sta. 151+85.9 Lt | OH |  | Coordinated | 2015-07-27
366f | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chris Robinson, 1-800-521-0570 x 2181, crobinson@central.coop | S.R. 3013, Sta. 144+21 to Sta. 151+85.9 Lt. | OH |  | Coordinated | 2015-07-27
367a | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | Elect | WEST PENN POWER COMPANY | Kevin Baker, 724-548-3538, kbaker2@firstenergycorp.com | SR 3017, Sta. 1143+18 to Sta. 1150+37.18 Rt. /Lt | OH |  | Coordinated | 2015-08-10
367b | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | Gas | PEOPLES NATURAL GAS COMPANY LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | SR 3017, Sta. 1144+00 to Sta. 1150+25 Rt. /Lt. | UG |  | RESTRICTIVE | 2015-08-10
367c | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | Wtr | KITTANNING SUBURBAN JOINT WATER AUTHORITY | Michael Moore, 412-767-5100, mmoore@banksonengineers.com | SR 3017, Sta. 1144+86.5 to Sta. 1150+03 Rt. | UG |  | INCORPORATED | 2015-08-10
367d | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | SS | WEST HILLS AREA WATER POLLUTION AUTH | Corey S. Heller, 724-545-9126 | SR 3017, Sta. 1147+27 Rt. & Sta. 1149+05 Rt | UG |  | INCORPORATED | 2015-08-10
367e | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kirk Myers, 724-543-7285, Kirk.Myers@windstream.com | SR 3017, Sta. 1143+18 to Sta. 1150+37.18 Rt./Lt | OH |  | RESTRICTIVE | 2015-08-10
367f | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | TV | COMCAST CABLE CORPORATION | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com | SR 3017, Sta. 1143+18 to Sta. 1150+37.18 Rt./Lt | OH |  | RESTRICTIVE | 2015-08-10
367g | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | Comm | ZAYO | John Lynch, 724-850-6241, john.lynch@zayo.com | SR 3017, Sta. 1143+18 to Sta. 1150+37.18 Rt./Lt | OH |  | RESTRICTIVE | 2015-08-10
368a | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 | gas | Peoples Gas Valley Division | Michelle Saxion, 412-208-7239 | Marked. Follow up letter stated that they do not have facilities within the project area. | UG |  |  | 2017-03-01
368b | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 |  | West Kittanning B/West Kittanning MA | 724-548-4740 | DID NOT RESPOND | UG |  |  | 2017-03-01
368c | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-03-01
368d | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Chad Shepherd, 724-733-3295, chad.e.shepherd@windstream.com | Aerial fiber and copper lines that cross 28 and 422 east of Freeport Rd. Please see utility map located in the onecall folder for the bridge in sharepoint. | OH |  |  | 2017-03-01
369a | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | SS | WESTERN BUTLER COUNTY AUTHORITY | Paul J. Kremer, 724 452-5501, wbca@zoominternet.net | S.R. 0068, Sta. 578+44.30 | UG | 12 | Not Affected | 2016-06-07
369b | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | S.R. 0068, Sta. 579+85 Rt | UG |  | Not Affected | 2016-06-07
369c | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | Wtr | ZELIENOPLE BOROUGH | Jill Ann Stedina, 724-452-6610 ext. 233 or Tom Thompson 724-662-2402 | S.R. 0068, Sta. 577+645 Lt | UG | 8 | Prior | 2016-06-07
369d | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | Elect | ARMSTRONG | Michael Cratty, 724-452-5695, mcratty@agoc.com | S.R. 0068, Sta. 576+50 to Sta. 580+50 Lt. | OH |  | RESTRICTIVE | 2016-06-07
369e | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | Comm | VERIZON | Jim Garrett, 724-698-4202, james.garrett@rjetelecom.com | SR 68 | OH |  | RESTRICTIVE | 2016-06-07
369f | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | Comm | VERIZON | Jim Garrett, 724-698-4202, james.garrett@rjetelecom.com | S.R. 0068, Sta. 575+63, 16 ½ to Sta. 580+60, 24 Rt./Lt | OH |  | RESTRICTIVE | 2016-06-07
369g | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | Elect | ZELIENOPLE BOROUGH | Jill Ann Stedina, 724-452-6610 ext. 233 or Ed Sullivan, 412-781-1344, esullivan@quad3.com | S.R. 0068, Sta. 575+63.12 to Sta. 580+60.3 Rt./Lt | OH |  | RESTRICTIVE | 2016-06-07
369h | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | Elect | ZELIENOPLE BOROUGH | Jill Ann Stedina, 724-452-6610 ext. 233 or Ed Sullivan, 412-781-1344, esullivan@quad3.com | S.R. 0068, Sta. 575+63.12 to Sta. 580+60.3 Rt./Lt | OH |  | Coordinated | 2016-06-07
370 | -- | 370 | 7925 | 24757 | 10030800801195 | 10 | Butler | RIDER CHURCH | LR10056,SR0308 | TRIB TO STONY RUN | 10/205 - CENTER | 40.9514 | -79.9002 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-05-30
371a | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Gas | PEOPLES TWP LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | S.R. 0356, Sta. 131+25 Lt. to Sta. 132+62 Lt | UG | 6 | RESTRICTIVE | 2015-08-31
371b | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Gas | PEOPLES TWP LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | S.R. 0356, Sta. 131+60 Rt. to Sta. 132+63 Rt | UG | 4 | RESTRICTIVE | 2015-08-31
371c | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | S.R. 0356, Sta. 131+84, 23.26’ offset Rt | OH |  | Coordinated | 2015-08-31
371d | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | S.R. 0356, Sta. 133+69.09, 31.47’ offset Rt | OH |  | Coordinated | 2015-08-31
371e | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | S.R. 0356, Sta. 135+55, 35.00’ offset Rt | OH |  | Coordinated | 2015-08-31
371f | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chris Robinson, 1-800-521-0570 x2181, crobinson@central.coop or Jeff Fleming, 800-521-0570 ext. 2196 | S.R. 0356, Sta. 131+84 to Sta. 135+55 Rt | OH |  | Coordinated | 2015-08-31
371g | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | S.R. 0356, Sta. 133+69 Rt. & Sta. 135+54 Rt. & Sta. 135+55 Rt | OH |  | Coordinated | 2015-08-31
371h | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | Comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com | SR 356 Sta. 133+69 Rt. & Sta. 135+54 Rt. & Sta. 135+55 Rt | OH |  | Coordinated | 2015-08-31
372 | -- | 372 | 8016 | 24779 | 10102500100211 | 10 | Butler | RINGNECK | SR1025 | BONNIE BROOK | 10/228 - SUMMIT | 40.867 | -79.8292 |  | all facilities responded clear per one call | [5 empty] | 2017-06-01
373a | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | S.R. 2007, Sta. 11+00 to Sta. 12+30 Lt | UG |  | Not Affected | 2015-06-22
373b | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | S.R. 2007, Utility to relocate 6” gas line from Sta. 11+50 Lt. to Sta. 12+50 Lt | UG |  | RESTRICTIVE | 2015-06-22
373c | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | S.R. 2007, Utility to relocate 6” gas line from Sta. 12+70 Lt. to Sta. 13+50 Lt | UG |  | RESTRICTIVE | 2015-06-22
373d | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | S.R. 2007 Utility has 6” gas line from Sta. 12+00 Lt to Sta. 12+70 Lt | UG |  | NOT AFFECTED | 2015-06-22
373e | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | Comm | CONSOLIDATED COMMUNICATIONS | Gabe White, 724-443-9832, gabe.white@consolidated.com or Jeff Hall, telephone 724-443-9639 | S.R. 2007, Sta. 10+12 to Sta. 12+55 Rt. / Lt. | OH |  | Prior | 2015-06-22
373f | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | Comm | CONSOLIDATED COMMUNICATIONS | Gabe White, 724-443-9832, gabe.white@consolidated.com or Jeff Hall, telephone 724-443-9639 | S.R. 2007, Sta. 10+05 to Sta. 12+55 Rt./ Lt | OH |  | Prior | 2015-06-22
373g | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | TV | COMCAST CABLE CORPORATION | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | S.R. 2007 Sta. 11+25 to 13+95 Rt./Lt | OH |  | Prior | 2015-06-22
373h | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | Elect | WEST PENN POWER COMPANY | Rick Hobbins, 724-334-5237, rhobbin@firstenergycorp.com | S.R. 2007 Sta. 11+25 Rt. and Sta. 13+95 Rt | OH |  | RESTRICTIVE | 2015-06-22
374 | -- | 374 | 8061 | 83332 | 10300400300433 | 10 | Butler | MCCALMONT NO.1 | SR3004 | CONNOQUENESSING CR | 10/101 - BUTLER | 40.8194 | -79.9457 |  | all facilities responded clear per one call | [5 empty] | 2016-08-05
375a | -- | 375 | 8071 | 24703 | 10301000600000 | 10 | Butler | BROWNSDALE ROAD | SR3010 | GLADE RUN | 10/215 - FORWARD | 40.7786 | -80.0096 | gas | Peoples TWP LLC/TW Phillips | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Conflict. Lines Nearby. | UG |  |  | 2016-07-18
375b | -- | 375 | 8071 | 24703 | 10301000600000 | 10 | Butler | BROWNSDALE ROAD | SR3010 | GLADE RUN | 10/215 - FORWARD | 40.7786 | -80.0096 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2016-07-18
375c | -- | 375 | [11 empty] | Comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com | Possible Conflict. Did Not Respond |  |  |  | 2016-07-18
375d | -- | 375 | [11 empty] | Comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | Possible Conflict. Did Not Respond |  |  |  | 2016-07-18
376a | Y | 376 | 8073 | 83335 | 10301200500000 | 10 | Butler | CRUIKSHANK ROAD | LR10013,SR3012 | TRIB TO GLADE RUN | 10/222 - MIDDLESEX | 40.7394 | -79.9596 | Elect | ARMSTRONG | Michael Cratty, 724-452-5695 | S.R. 3012, Utility has facilities outside of the project limits | OH |  | Not Affected | 2015-06-24
376b | Y | 376 | 8073 | 83335 | 10301200500000 | 10 | Butler | CRUIKSHANK ROAD | LR10013,SR3012 | TRIB TO GLADE RUN | 10/222 - MIDDLESEX | 40.7394 | -79.9596 | Elect | WEST PENN POWER COMPANY | Rick Hobbins, 724-334-5237 | S.R. 3012, Utility has facilities outside of the project limits | OH |  | Not Affected | 2015-06-24
377a | -- | 377 | 8104 | 77989 | 10302700500194 | 10 | Butler | SENACA SCHOOL | SR3027 | LIT CONNOQUENESSING CR | 10/217 - JACKSON | 40.8102 | -80.1082 | gas | PEOPLES NATURAL GAS COMPANY LLC | Christopher (Chris) Carlisle, christopher.carlisle@peoples-gas.com, 412-398-4543 | Please see map located in the one call folder for the bridge in sharepoint | UG |  |  | 2017-03-06
377b | -- | 377 | 8104 | 77989 | 10302700500194 | 10 | Butler | SENACA SCHOOL | SR3027 | LIT CONNOQUENESSING CR | 10/217 - JACKSON | 40.8102 | -80.1082 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Please see map located in the one call folder for the bridge in sharepoint. It doesn’t appear that the utilities will be in conflict with the bridge project. | Both |  |  | 2017-03-06
378 | -- | 378 | 8113 | 89967 | 10400201302768 | 10 | Butler | SOUTH OF QUEEN JCT. | SR4002 | B & LE RR | 10/207 - CLAY | 40.9603 | -79.9313 | comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | Marked 12/26/14 | Both |  |  | 2017-03-16
378 | -- | 378 | 8113 | 89967 | 10400201302768 | 10 | Butler | SOUTH OF QUEEN JCT. | SR4002 | B & LE RR | 10/207 - CLAY | 40.9603 | -79.9313 | comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com | Conflict. Lines Nearby | OH |  |  | 2017-03-16
379a | -- | 379 | 8334 | 24710 | 10800505000898 | 10 | Butler | ROCK LAKE SB RAMP NO.2 | SR8005 SB (RAMP F) | SR0019 NB | 10/217 - JACKSON | 40.7734 | -80.1304 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | DID NOT RESPOND |  |  |  | 2017-04-11
379b | -- | 379 | 8334 | 24710 | 10800505000898 | 10 | Butler | ROCK LAKE SB RAMP NO.2 | SR8005 SB (RAMP F) | SR0019 NB | 10/217 - JACKSON | 40.7734 | -80.1304 | sanitary | WESTERN BUTLER COUNTY AUTHORITY | Autumn Heckathorn, wbca@zoominternet.net | Marked. Sanitary line crosses I-79 exit ramp. Please see utility plans located in the onecall folder for the bridge on sharepoint. | UG |  |  | 2017-04-11
379c | -- | 379 | 8334 | 24710 | 10800505000898 | 10 | Butler | ROCK LAKE SB RAMP NO.2 | SR8005 SB (RAMP F) | SR0019 NB | 10/217 - JACKSON | 40.7734 | -80.1304 | gas | Peoples Gas (Equitable Gas) | Chris Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | work site is in the vicinity of a very high pressure transmission line, proceed with extreme caution before performing any work. There are various restrictions when working near such a line. Please see utility plans located in the onecall folder for the bridge on sharepoint. | UG |  |  | 2017-04-11
380a | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | gas | Gas City Oil and Gas Corp | John Exley, neigroup@aol.com | CLEAR - NO FACILITIES * 05/14/2015 01:41:50 |  |  |  | 2016-04-18
380b | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 |  | Northeastern ITS | Dana T. Costa Jr., O: (937)-309-0470, C: (513)-254-4348, dana.costa@spreadnetworks.com | 3 – 1 ½” HDPE ducts and one has a 432 fiber cable in it. The fiber is located on the south side of SR 322. Please see utility plans located in the onecall folder for the bridge on sharepoint. | UG |  |  | 2016-04-18
380c | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com | Clear No Conflict. | OH |  |  | 2016-04-18
380d | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | gas | Pine Roe Natural Gas Co | John Habjan, 814-227-2611 | DID NOT RESPOND | UG |  |  | 2016-04-18
380e | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | Comm | ZAYO | John Lynch, 724-850-6241, 724-972-5667 john.lynch@zayo.com | Clear No Conflict. | UG |  |  | 2016-04-18
380f | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | Comm | ARMSTRONG | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Clear No Conflict. | UG |  |  | 2016-04-18
381a | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | Comm | Comcast Cable Communications, Inc. | Doug Olszewski, 724-459-9042, Douglas_Olszewski@cable.comcast.com | Conflict. Lines Nearby. | OH |  |  | 2016-04-20
381b | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 |  | Madison TWP Clarion Co | Denny Montgomery, 814-473-6307 | DID NOT RESPOND | UG |  |  | 2016-04-20
381c | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2016-04-20
381d | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | Comm | ARMSTRONG | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Clear No Conflict | OH |  |  | 2016-04-20
381e | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | Comm | AT&T Local Services | Ford McLean, 412-979-4455, fmclean@att.com | DID NOT RESPOND | OH |  |  | 2016-04-20
381f | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chad Master, 1-800-521-0570 x2199, cmaster@central.coop Chris Robinson, 1-800-521-0570 x 2191, crobinson@central.coop | Conflict. Lines Nearby | OH |  |  | 2016-04-20
381g | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | Comm | WINDSTREAM COMMUNICATIONS | Tom Gerg, 814-849-3552, tom.gerg@windstream.com | Conflict. Lines Nearby | UG |  |  | 2016-04-20
382a | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | Comm | Comcast | Doug Olszewski, 724-459-9042, Douglas_Olszewski@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | ? | UG |  |  | 2016-05-25
382b | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 |  | Madison TWP Clarion Co | Denny Montgomery, 814-473-8162, madison_twp@windstream.net | ? | OH |  |  | 2016-05-25
382c | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com | National Fuel does not have any active facilities within 15 of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2016-05-25
382d | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | Comm | ARMSTRONG | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Clear No Conflict | 0 |  |  | 2016-05-25
382e | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chad Master, 1-800-521-0570 x2199, cmaster@central.coop Chris Robinson, 1-800-521-0570 x 2191, crobinson@central.coop | Conflict. Lines Nearby | 0 |  |  | 2016-05-25
383a | -- | 383 | 11042 | 25221 | 16200900100000 | 10 | Clarion | LAWSONHAM NO.1 | SR2009 | REDBANK CREEK | 16/211 - MADISON | 40.995 | -79.4857 | Comm | WINDSTREAM COMMUNICATIONS | Tom Gerg, 814-849-3552, tom.gerg@windstream.com | Conflict. Lines Nearby | UG |  |  | 2017-05-11
383b | -- | 383 | 11042 | 25221 | 16200900100000 | 10 | Clarion | LAWSONHAM NO.1 | SR2009 | REDBANK CREEK | 16/211 - MADISON | 40.995 | -79.4857 | Comm | Comcast Cable Communications, Inc. | Gary Barnett, gary_barnett@cable.comcast.com | Conflict. Lines Nearby. |  |  |  | 2017-05-11
383c | -- | 383 | 11042 | 25221 | 16200900100000 | 10 | Clarion | LAWSONHAM NO.1 | SR2009 | REDBANK CREEK | 16/211 - MADISON | 40.995 | -79.4857 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-05-11
384a | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 |  | Licking TWP | 814-358-2250, lickingtwp@windstream.net, 152 Canoe Ripple Road Sligo, PA 16255 | Did Not Respond |  |  |  | 2017-03-20
384b | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 | Gas | UGI Central Penn Gas | Roy Carr (570) 829-8967 | Did Not Respond | UG |  |  | 2017-03-20
384c | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 | Elect | Pennsylvania Electric Company | John Forbes, 814-676-7551, jforbes@firstenergycorp.com | Clear No Conflict | Both |  |  | 2017-03-20
384d | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 | gas | UGI CENTRAL PENN GAS | Roy Carr, 570-829-8967, rcarr@ugi.com, ANDREW BLACK, ABLACK@UGI.COM | Clear No Conflict | Both |  |  | 2017-03-20
384e | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 | Comm | WINDSTREAM COMMUNICATIONS | Tom Gerg, 814-849-3552, tom.gerg@windstream.com | Conflict. Lines Nearby | Both |  |  | 2017-03-20
385a | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | Comm | ARMSTRONG | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com | Clear No Conflict | OH |  |  | 2017-05-26
385b | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chad Master, 1-800-521-0570 x2199, cmaster@central.coop Chris Robinson, 1-800-521-0570 x 2191, crobinson@central.coop | Conflict. Lines Nearby | OH |  |  | 2017-05-26
385c | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | Gas | UGI Central Penn Gas | Roy Carr (570) 829-8967 | Did Not Respond. | UG |  |  | 2017-05-26
385d | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | Comm | Verizon | Cindy Oberholtzer, coberholtzer@usceng.com | Field Marked. Please see maps and email located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-05-26
385e | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | National Fuel does not have any active facilities within 15? of the described work area. There may be abandoned gas lines in the described work area. Contact National Fuel if such gas lines are damaged or require removal. | UG |  |  | 2017-05-26
386a | -- | 386 | 19087 | 83293 | 32028601500520 | 10 | Indiana | CLARKSBURG NO.3 | SR0286 | BLACKLEGS CREEK | 32/224 - YOUNG | 40.5371 | -79.3754 | wtr | Indiana County Municipal Services Authority | Dan Fmura, Gibson-Thomas Engineering Co, Inc, dan.fmura@gibson-thomas.com, 724-539-8562 | Field Marked. Please see as-builts and email located in the onecall folder in sharepoint for the bridge. | UG |  |  | 2017-05-22
386b | -- | 386 | 19087 | 83293 | 32028601500520 | 10 | Indiana | CLARKSBURG NO.3 | SR0286 | BLACKLEGS CREEK | 32/224 - YOUNG | 40.5371 | -79.3754 |  | KASTLE RESOURCES ENTERPRISES INC | Jesse Welcheck, 814-602-6231, jwelcheck25@gmail.com | Did not respond through one call |  |  |  | 2017-05-22
386c | -- | 386 | 19087 | 83293 | 32028601500520 | 10 | Indiana | CLARKSBURG NO.3 | SR0286 | BLACKLEGS CREEK | 32/224 - YOUNG | 40.5371 | -79.3754 | Gas | Peoples Gas (Equitable Gas) | Michelle Saxion, 412-208-7239 | Have facilities near design one call site. Please map located in the one call folder in sharepoint for the bridge. | UG |  |  | 2017-05-22
387 | -- | 387 | 19183 | 95851 | 32055302000620 | 10 | Indiana | ALVERDA NO.2 | SR0553 | DUTCH RUN | 32/217 - PINE | 40.6265 | -78.8533 |  | all facilities responded clear per one call | [5 empty] | 2016-06-24
388a | -- | 388 | 19200 | 25780 | 32095403700000 | 10 | Indiana | WILLET | SR0954 | SOUTH BRANCH PLUM CREEK | 32/220 - WASHINGTON | 40.7287 | -79.2014 | Elect | Pennsylvania Electric Company | Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com | Clear. No Conflict |  |  |  | 2016-05-20
388b | -- | 388 | 19200 | 25780 | 32095403700000 | 10 | Indiana | WILLET | SR0954 | SOUTH BRANCH PLUM CREEK | 32/220 - WASHINGTON | 40.7287 | -79.2014 |  | XTO Energy Inc/Mountain Gathering LLC | Jerry Ondrizek, 412-585-2828, jerry_ondrizek@xtoenergy.com Derek Folmer, 724-772-9594, derek_folmer@xtoenergy.com | Not Affected. Clear of bridge. the Northeast end of the bridge pipeline is 60 feet from the side of the bridge. On the Southwest end of the bridge pipe line is 48 feet from the side of the bridge |  |  |  | 2016-05-20
389a | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | Gas | XTO Energy Inc/Mountain Gathering LLC | Jerry Ondrizek, 412-585-2828, jerry_ondrizek@xtoenergy.com Derek Folmer, 724-772-9594, derek_folmer@xtoenergy.com | DID NOT RESPOND | UG |  |  | 2016-07-26
389b | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | Gas | PEOPLES NATURAL GAS COMPANY LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Have facilities near design one call site. Please map located in the one call folder in sharepoint for the bridge. | UG |  |  | 2016-07-26
389c | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | Elect | West Penn Power Company | Zach Reedy, (724) 548-3578, zreedy@firstenergycorp.com | DID NOT RESPOND | OH |  |  | 2016-07-26
389d | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | DID NOT RESPOND | OH |  |  | 2016-07-26
389e | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | Comm | Comcast | Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | DID NOT RESPOND | OH |  |  | 2016-07-26
389f | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 |  | REA Energy Cooperative Inc | Chris Masterson, cmasterson@reaenergy.com | DID NOT RESPOND | OH |  |  | 2016-07-26
390a | -- | 390 | 19392 | 78120 | 32401000100530 | 10 | Indiana | KIMMEL RD NO.1 | SR4010 | CROOKED CREEK | 32/218 - RAYNE | 40.7137 | -79.1285 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com. Email him first and he will verify if that is area or get you to the right person | DID NOT RESPOND |  |  |  | 2017-05-11
390b | -- | 390 | 19392 | 78120 | 32401000100530 | 10 | Indiana | KIMMEL RD NO.1 | SR4010 | CROOKED CREEK | 32/218 - RAYNE | 40.7137 | -79.1285 | gas | Peoples TWP LLC/TW Phillips | Mike Shearer, 724-287-2751, mike.shearer@peoplestwp.com | Marked. Gas main crosses Kimmell Road south of project area. Please see utility map located in the onecall folder for the bridge on sharepoint. The map does not depict individual customer service lines. | UG |  |  | 2017-05-11
391a | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | Gas | KRIEBEL MINERALS INC | Barbara Flinspach, 814-226-4160 ext 130, bflinspach@kriebelgas.com James Brant, 814-221-4160, Jbrant@kriebelgas.com | Clear No Conflict | UG |  |  | 2016-06-08
391b | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | Wtr | Pennsylvania American Water Company | Jed Fiscus, 814-226-9803, jed.fiscus@amwater.com | Marked. | UG |  |  | 2016-06-08
391c | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | gas | Peoples TWP LLC/TW Phillips | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked. Gas main runs parallel to PA36 at project area. Please see utility map located in the onecall folder for the bridge on sharepoint. The map does not depict individual customer service lines. | UG |  |  | 2016-06-08
391d | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | Elect | Pennsylvania Electric Company | Marty Kerch, 814-269-6773, mkerch@firstenergycorp.com | Conflict. Lines Nearby | UG |  |  | 2016-06-08
391e | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | Comm | VERIZON PENNSYLVANIA LLC | John Grech, 814-375-7504, john.m.grech@verizon.com | DID NOT RESPOND | UG |  |  | 2016-06-08
391f | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | Elect | United Electric Cooperative | Brenda Swartzlander, 814-371-8570 x3158, bswartzlander@unitedpa.com | DID NOT RESPOND | UG |  |  | 2016-06-08
392a | -- | 392 | 19699 | 83312 | 33200300700000 | 10 | Jefferson | FOXBURG | SR2003 | MAHONING CREEK | 33/401 - BIG RUN | 40.9642 | -78.8798 | sanitary | Big Run Area Municipal Authority | 814-427-5091 | Field Marked. | UG |  |  | 2017-05-30
392b | -- | 392 | 19699 | 83312 | 33200300700000 | 10 | Jefferson | FOXBURG | SR2003 | MAHONING CREEK | 33/401 - BIG RUN | 40.9642 | -78.8798 | gas | Peoples TWP LLC/TW Phillips | Jim Shaffer, 724-286-9010, John Carr, John.Carr@peoples-gas.com, 724-431-4985 | Conflict. Lines Nearby. Please see utility map and email located in onecall folder for bridge in sharepoint . | UG |  |  | 2017-05-30
392c | -- | 392 | 19699 | 83312 | 33200300700000 | 10 | Jefferson | FOXBURG | SR2003 | MAHONING CREEK | 33/401 - BIG RUN | 40.9642 | -78.8798 | Comm | Comcast Cable Communications, Inc. | David Bowen, 800-892-7300 | Conflict. Lines Nearby. |  |  |  | 2017-05-30
393 | -- | 393 | 19708 | 26151 | 33200802100200 | 10 | Jefferson | STUMP CREEK NO.2 | SR2008 | STUMP CREEK (CROSSING @ LOW) | 33/208 - HENDERSON | 41.0137 | -78.8303 | gas | Peoples TWP LLC/TW Phillips | Jim Shaffer, 724-286-9010, John Carr, John.Carr@peoples-gas.com, 724-431-4985 | Conflict. Lines Nearby. Please see utility map and email located in onecall folder for bridge in sharepoint . | UG |  |  | 2017-07-24
394a | -- | 394 | 19737 | 26069 | 33300302500000 | 10 | Jefferson | NEAR OHL NO. 1 | SR3003 | BEAVER RUN | 33/202 - BEAVER | 41.0894 | -79.1532 |  | Beaver TWP | 324 Tippecanoe Road Knox, PA 16232. 814-797-1408, beavertownship@windstream.net, hours M,TUE,F 9-3pm | Did not respond. |  |  |  | 2017-05-26
394b | -- | 394 | 19737 | 26069 | 33300302500000 | 10 | Jefferson | NEAR OHL NO. 1 | SR3003 | BEAVER RUN | 33/202 - BEAVER | 41.0894 | -79.1532 | GAS | National Fuel Supply/National Fuel Brook | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | Design Conflict. National Fuel has facilities in the area of your One Call Design Request. Forward design drawings to James Kennedy, Engineering Dept. 6363 Main Street, Williamsville, NY 14221, Email: KennedyJ@natfuel.com, Fax: (716) 857-7456 or call (716) 857-7368. | UG |  |  | 2017-05-26
394c | -- | 394 | 19737 | 26069 | 33300302500000 | 10 | Jefferson | NEAR OHL NO. 1 | SR3003 | BEAVER RUN | 33/202 - BEAVER | 41.0894 | -79.1532 | gas | Peoples TWP LLC/TW Phillips | Jim Shaffer, 724-286-9010, John Carr, John.Carr@peoples-gas.com, 724-431-4985 | Conflict. Lines Nearby. Please see utility map and email located in onecall folder for bridge in sharepoint . | UG |  |  | 2017-05-26
395a | -- | 395 | 19807 | 83343 | 33400100700000 | 10 | Jefferson | NORTH OF ROSEVILLE | SR4001 | MILL CREEK | 33/219 - UNION | 41.2136 | -79.1473 |  | Union TWP Jefferson Township | David Mathies (secy) 724-348-4250 | Did Not Respond. |  |  |  | 2017-05-26
395b | -- | 395 | 19807 | 83343 | 33400100700000 | 10 | Jefferson | NORTH OF ROSEVILLE | SR4001 | MILL CREEK | 33/219 - UNION | 41.2136 | -79.1473 |  | Eldred TWP Municipal Authority | 814-752-2881 | Did Not Respond. |  |  |  | 2017-05-26
395c | -- | 395 | 19807 | 83343 | 33400100700000 | 10 | Jefferson | NORTH OF ROSEVILLE | SR4001 | MILL CREEK | 33/219 - UNION | 41.2136 | -79.1473 | GAS | National Fuel Supply/National Fuel Brook | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | Design Conflict. National Fuel has facilities in the area of your One Call Design Request. Forward design drawings to James Kennedy, Engineering Dept. 6363 Main Street, Williamsville, NY 14221, Email: KennedyJ@natfuel.com, Fax: (716) 857-7456 or call (716) 857-7368. | UG |  |  | 2017-05-26
396a | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | sanitary | Richland TWP | Jerry Reichart, 724-4443-5921, JREICHART@RICHLAND.PA.US | Marked. | UG |  |  | 2016-07-11
396b | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | GAS | Peoples Gas Design Gibsonia | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Gas Main running parallel to PA-8 (WM Flynn HWY) on east side. Please see field maps located in the one call folder in sharepoint for this bridge. | UG |  |  | 2016-07-11
396c | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | Comm | Consolidated Communications | Jeff Hall, 724-443-9639, Jeff.Hall@consolidated.com Gabe White, 724-443-9832, gabe.white@consolidated.com | Conflict. Lines Nearby | Both |  |  | 2016-07-11
396d | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-07-11
396e | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com | DID NOT RESPOND | OH |  |  | 2016-07-11
396f | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | Comm | ARMSTRONG | Michael Cratty, 724-452-5695, mcratty@agoc.com | DID NOT RESPOND | OH |  |  | 2016-07-11
396g | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | Comm | Verizon | Gary Redondo, 412-667-8618, gary.redondo@verizon.com | DID NOT RESPOND | OH |  |  | 2016-07-11
396h | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | DID NOT RESPOND | OH |  |  | 2016-07-11
397a | -- | 397 | 659 | 27272 | 2003001202263 | 11 | Allegheny | 400 FEET SE OF SR 3070 | LINCOLN HW | SOUTH FORK MONTOUR RUN | 02/214 - NORTH FAYETTE | 40.45 | -80.2504 | Wtr | Findlay Township Municipal Authority | Jason Orsini, 724-695-3108, jason@ftmunauth.com | Not Affected. 8” AC waterline that stops shortly after that hydrant (coming from the West heading East | UG |  |  | 2016-05-20
397b | -- | 397 | 659 | 27272 | 2003001202263 | 11 | Allegheny | 400 FEET SE OF SR 3070 | LINCOLN HW | SOUTH FORK MONTOUR RUN | 02/214 - NORTH FAYETTE | 40.45 | -80.2504 | SS | Findlay Township Municipal Authority | Jason Orsini, 724-695-3108, jason@ftmunauth.com | Not Affected. SS outside construction area | UG |  |  | 2016-05-20
397ac | -- | 397 | 659 | 27272 | 2003001202263 | 11 | Allegheny | 400 FEET SE OF SR 3070 | LINCOLN HW | SOUTH FORK MONTOUR RUN | 02/214 - NORTH FAYETTE | 40.45 | -80.2504 | gas | Peoples Gas of Hopewell Division | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked 1/23/15. Please see field maps located in the one call folder in sharepoint for this bridge. | UG |  |  | 2016-05-20
397d | -- | 397 | 659 | 27272 | 2003001202263 | 11 | Allegheny | 400 FEET SE OF SR 3070 | LINCOLN HW | SOUTH FORK MONTOUR RUN | 02/214 - NORTH FAYETTE | 40.45 | -80.2504 | Wtr | NORTH FAYETTE TOWNSHIP | PATRICK FELTON , pfelton@north-fayette.com | Clear No Conflict | UG |  |  | 2016-05-20
397e | -- | 397 | 659 | 27272 | 2003001202263 | 11 | Allegheny | 400 FEET SE OF SR 3070 | LINCOLN HW | SOUTH FORK MONTOUR RUN | 02/214 - NORTH FAYETTE | 40.45 | -80.2504 | Elect | West Penn Power | Scott Curcio, 724-796-1021, scurcio@firstenergycorp.com | Clear No Conflict. Phone Call 8/13/15 | OH |  |  | 2016-05-20
398a | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | Clear No Conflict | UG |  |  | 2016-09-02
398b | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 |  | Forest Hills Borough | Steve Morus (manager/secy), 412-351-7330 | Marked. | UG |  |  | 2016-09-02
398c | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 | Gas | Peoples Gas Pittsburgh Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Conflict. Lines Nearby. Main on south side of ardmore that ties into a main running north-south on Braddock at intersection. Please see utility plans in one call folder for the bridge on sharepoint. | UG |  |  | 2016-09-02
398d | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 | wtr | Wilkinsburg Penn Joint Water Auth | Bill Grassi, 412-728-6847, Gary Melvin, 412-243-6163 | Design conflict. Please send plans to: Bill Grassi Wilkinsburg Penn Joint Water Auth 800 Ramsey Street Wilkinsburg PA 15221. 12" WM running parallel on the north side of Ardmore and a 6" WM running parallel to Ardmore on the south side running east from the intersection. 16" WM running north on Braddock that connects the 12" and 6" mains on Ardmore. The 16" reduces to 12" north of the intersection. Please see field maps located in the one call folder in sharepoint for this bridge. | UG | 6, 12, and 16" |  | 2016-09-02
399a | -- | 399 | 709 | 91923 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 |  | Forward TWP | 724-258-7895 | DID NOT RESPOND | UG |  |  | 2017-02-13
399b | -- | 399 | 709 | 91923 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | Gas | Peoples Gas Design Monongahela | Mary M. Vitalbo-Madden, 724-292-3415 | Design Conflict. Please send plans to: Design Department Peoples Natural Gas Company LLC 1291 W Main St Monongahela, PA 15063. Gas main runs south-east along SR51 and ends at the intersection with weigles hill rd. | UG |  |  | 2017-02-13
399c | -- | 399 | 709 | 91923 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | Gas | Peoples Gas Monongahela Division | Mary M. Vitalbo-Madden, 724-292-3415 | Conflict. Lines Nearby. | UG |  |  | 2017-02-13
399d | -- | 399 | 709 | 91923 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | Elect | West Penn Power | Dave Lucas, 724-838-6126 | Conflict. Lines Nearby. |  |  |  | 2017-02-13
399e | -- | 399 | 709 | 91923 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | wtr | Municipal Auth of Westmoreland Cnty | April Tilson, 724-755-5955, atilson@mawc.org | Conflict. Lines Nearby. 8" DI WM runs parallel to SR51 and crossing creek and Weigles Hill Rd. Please see utility plans located in the one call folder for the bridge in sharepoint. | UG | 8" |  | 2017-02-13
399f | -- | 399 | 709 | 91923 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 |  | Elizabeth TWP AUTH | 412-751-2880 | Marked. | UG |  |  | 2017-02-13
| R | 400 | 41065 | #REF! | 2013000420000 | 11 | Allegheny | 1 1/2 MILES E. OF PA 8 | #N/A | ABANDONED RR | 02/105 - ELIZABETH | 40.2642 | -79.8786 | [7 empty] | 2017-02-13
| R | 401 | 41066 | #REF! | 2013000420165 | 11 | Allegheny | 1 1/2 MILES E. OF PA 8 | #N/A | ABANDONED RR | 02/105 - ELIZABETH | 40.2642 | -79.8786 | [7 empty] | 2017-02-13
402a | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | GAS | Peoples Gas Company | John Walko, John.Walko@peoples-gas.com Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Conflict. Lines Nearby | UG |  |  | 2016-06-03
402b | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Aguerra, PE, daguerra@mawc.org, Chris Kerr, 724-834-6500, John P. Shuey, 1-800-887-9190, M. Curtis Fontaine, PE, fontaine@mawc.org | Marked on 1/8/15. 8" DI WM on SR 0136 and 8" WM on Rostosky Ridge Rd. See drawings located in the one call folder on sharepoint | UG | 8" |  | 2016-06-03
402c | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | Elect | West Penn Power | Christine Smith, 724-489-3237, smithc@firstenergycorp.com | Conflict. Lines nearby. | OH |  |  | 2016-06-03
402d | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | Comm | VERIZON PENNSYLVANIA LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | DID NOT RESPOND | OH |  |  | 2016-06-03
402e | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-06-03
403a | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-03-25
403b | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Incorporated Design and Construction | UG |  |  | 2016-03-25
403c | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | Comm | VERIZON PENNSYLVANIA LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-03-25
403d | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-03-25
403e | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | Conflict. Lines Nearby | OH |  |  | 2016-03-25
404a | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | sanitary | Richland TWP | Jerry Reichart, 724-4443-5921, JREICHART@RICHLAND.PA.US | Marked. | UG |  |  | 2016-06-09
404b | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | Gas | PEOPLES NATURAL GAS COMPANY LLC | George Heil, 724-444-3237, George.J.HeilIII@peoples-gas.com Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | PNG line goes around the bridge, missing the existing wing walls by 15’. | UG |  |  | 2016-06-09
404c | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | Comm | Consolidated Communications | Gabe White, 724-443-9832, gabe.white@consolidated.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-06-09
404d | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-06-09
404e | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-06-09
404f | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | Comm | ARMSTRONG | Michael Cratty, 724-452-5695, mcratty@agoc.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-06-09
405a | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR: 0910-A37-Station 99+35 to Station 102+30 | OH |  | CONDITIONAL RESTRICTION | 2016-06-27
405b | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | Comm | CONSOLIDATED COMMUNICATIONS OF PA COMPANY, LLC | Harry R Brown, 724 443-9535 or Jeff Hall, 724-443-9639 | SR: 0910-A37-Station 99+35 to Station 102+30 | OH |  | Not Affected | 2016-06-27
405c | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or Kent Norton, 724-594-0063 | SR: 0910-A37-Station 99+35 to Station 102+30 | OH |  | Not Affected | 2016-06-27
405d | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | Wtr | Oakmont Muni Auth | John Dunlap, 412-828-7220 or Jim McCaskey, 412-327-0096 | SR: 0910-A37-Station 99+35 to Station 102+30 | UG |  | Not Affected | 2016-06-27
405e | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | Wtr | SUNESYS, INC. | Dave Hayward, 267-927-2000 or Mike Coudriet, 412-462-4561X2353 | SR: 0910-A37-Station 99+35 to Station 102+30 | UG |  | Not Affected | 2016-06-27
405f | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | Unk | Deer Creek Drainage Basin | Enoch Jenkins, 724-265-5315 | SR: 0910-A37-Station 99+35 to Station 102+30 | UG |  | Not Affected | 2016-06-27
406a | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | Gas | Columbia Gas of PA Design | Dominic Tarella, dtarella@nisource.com, 724-462-3479 Stephanie Hardenstine Field Engineer Cell: 412-584-5015 Office: 412-220-1531 | Conflict. Lines Nearby | UG |  |  | 2016-03-23
406b | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | SS | South Fayette TWP Municipal Auth | Jerry Brown, (412) 257-5100, jbrown@sftwp.com | Based upon a review of the information that you forwarded to me regarding the Millers Run Road bridge replacement at Fishing Run, I see no conflict with the MATSF sanitary sewers in that vicinity. | UG |  |  | 2016-03-23
406c | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | Wtr | Pennsylvania American Water CO | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines Nearby. Please see field maps located in the one call folder in sharepoint for this bridge. | UG |  |  | 2016-03-23
406d | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | Elect | West Penn Power | Scott Curcio, 724-796-1021 scurcio@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-03-23
406e | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | Comm | Verizon | Daniel Barren, 412-633-4341, daniel.barren@1.verizon.com | Conflict. Lines Nearby. | OH |  |  | 2016-03-23
406f | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | Comm | Comcast Cable Communications, Inc. | Craig Tacy, 724-503-4362, Craig_Tacy@cable.comcast.com | Conflict. Lines Nearby. | OH |  |  | 2016-03-23
407a | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | Comm | WINDSTREAM | Dustin Velcoff, 501-748-4434, dustin.velcoff@windstream.com | UG fiber running parallel to RR over guys run. Please see utility map located in the one call folder for the bridge in sharepoint |  |  |  | 2017-02-16
407b | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 1/8/15 | UG |  |  | 2017-02-16
407c | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | Comm | AT&T Local Services | Nancy Spence, spence@ems.att.com | Conflict. Lines Nearby. |  |  |  | 2017-02-16
407d | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | sanitary | TWP of Harmar | Mike Ziencik, harmar701@comcast.net | Marked. 12/26/14 | UG |  |  | 2017-02-16
407e | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-02-16
408a | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | DID NOT RESPOND | UG |  |  | 2017-05-22
408b | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 |  | East Deer TWP | 724-224-3434 | DID NOT RESPOND | UG |  |  | 2017-05-22
408c | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 20" steel high pressure main runs parallel to Freeport at bridge. | UG | 20" |  | 2017-05-22
408d | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-05-22
408e | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona (Ann) Pilarczyk 319-790-6779, Aldona.Pilarczyk@windstream.com | Line runs parallel to Freeport on east side of road. See utility map located in the onecall folder for the bridge in sharepoint. |  |  |  | 2017-05-22
409a | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | DID NOT RESPOND | UG |  |  | 2017-04-03
409b | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 |  | East Deer TWP | 724-224-3434 | DID NOT RESPOND | UG |  |  | 2017-04-03
409c | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 12" wrought iron low pressure pipe runs parallel to freeport east of bridge | UG | 12" |  | 2017-04-03
409d | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | Gas | Peoples TWP LLC/TW Phillips | Larry Shane, 724-295-2600, Lawrence.R.Shane@peoples-gas.com | Line running parallel to bailes run rd that crosses freeport and RR. Line that runs parallel to freeport west of the bridge. Please see utility map located in the onecall folder for the bridge in sharepoint. The map doesn’t depict individual customer service lines. | UG |  |  | 2017-04-03
409e | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-04-03
409f | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | Marked. UG fiber running parallel to freeport. Please see utility map located in the one call folder for the bridge on sharepoint. | UG |  |  | 2017-04-03
410a | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | sanitary | DEER CREEK DRAINAGE BASIN AUTHORITY | Enoch Jenkins, enoch@deercreekauthority.com Chuck Debaldo (412) 913-6684 - chuck@deercreekauthority .com | Marked. | UG |  |  | 2016-07-05
410b | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | wtr | HAMPTON SHALER WATER AUTHORITY | Kevin M. Creagh, 412-486-4867, kevin.creagh@hswa-pa.org Sam Scarfone, 412-486-4867 | Conflict. Lines Nearby | UG |  |  | 2016-07-05
410b | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | Gas | Peoples Gas Company | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Possible Conflict. Did Not Respond | UG |  |  | 2016-07-05
410c | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-05
410d | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | Comm | Verizon | Gary Redondo, 412-667-8618, gary.redondo@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-05
410e | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | Comm | Consolidated Communications | Jeff Hall, 724-443-9639, Jeff.Hall@consolidated.com Gabe White, 724-443-9832, gabe.white@consolidated.com | Clear. No Conflict | OH |  |  | 2016-07-05
410f | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-05
410g | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | Comm | Comcast | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2016-07-05
411a | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | sanitary | TWP of Harmar | Mike Ziencik, 724.274.4550, harmarroad@comcast.net | Marked | UG |  |  | 2016-07-11
411b | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | wtr | Municipal Auth of Harmar TWP | Joseph R. McCollum Harmar Water Authority Ph: 724-274-8028 joemccollum@harmarwater.com | Marked. | UG |  |  | 2016-07-11
411c | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | Gas | Peoples Gas Company | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Marked. 8" steel high pressure pipe running parallel on guys run road at bridge. Please see the utility map located in the onecall folder for the bridge in sharepoint. | UG | 8" |  | 2016-07-11
411d | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-07-11
411e | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-11
411f | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | Comm | Verizon | Gary Redondo, 412-667-8618, gary.redondo@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-11
411g | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | Comm | Comcast | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-07-11
411h | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | Conflict. Lines Nearby | OH |  |  | 2016-07-11
412a | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | SS | HARMAR TOWNSHIP | Annette Dietz, 724-274-4550 | SR 1011-A03 Station 11+00 to Station 18+00 | UG |  | Incorporated | 2016-05-23
412b | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | SR 1011-A03 Station 11+00 to Station 18+00 | UG | Unk | Coordinated | 2016-05-23
412c | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | Elect | West Penn Power | Nick Ensminger, 304-534-7437 | SR 1011-A03 Station 11+00 to Station 18+00 | OH |  | Not Affected | 2016-05-23
412d | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | Tel | Verizon | Deborah D Delia, 412-633-3810 | SR 1011-A03 Station 11+00 to Station 18+00 | OH |  | Not Affected | 2016-05-23
412e | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | Wtr | HARMAR TOWNSHIP MUNICIPAL WATER AUTHORITY | Joe McCullum, 724-274-7383 | SR 1011-A03 Station 11+00 to Station 18+00 | UG |  | Incorporated | 2016-05-23
412f | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | TV | Comcast | Mike Gross, 412-875-1147 | SR 1011-A03 Station 11+00 to Station 18+00 | OH |  | Not Affected | 2016-05-23
413 | -- | 413 | 1404 | 28603 | 2101200602013 | 11 | Allegheny | 70'E.INTER.W/TWP.RD.613 | CHURCH LN | SHAFERS RUN | 02/209 - INDIANA | 40.5812 | -79.9071 | Gas | Peoples Gas Gibsonia | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | Marked. Please see field maps located in the one call folder in sharepoint for this bridge. | UG |  |  | 2016-09-02
414a | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | Wtr | HAMPTON SHALER WATER AUTHORITY | Sam Scarfone, 412-486-4867 | Station 84+00 RT Install Isolation Valve and Station 85+50 RT Install Isolation Valve | UG | 6 | Prior | 2016-05-26
414b | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | Wtr | HAMPTON SHALER WATER AUTHORITY | Sam Scarfone, 412-486-4867 | SR 1013-A17 – Station 84+00 RT and Station 85+50 RT | UG | 6 | RESTRICTIVE | 2016-05-26
414c | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | Wtr | HAMPTON SHALER WATER AUTHORITY | Sam Scarfone, 412-486-4867 | SR 1013-A17 – Station 84+05 to Station 84+45 RT | UG | 6 | Incorporated | 2016-05-26
414d | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SR: 1013, Section A17 - SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 or Robert Layhew, 412-444-3231 | SR 1013, Station 83+00 to Station 87+00 RT | UG | 4 | Coordinated | 2016-05-26
414e | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 1013-A17 – Station 84+00 to Station 86+00 RT | OH |  | Not Affected | 2016-05-26
414f | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | SS | SHALER TOWNSHIP | Timothy Rogers, 412-486-9700 | SR 1013-A17 – Station 84+25 to Station 85+25 LT/RT | UG |  | Not Affected | 2016-05-26
414g | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or Kent Norton, 724-406-4133 | SR 1013-A17 – Station 83+00 to Station 87+00 RT | OH | TV | Not Affected | 2016-05-26
414h | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Ron Ranone, (412) 633-3779 | SR 1013-A17 – Station 83+00 to Station 87+00 RT | OH | Tele | Not Affected | 2016-05-26
415a | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | Wtr | Hampton-Shaler | Sam Scarfone, 412-486-4867 | SR 1013 - Station 701+00 to Station 703+00 | UG | 4 | Not Affected | 2016-03-29
415b | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | SR 1013-A14 - Station 701+00 to Station 703+00 LT | UG | 8 | Coordinated | 2016-03-29
415c | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SR: 1013, Section A14 - SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | SR 1013-A14 - Station 701+00 to Station 703+00 LT | UG | 8 | Coordinated | 2016-03-29
415d | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | Elect | Duquesne | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 1013 - Station 701+00 to Station 703+00 | OH |  | Not Affected | 2016-03-29
415e | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | Comm | Verizon | Deborah D Delia, 412-633-3810 | SR 1013 - Station 701+00 to Station 703+00 | OH | Tele | Not Affected | 2016-03-29
415f | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | Comm | Comcast | Richard Maslen - (412) 999-0590 Kent Norton (412) 352-7045 | SR 1013 - Station 701+00 to Station 703+00 | OH | TV | Not Affected | 2016-03-29
416a | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Shane Moriarty (412) 473-3962 Bob Layhew (724) 444-3231 | SR 1013— Station 86+00 to Station 88+00 | UG | 8 | Coordinated | 2015-09-09
416b | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | SR 1013— Station 86+00 to Station 88+00 | UG | 8 | Coordinated | 2015-09-09
416c | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | Elect | Duquesne | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 1013— Station 86+00 to Station 88+00 | OH |  | Not Affected | 2015-09-09
416d | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | Wtr | Hampton-Shaler | Sam Scarfone, 412-486-4867 | SR 1013 Station 86+50 LT to Station 87+50 LT | UG |  | Prior | 2015-09-09
416e | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | Comm | Consolidated Communications | Gabe White, (412) 443-9832 | SR 1013— Station 86+00 to Station 88+00 | OH | tele | Not Affected | 2015-09-09
416f | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | Comm | Comcast | Rick Moslen, 412-999-0590 | SR 1013— Station 86+00 to Station 88+00 | OH | TV | Not Affected | 2015-09-09
417a | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | DID NOT RESPOND | UG |  |  | 2017-05-22
417b | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | sanitary | DEER CREEK DRAINAGE BASIN AUTHORITY | Chuck Debaldo (412) 913-6684 - chuck@deercreekauthority .com | Marked. | UG |  |  | 2017-05-22
417c | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | wtr | Oakmont Borough Municipal Auth | 412-828-7220 | Marked. | UG |  |  | 2017-05-22
417d | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | Gas | Peoples TWP LLC/TW Phillips | Larry Shane, 724-295-2600, Lawrence.R.Shane@peoples-gas.com | Marked. Gas main running parallel to Little Deer Creek RD that crosses the bridge and there is main coming from the eeast that ties into the main on little deer creek near the bridge. Please see utility map located in the onecall folder for the bridge in sharepoint. The map doesn’t depict individual customer service lines. | UG |  |  | 2017-05-22
418a | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | SS | DEER CREEK DRAINAGE BASIN AUTHORITY | Chuck Debalno (412) 913-6684 - chuck@deercreekauthority .com | SR 1016 - Station 96+35 to Station 98+50 LT | UG |  | Not Affected | 2015-08-28
418b | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | Gas | DOMINION TRANSMISSION | Bradley Buzzard (724) 331-3695 - Bradley.l.buzzard@dom .com or Jonathan Cherry (724) 468-7730 - jonathan.w.cherry@dom .com | SR 1016 - Station 96+35 to Station 98+50 LT | UG |  | Not Affected | 2015-08-28
418c | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 1016-Section A02 Segment/Offset 0080/1980 | OH |  | Prior | 2015-08-28
418d | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | Wtr | MUNICIPAL WATER AUTHORITY OF THE BOROUGH OF OAKMONT | Jim Mccaskey (412) 327-0096 - jfm@oakmontwater.com | SR 1016 - Station 96+89 to Station 98+45 LT | UG |  | Prior | 2015-08-28
418e | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | Comm | Comcast | Rick Moslen, rickmoslen@cable.comcast.com 412-999-0590 or Kent Norton (412) 352-7045 - kentnorton@cable.comcast.com | SR 1016 - Station 97+30 LT | OH | Tele | Coordinated | 2015-08-28
418f | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | Comm | Consolidated | Jeff Hall - (724) 443-9639 - jeff.hall@conso l idated .com | SR 1016 - Station 97+30 LT | OH | TV | Coordinated | 2015-08-28
419a | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | Unk | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Bruce Burtner, (724) 287-2751 or James Barnett 412-290-2421 | SR 1028-Section A11 Segment/Offset 0180/1751 | UG |  | Not Affected | 2015-08-17
419b | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | Elect | WEST PENN POWER COMPANY | Dan Henry 724-838-6126 or Richard Hobbins 724-334-5237 | SR: 1028-A11-Station 270+18 to Station 270+29 | OH |  | CONDITIONAL RESTRICTION | 2015-08-17
419c | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Gary Redondo, 412-237-2293 | SR 1028-Section A11 Segment/Offset 0180/1751 | OH | Tele | Not Affected | 2015-08-17
419d | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | Comm | FAWN-FRAZIER JOINT WATER AUTHORITY | Nick Irvine, 724-884-6562 | SR 1028-Section A11 Segment/Offset 0180/1751 | OH | Tele | Not Affected | 2015-08-17
419e | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | Comm | CONSOLIDATED COMMUNICATIONS OF PA COMPANY, LLC | Harry R Brown, 724 443-9535 or Jeff Hall, 724-443-9639 | SR 1028-Section A11 Segment/Offset 0180/1751 | OH | Tele | Not Affected | 2015-08-17
419f | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or John Radeshak, 724-212-7236 | SR: 1028-A11-Station 270+18 to Station 270+29 | OH | TV | Not Affected | 2015-08-17
420a | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or John Radeshak, 724-212-7236 | SR: 1034-A07-Station 302+75 to Station 305+70 | OH |  | Not Affected | 2015-08-24
420b | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Elect | WEST PENN POWER COMPANY | Dan Henry, 724-838-6126 or Richard Hobbins, 724-334-5237 | SR: 1034-A07-Station 302+75 to Station 305+70 | OH |  | Not Affected | 2015-08-24
420c | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | SR: 1034-A07 | OH |  | Coordinated | 2015-08-24
420d | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | SR: 1034-A07 | OH |  | Coordinated | 2015-08-24
420e | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | SR: 1034-A07 | OH |  | Coordinated | 2015-08-24
420f | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | SR: 1034-A07 | OH |  | Coordinated | 2015-08-24
420g | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | SR: 1034-A07 | OH |  | Coordinated | 2015-08-24
420h | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | wtr | Fawn-Frazier Joint Water Authority | Nick Irvine, 724-681-8208 | SR-1034-Section A04 Segment/Offset 0050/1321 | UG |  | Incorporated | 2015-08-24
420i | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Larry Shane, 412-473-3960 | Station 303+50 to Station 303+85 RT | UG |  | Coordinated | 2015-08-24
421a | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | Gas | PEOPLES NATURAL GAS | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Marked 1/8/15 | UG |  |  | 2016-03-30
421b | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | wtr | Municipal Auth of Westmoreland CO | Don Aguerra, 724-755-5951, daguerra@mawc.org M. Curtis Fontaine, 724-755-5950, fontaine@mawc.org | Marked 1/8/15. Please see field maps located in the one call folder in sharepoint for this bridge. | UG |  |  | 2016-03-30
421c | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines Nearby |  |  |  | 2016-03-30
421d | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | Comm | VERIZON PENNSYLVANIA LLC | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | Conflict. Lines Nearby |  |  |  | 2016-03-30
421e | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2016-03-30
422a | Y | 422 | 1481 | 62174 | 2200101300130 | 11 | Allegheny | AT PANGBURN RD | MONONGAHELA RD | PERRY MILL RUN (ADJACENT CSX) | 02/204 - FORWARD | 40.2516 | -79.9121 | Elect | WEST PENN POWER COMPANY | Nick Ensminger, 304-534-7437 | SR 2001-Section A15 Segment/Offset 0130/0130 | OH |  | Coordinated | 2016-05-23
422b | Y | 422 | 1481 | 62174 | 2200101300130 | 11 | Allegheny | AT PANGBURN RD | MONONGAHELA RD | PERRY MILL RUN (ADJACENT CSX) | 02/204 - FORWARD | 40.2516 | -79.9121 | Comm | Verizon | Deborah D Delia, 412-633-3810, Fred Fraer Jr, f.g.fraer.jr@verizon.com, 412-237-2292 work 412-216-9260 cell | SR 2001-Section A15 Segment/Offset 0130/0130 | OH |  | Coordinated | 2016-05-23
423a | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | Wtr | Pennsylvania American Water Company | Eric R. Beringer, eric.beringer@amwater.com 724-743-3108 | Marked. | UG |  |  | 2016-04-27
423b | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Not Affected | OH |  |  | 2016-04-27
423c | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | Comm | Verizon | Fred Fraer 412-237-2292 Fraer Jr, f.g.fraer.jr@verizon.com, | Not Affected | OH |  |  | 2016-04-27
423d | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com | Not Affected | OH |  |  | 2016-04-27
424a | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | Gas | Columbia Gas of PA Design | Joseph (Joby) Lapkowicz jlapkowicz@nisource.com C: 724-415-9293 O: 724-425-2358 Dominic Tarella, 724-462-3479 dtarella@nisource.com | Joseph (Joby) Lapkowicz jlapkowicz@nisource.com C: 724-415-9293 O: 724-425-2358 Dominic Tarella, 724-462-3479 dtarella@nisource.com | UG |  |  | 2016-04-14
424b | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | sanitary | Elizabeth TWP AUTH | Michael S. Glister, 412-921-4030 x172, mglister@gatewayengineers.com Kurt Todd, 412-921-4030x184, ktodd@gatewayengineers.com Ruthann Omer, 421-921-4030, romer@gatewayengineers.com Gateway Engineers Ed Campbell, (412) 754-1643, Etsa1@comcast.net | Lines should have no affect on the bridge replacement | UG |  |  | 2016-04-14
424c | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-04-14
424d | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | Wtr | Pennsylvania American Water Company | Garret J. Hargenrader, P.E., (814) 943-5214, ghargenrader@gdfengineers.com Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines Nearby | UG |  |  | 2016-04-14
424e | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | Comm | VERIZON PENNSYLVANIA LLC | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | Conflict. Lines Nearby | UG |  |  | 2016-04-14
424f | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby | UG |  |  | 2016-04-14
425a | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | sanitary | Elizabeth TWP AUTH | Michael S. Glister, 412-921-4030 x172, mglister@gatewayengineers.com Kurt Todd, 412-921-4030x184, ktodd@gatewayengineers.com Ed Campbell, (412) 754-1643, Etsa1@comcast.net | Marked | UG |  |  | 2016-04-20
425b | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | Wtr | Pennsylvania American Water CO | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Marked | UG |  |  | 2016-04-20
425c | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Design CONFLICT. Please send plans to Design Department, Peoples Natural Gas Co, 1291 W Main St, Monongahela, PA 15063 | UG |  |  | 2016-04-20
425d | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | gas | Peoples Gas Monongahela Division | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Marked | UG |  |  | 2016-04-20
425e | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines nearby. | OH |  |  | 2016-04-20
425f | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | Comm | Verizon | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | Conflict. Lines nearby. | UG |  |  | 2016-04-20
425g | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines nearby. | OH |  |  | 2016-04-20
426a | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | DID NOT RESPOND | UG |  |  | 2016-07-13
426b | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | Wtr | Pennsylvania American Water CO | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Marked | UG |  |  | 2016-07-13
426c | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Design Conflict. Please send plans to: Design Department Peoples Natural Gas Company LLC 1291 W Main St Monongahela, PA 15063. Marked | UG |  |  | 2016-07-13
426d | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | Comm | ZAYO | John Lynch, 724-850-6241, 724-972-5667 john.lynch@zayo.com | Conflict. Lines Nearby | UG |  |  | 2016-07-13
426e | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Possible Conflict. Did Not Respond | UG |  |  | 2016-07-13
426f | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | Comm | VERIZON PENNSYLVANIA LLC | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | Verizon facilities cross over Rock Run above the bridge in WPP poles 379760 and 10238. No facilities crossing over the bridge(looks like CATV and power off the west side of the bridge) | UG |  |  | 2016-07-13
426g | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Possible Conflict. Did Not Respond | UG |  |  | 2016-07-13
426h | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | ss | Elizabeth TWP AUTH | Michael S. Glister, 412-921-4030 x172, mglister@gatewayengineers.com Ed Campbell, (412) 754-1643, Etsa1@comcast.net | Preliminary review shows no work shall be necessary | UG |  |  | 2016-07-13
427a | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Marked | UG |  |  | 2016-04-20
427b | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines nearby. | OH |  |  | 2016-04-20
427c | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | sanitary | Elizabeth TWP AUTH | Michael S. Glister, 412-921-4030 x172, mglister@gatewayengineers.com Kurt Todd, 412-921-4030x184, ktodd@gatewayengineers.com Ed Campbell, (412) 754-1643, Etsa1@comcast.net | Marked | UG |  |  | 2016-04-20
427d | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Design CONFLICT. Please send plans to Design Department, Peoples Natural Gas Co, 1291 W Main St, Monongahela, PA 15063 | UG |  |  | 2016-04-20
427e | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | Comm | Verizon | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | Conflict. Lines nearby. | OH |  |  | 2016-04-20
427f | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines nearby. | OH |  |  | 2016-04-20
428a | -- | 428 | 1527 | 99670 | 2202200102622 | 11 | Allegheny | 2644'N.E.OF LR02310 | STEWARTSVILLE H RD | BR. LONG RUN | 02/477 - WHITE OAK | 40.3309 | -79.7877 | Gas | Peoples Gas Pittsburgh Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. Gas main runs on the north side of LR 02232 (stewartsville hollow rd) and then crosses to the sout side just west of the bridge and then continues on the south side past the bridge. Please see utility plans located in the onecall folder for the bridge located in sharepoint. | UG |  |  | 2017-05-22
428b | -- | 428 | 1527 | 99670 | 2202200102622 | 11 | Allegheny | 2644'N.E.OF LR02310 | STEWARTSVILLE H RD | BR. LONG RUN | 02/477 - WHITE OAK | 40.3309 | -79.7877 | Wtr | Municipal Auth of Westmoreland Cnty | April Tilson, 724-755-5955, atilson@mawc.org | Marked. There is an 8" DI WM that runs east on stewartsville hollow road from the intersection with tangleview. Does not appear to be in conflict with project. Please see utility map located in the onecall folder for the bridge located on sharepoint. | UG | 8" |  | 2017-05-22
429a | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | Comm | Verizon Pennsylvania LLC | Chuch Bartoles, 724-656-5206 | Conflict. Lines Nearby. Verizon does have underground cable at this location. Verizon does not send out prints, however, you can forward any maps/prints to the local Engineering Office at 15 East Montgomery Place, 2nd Floor, Pittsburgh, Pennsylvania 15212 to the attention of the Drafting Department. | UG |  |  | 2017-02-16
429b | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 |  | Borough of Dravosburg | George Cribbs, 412-401-0833 | DID NOT RESPOND |  |  |  | 2017-02-16
429c | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 1/6/15 | UG |  |  | 2017-02-16
429d | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 |  | United States Steel Corp | Edward McKeever, 412-675-7459 | Marked. 12/30/14 |  |  |  | 2017-02-16
429e | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | wtr | Pennsylvania American Water CO | Gary Eiter, 412-854-7619, Gary.Eiter@amwater.com | Marked. Conflict. Lines Nearby. 8" WM on the east side and an 8" WM on the west side of Pittsburgh and McKeesport Blvd within the project area. There is an 8" WM that ties into the 8" WM on the east side of P&M Blvd that extends south parallel to the RR in a ROW on the west side of the RR. PLease see utility plans located in the onecall folder for the bridge on sharepoint | UG |  |  | 2017-02-16
430a | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | Gas | COLUMBIA GAS OF PA | Dominic Tarella, dtarella@nisource.com 724-462-3479 | Conflict. Lines Nearby. Please see utility map located in onecall folder for bridge in sharepoint. Columbia Gas doesn’t provide info on depths of lines. | UG |  |  | 2017-03-16
430b | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines Nearby. | UG |  |  | 2017-03-16
430c | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | Gas | PEOPLES GAS COMPANY (EQUITABLE) | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked. 1 1/4" pastic high pressure pipe that extends from the west on Streets Run Rd and terminates west of the intersection with Doyle Road. Please see utility plans located in the onecall folder for the bridge on share point. | UG |  |  | 2017-03-16
430d | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com |  | OH |  |  | 2017-03-16
430e | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com |  | OH |  |  | 2017-03-16
430f | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | Comm | Verizon Pennsylvania LLC | Jon Gaunt, 412-237-2290, jon.c.gaunt@verizon.com |  | OH |  |  | 2017-03-16
430g | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com |  | OH |  |  | 2017-03-16
431a | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 or Carl Taylor, 412-258-4616 | SR: 2046-A12- Segment/Offset 0080/0256 | UG |  | Not Affected | 2015-09-09
431b | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 | Wtr | Baldwin Borough | Ann Scott, Secy., telephone 412-882-9600X251 or John Barrett, 412-882-9600X251 | SR: 2046-A12- Segment/Offset 0080/0256 | UG |  | Not Affected | 2015-09-09
431c | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Jon Gaunt, 412-237-2290 | SR: 2046-A12- Segment/Offset 0080/0256 | OH |  | Not Affected | 2015-09-09
431d | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 | Elect | Duquesne | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR: 2046-A12- Segment/Offset 0080/0256 | OH |  | Not Affected | 2015-09-09
431e | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 | Wtr | PENNSYLVANIA AMERICAN WATER COMPANY | Jerry Hankey, 724-463-87069 or Matt Macek, 412-854-7603 | SR: 2046-A12- Segment/Offset 0080/0256 | UG |  | Not Affected | 2015-09-09
431f | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 | Comm | COMCAST CABLE COMMUNICATIONS, INC. | Rick Moslen, 412-999-0590 | SR: 2046-A12- Segment/Offset 0080/0256 | OH |  | Not Affected | 2015-09-09
432a | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked. Please see field maps located in the one call folder in sharepoint for this bridge. 2" and 8" steel HP lines | UG |  |  | 2016-05-06
432b | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | gas | Sunoco Pipeline LP | Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com, 1-888-786-3260, sxldesignreviews@sunocologistics.com | Not Affected | UG |  |  | 2016-05-06
432c | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | storm | West Mifflin Borough | Jim Hess, 412-461–5300 | Clear No Conflict | UG |  |  | 2016-05-06
432d | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-05-06
432g | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | Comm | VERIZON PENNSYLVANIA LLC | Jon Gaunt, 412-237-2290, jon.c.gaunt@verizon.com | DID NOT RESPOND | OH |  |  | 2016-05-06
432g | -- | 432 | 1568 | 74324 | [9 empty] | ss | Brentwood Borough | Dennis Flynn, 724-510-1630, dflynn@gatewayengineers.com, Gateway Engineers George Zboyovsky, 412-884-1500, | Possible Conflict | UG |  |  | 2016-05-06
433a | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | SS | Penn Hills Municipality | Tom O’Grady, 412-798-2171 | SR 2065-A08 - Sta. 25+80 – 29+60 RT/LT | UG |  | CONDITIONAL RESTRICTION | 2016-02-26
433b | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | SS | ALLEGHENY COUNTY SANITARY AUTHORITY (ALCOSAN) | Mr. Dave Boreman, 412-766-4810 | SR 2065-A08 - Sta. 25+80 – 29+60 RT/LT | UG |  | CONDITIONAL RESTRICTION | 2016-02-26
433c | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 or Carl Taylor, (412) 258-4616 | SR 2065-A08 - Sta. 50+90 – 54+50 RT | UG |  | CONDITIONAL RESTRICTION | 2016-02-26
433d | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | Comm | Comcast | Rick Moslen, 412-999-0590 | SR 2065-A08, Station 22+80 to Station 29+60 | OH |  | Not Affected | 2016-02-26
433e | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Peter Zlkoas, (412) 824-0760 | SR 2065-A08 - Sta. 52+25 RT Offset 38 | OH |  | Coordinated | 2016-02-26
433f | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Peter Zlkoas, (412) 824-0760 | SR 2065-A08 - Sta. 52+25 RT Offset 38 | OH |  | Coordinated | 2016-02-26
433g | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | SS | Wilkins Township | Paul Vargo, 412-824-6650 | SR 2065-A08 - Sta. 25+80 – 29+60 RT/LT | UG |  | Protect-In-Place | 2016-02-26
433h | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 2065-A08 - Sta. 52+48 RT Offset 25’ | OH |  | Not Affected | 2016-02-26
433i | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 2065-A08 - Sta. 52+48 RT Offset 25’ | OH |  | Coordinated | 2016-02-26
433j | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 2065-A08 - Sta. 52+48 RT Offset 25’ | OH |  | Coordinated | 2016-02-26
433k | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | SS | Churchill Borough | Craig Robinson, 412-241-7113 | SR 2065-A08 - Sta. 25+80 – 29+60 RT/LT | UG |  | CONDITIONAL RESTRICTION | 2016-02-26
433l | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | SS | Monroeville Municipal Authority | Timothy Little, (412) 856-3304 or Joe Storey, (412) 287-6015 | SR 2065-A08 - Sta. 25+80 – 29+60 RT/LT | UG |  | CONDITIONAL RESTRICTION | 2016-02-26
433m | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | SS | Turtle Creek Borough | Julie Pantalone, 412 824-2500 | SR 2065-A08 - Sta. 25+80 – 29+60 RT/LT | UG |  | CONDITIONAL RESTRICTION | 2016-02-26
434a | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | gas | Peoples Gas Pittsburgh Division | Jerome Vergenes, 724-857-2127, JEROME.P.VERGENES@peoples-gas.com, | Conflict. Lines nearby. | UG |  |  | 2016-04-20
434b | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | gas | Peoples TWP LLC/TW Phillips | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Not Affected. Existing 1.25” People TWP line that is clear of your project as noted | UG | 4" |  | 2016-04-20
434c | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 |  | Plum Borough Municipal Auth | Michael DiGuilio, 412-798-0950, mdigs33@aol.com | Marked | UG |  |  | 2016-04-20
434d | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | sanitary | Allegheny County Dept of Public Works | Steve Smallhoover, 412-350-4005 steve.smallhoover@alleghenycounty.us | Clear No Conflict | UG |  |  | 2016-04-20
434e | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 |  | Plum Borough | Michael DiGuilio, 412-798-0950, mdigs33@aol.com | DID NOT RESPOND | UG |  |  | 2016-04-20
434f | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | Comm | WINDSTREAM | Dave Marshall, David.Marshall@windstream.com | DID NOT RESPOND | OH |  |  | 2016-04-20
434g | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-04-20
434h | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | Comm | Comcast | David Schade, 724-388-1652, David_Schade@cable.comcast.com Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | DID NOT RESPOND | OH |  |  | 2016-04-20
434i | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | Comm | VERIZON PENNSYLVANIA LLC | Gary Redondo, 412-667-8618, gary.redondo@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-04-20
434j | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | Conflict. Lines Nearby | OH |  |  | 2016-04-20
435a | -- | 435 | 1626 | 102648 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 | gas | Peoples Gas (Equitable Gas) | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | Please see map located in the one call folder for the bridge in sharepoint. Transmission main and high pressure main on Logans Ferry Road. | UG | 12 & 6" |  | 2017-07-28
435b | -- | 435 | 1626 | 102648 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 |  | Plum Borough | Bill Binnie, 412-795-6800 x4601 | Did Not Respond |  |  |  | 2017-07-28
435c | -- | 435 | 1626 | 102648 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | Sent map which is located in the one call folder for the bridge in sharepoint. They appear not to be in conflict. |  |  |  | 2017-07-28
435d | -- | 435 | 1626 | 102648 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 | gas | PEOPLES NATURAL GAS COMPANY LLC | Michelle Saxion, 412-208-7239 | Insufficient information. Do not dig. Please see letter and map located in the one call folder for the bridge in sharepoint. Letter says not affected. | UG |  |  | 2017-07-28
436a | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 2118, Station 72+90 Rt., Offset 60 | OH |  | Coordinated | 2015-08-10
436b | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 2118, Station 74+65 Rt., Offset 50 | OH |  | Coordinated | 2015-08-10
436c | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 2118, Station 75+60 Rt., Offset 40 | OH |  | Coordinated | 2015-08-10
436d | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Comm | Comcast | Tim Gazda, Tim_Gazda@cable.comcast.com, 412-875-1388 Rick Moslen, 412-999-0590 | SR 2118, Stations 72+90 Rt., Offset 60 to 75+60 Rt., Offset 40 | OH |  | Coordinated | 2015-08-10
436e | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Gas | Equitrans LP | Chris Baacke 412-395-2685, cbaacke@eqt.com Robert Crites, 724-852-7348 | SR 2118, Section: A02 Segment/Offset 0020/3544 | UG |  | Not Affected | 2015-08-10
436f | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Bart Ryan, telephone: 412-244-2210 | SR 2118, Station 72+60 to Station 73+75 Right | UG |  | Coordinated | 2015-08-10
436g | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Bart Ryan, telephone: 412-244-2210 | SR 2118, Station 72+60 to Station 73+75 Right | UG |  | Coordinated | 2015-08-10
436h | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Comm | Verizon | Deborah D Delia, 412-633-3810 Fred Fraer, telephone: 412-237-2292 | SR 2118, Stations 72+90 Rt., Offset 60 to 75+60 Rt., Offset 40 | OH |  | Coordinated | 2015-08-10
436i | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Unk | Municipal Authority of Westmoreland County | M. Curtis Fontaine, 724-755-5950 | SR 2118, Station 72+60 to Station 73+75 Right/Left | UG |  | Not Affected | 2015-08-10
436j | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 | Unk | Municipal Authority of the City of McKeesport | Michael Majzer, 412-673-8276 | SR 118 Section A02 Segment/Offset 0020/3544 | UG |  | Not Affected | 2015-08-10
437a | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Clear No Conflict | UG |  |  | 2016-08-22
437b | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Clear No Conflict | UG |  |  | 2016-08-22
437c | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | sanitary | Upper St. Clair TWP | Dan Flatz, flatz@twpusc.org, 421-831-9000x275 421-831-9000, yelich@twpusc.com | Marked. | UG |  |  | 2016-08-22
437d | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | DID NOT RESPOND | UG |  |  | 2016-08-22
437e | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | Comm | VERIZON PENNSYLVANIA LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | DID NOT RESPOND | UG |  |  | 2016-08-22
437f | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | DID NOT RESPOND | UG |  |  | 2016-08-22
437g | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | Comm | AT&T | Ford McLean, 412-979-4455, fmclean@att.com | DID NOT RESPOND | UG |  |  | 2016-08-22
438a | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127, 412-473-3960 | SR 3014, Section: A04 Sta. 12+20 – 15+70 LT/RT | UG |  | Not Affected | 2015-08-17
438b | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 | SR 3014, Section: A04 Sta. 12+20 – 14+70 LT/RT | OH |  | Coordinated | 2015-08-17
438c | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | wtr | SOUTH PARK TOWNSHIP | Bruce Beaver, 412-831-7000 | SR 3014, Section: A04 Sta. 12+20 – 14+70 LT/RT | UG |  | Not Affected | 2015-08-17
438d | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | Elect | First Energy Corporation (West Penn Power) | Dan Henry, 724-838-6126 | SR 3014, Section: A04 Sta. 12+20 – 14+70 LT/RT | OH |  | Coordinated | 2015-08-17
438e | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | Comm | COMCAST CABLE COMMUNICATIONS, INC. | Rick Moslen, 412-999-0590 | SR 3014, Section: A04 Sta. 12+20 – 14+70 LT/RT | OH |  | Coordinated | 2015-08-17
438f | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | wtr | PENNSYLVANIA AMERICAN WATER COMPANY | Jay Lucas, 724-873-3653 | SR 3014, Section: A04 Sta. 12+20 – 14+50 LT/RT | UG |  | Incorporated | 2015-08-17
439a | -- | 439 | 1727 | 27386 | 2301800260000 | 11 | Allegheny | 820' S.W. OF SR 3021 | SCHEINBACH RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2661 | -79.9305 | Gas | GUARDIAN INDUSTRIES CORPORATION | Tim Zeuger (Roach and Assoc), twzeuger@roachassoc.com, 412-706-2581 | Main located on Walton Road in project area. There is also an anode bed in the creek to the south of the Walton/Scheinbach intersection. Roach & Associates will be notified before any ground breaking activity begins. | UG |  |  | 2016-07-12
439b | -- | 439 | 1727 | 27386 | 2301800260000 | 11 | Allegheny | 820' S.W. OF SR 3021 | SCHEINBACH RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2661 | -79.9305 | Wtr | Pennsylvania American Water CO | Joe Tewell, joseph.tewell@amwater.com | Marked. | UG |  |  | 2016-07-12
439c | -- | 439 | 1727 | 27386 | 2301800260000 | 11 | Allegheny | 820' S.W. OF SR 3021 | SCHEINBACH RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2661 | -79.9305 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-07-12
439d | -- | 439 | 1727 | 27386 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-12
439e | -- | 439 | 1727 | 27386 | [9 empty] | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-12
440a | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | Gas | GUARDIAN INDUSTRIES CORPORATION | Tim Zeuger (Roach and Assoc), twzeuger@roachassoc.com, 412-706-2581 | 4” steel gas line that is the only feed to Guardian Industries and if that pipe is damaged they will have to rebuild the entire plant. Requests site visit to verify the gas line location / information | UG | 4" |  | 2016-06-22
440b | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 |  | Borough of Jefferson Hills | SHERRY TRBOVICH, 412-655-7735, strbovich@jeffersonhills.net | Marked. | UG |  |  | 2016-06-22
440c | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | Wtr | Pennsylvania American Water CO | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines Nearby. | UG |  |  | 2016-06-22
440d | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | Elect | West Penn Power | Christine Smith, 724-489-3237, smithc@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-06-22
440e | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | Gas | Peoples Gas (Equitable Gas) | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | 8" steel high pressure line on south side of walton road in project area. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2016-06-22
440e | -- | 440 | 1733 | 28136 | [9 empty] | Comm | Verizon Pennsylvania LLC | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | Possible Conflict. Did Not Respond | OH |  |  | 2016-06-22
440e | -- | 440 | 1733 | 28136 | [9 empty] | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-06-22
441a | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | Gas | Columbia Gas of PA | Dominic Tarella, dtarella@nisource.com 724-462-3479 | exposed service line under bridge. line serves and is owned by the customer at 1312 Noblestown Rd. | UG |  |  | 2016-06-14
441b | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines Nearby. Please see field maps located in the one call folder in sharepoint for this bridge. | UG |  |  | 2016-06-14
441c | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | Possible Conflict. Did Not Respond | UG |  |  | 2016-06-14
441d | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | Comm | Verizon Pennsylvania LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | Conflict. Lines Nearby | UG |  |  | 2016-06-14
441e | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Possible Conflict. Did Not Respond | UG |  |  | 2016-06-14
441f | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | sewer | Collier Twp | Jim Nordquist; NIRA Consulting Engineers, Inc. (412) 262-3970, jnordquist@niraengineers.com | Conflict. Lines Nearby | UG |  |  | 2016-06-14
442a | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | gas | COLUMBIA GAS OF PA | Dominic Tarella, dtarella@nisource.com 724-462-3479 | Clear No Conflict | UG |  |  | 2016-04-11
442b | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines Nearby | UG |  |  | 2016-04-11
442c | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | Gas | Peoples Gas Company | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked | UG |  |  | 2016-04-11
442d | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | sanitary | Pittsburgh Water and Sewer Authority | Robert Christian, (412) 255-2579, rchristian@pgh2o.com | Clear No Conflict. Baldwin Borough has a 15” sewer within the work area | UG |  |  | 2016-04-11
442e | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-04-11
442f | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | Comm | Verizon Pennsylvania LLC | Jon Gaunt, 412-237-2290, jon.c.gaunt@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-04-11
442g | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-04-11
442h | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | sanitary | Baldwin Borough | Ann Scott, Secy., telephone 412-882-9600X251 or John Barrett, 412-882-9600X251,jbarrett@baldwinborough.org | Conflict. Lines Nearby | OH |  |  | 2016-04-11
443a | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines nearby. | UG |  |  | 2016-05-25
443b | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | Gas | Peoples Gas Company | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked. 6" steel high pressure from the southwest that terminates at Glass Run Road near bridge. | UG |  |  | 2016-05-25
443c | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | sanitary | Pittsburgh Water and Sewer Authority | Don Waldorf, 412-255-8682, dwaldorf@pgh20.com | Clear No Conflict. PWSA has no facilities located in your proposed box culvert. Baldwin Borough private 18” Dia. Sanitary sewer line that runs through the City of Pgh. at this location | uG |  |  | 2016-05-25
443d | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | sanitary | Baldwin Borough | Ann Scott, Secy., telephone 412-882-9600X251 or John Barrett, 412-882-9600X251, jbarrett@baldwinborough.org | ? | UG |  |  | 2016-05-25
443e | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | gas | Sunoco Pipeline LP | Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com, 1-888-786-3260, sxldesignreviews@sunocologistics.com | Not Affected | UG |  |  | 2016-05-25
443f | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | ? | OH |  |  | 2016-05-25
443g | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | Comm | Verizon Pennsylvania LLC | Jon Gaunt, 412-237-2290, jon.c.gaunt@verizon.com | Clear No Conflict. Verizon has no aerial facilities going over this bridge. Our facilities come from the direction of Rt885 and stop short of the bridge on the pole that provides service to this house | OH |  |  | 2016-05-25
443h | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-05-25
444a | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | uG |  |  | 2016-04-20
444b | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Dennis Rachocki, 814-333-0288, dennis.rachocki@windstream.com | Clear No Conflict | OH |  |  | 2016-04-20
444c | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 |  | Robinson TWP | Anthony Lenze, 412-923-2411 | Clear No Conflict | UG |  |  | 2016-04-20
444d | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 |  | Municipal Auth of Western Allegheny Cnty | Ron Usenic, 412-788-4337 | Clear No Conflict | UG |  |  | 2016-04-20
444e | -- | 444 | 1881 | 89079 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-04-20
445a | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 |  | North Fayette TWP | Robert Grimm, 412-788-4888 | Marked. | UG |  |  | 2017-05-22
445b | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 | Gas | Peoples Gas Hopewell Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. Gas Main on N. Branch Road in project location. Please see utility plans in the onecall folder for the bridge on sharepoint. | UG |  |  | 2017-05-22
445c | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 | Elect | West Penn Power | Heather Buknic, 724-942-5295, Dan Henry, DHENRY2@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-05-22
445d | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 |  | Municipal Auth of Western Allegheny Cnty | Ron Usenic, 412-788-4337 | Marked. | UG |  |  | 2017-05-22
446a | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | Comm | SUNESYS | Mike Coudriet, (412) 462-4561 X 2353 | SR 4017— Station 85+73 RT to Station 84+20 RT | OH |  | Coordinated | 2015-08-10
446b | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | Comm | Verizon | Deborah D Delia, 412-633-3810 | SR 4017— Station 85+73 RT to Station 84+20 RT | OH |  | Coordinated | 2015-08-10
446c | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | Wtr | Hampton-Shaler | Sam Scarfone, 412-486-4867 | SR 4017 - Station 84+10 to Station 85+80 | UG |  | Prior | 2015-08-10
446d | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127, 412-473-3960 | SR 4017 — Station 84+50 to Station 85+75 | UG |  | Prior | 2015-08-10
446e | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127, 412-473-3960 | SR 4017 — Station 84+50 LT to Station 85+75 LT | UG |  | Coordinated | 2015-08-10
446f | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | SR 4017 - Station 85+73 RT to Station 85+25, 50’ RT — Relocate Pole #106750 SR 4017 - Station 84+20 RT to Station 83+70, 28’ RT — Relocate Pole #106751 possible anchor needed | OH |  | Prior | 2015-08-10
447 | -- | 447 | 1974 | 78413 | 2403200902202 | 11 | Allegheny | 419' W OF LR 02090 | FERN HOLLOW RD | BR LITTLE SEWICKLEY CRK | 02/459 - SEWICKLEY HEIGH | 40.5816 | -80.1483 |  | all ug facilities responded clear per one call | [5 empty] | 2016-08-22
447 | -- | 447 | 1974 | 78413 | [9 empty] | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-08-22
447 | -- | 447 | 1974 | 78413 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Gary Redondo, 412-667-8618, gary.redondo@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-08-22
447 | -- | 447 | 1974 | 78413 | [9 empty] | Comm | Comcast | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-08-22
448 | -- | 448 | 1976 | 78414 | 2403600701676 | 11 | Allegheny | @ INTER.TURKEY FOOT ROAD | BIG SEWICKLEY C RD | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.5953 | -80.1949 | wtr | Ambridge Water Authority | Jim Nordquist; NIRA Consulting Engineers, Inc. (412) 262-3970, jnordquist@niraengineers.com Jeff Allen, 724-266-6784, jallen@ambwater.org | Clear No Conflict | UG |  |  | 2016-09-02
448 | -- | 448 | 1976 | 78414 | [9 empty] | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-09-02
448 | -- | 448 | 1976 | 78414 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-09-02
448 | -- | 448 | 1976 | 78414 | [9 empty] | Comm | Comcast | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-09-02
449a | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | wtr | Ambridge Water Authority | Jim Nordquist; NIRA Consulting Engineers, Inc. (412) 262-3970, jnordquist@niraengineers.com Jeff Allen, 724-266-6784, jallen@ambwater.org | Not Affected | UG |  |  | 2016-06-23
449b | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | Gas | Columbia Gas of PA Design | Matt Coyner, (412) 295-5961, mcoyner@nisource.com Steve Scherling, sscherl@nisource.com | Conflict. Lines Nearby. 2" line on camp meeting road and a 4" on big sewickley creek road. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2016-06-23
449c | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | Comm | Comcast | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-06-23
449d | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-06-23
449e | -- | 449 | 1980 | 78416 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-06-23
450a | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | wtr | Ambridge Water Authority | Jim Nordquist; NIRA Consulting Engineers, Inc. (412) 262-3970, jnordquist@niraengineers.com Jeff Allen, 724-266-6784, jallen@ambwater.org | Marked. Phone Call 8/10. 8" High Pressure close to wingwalls | UG |  |  | 2016-04-20
450b | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | sanitary | Economy Borough Municipal Auth | Jim Skonieczny, 724-869-3201, gymsko10@gmail.com | voice message - main sewer line runs north of bridge marked by mh (16' deep) in parking lot (address 2010) then runs 95' diagonal across street to mh (11' deep) located near house (address 2009) | UG |  |  | 2016-04-20
450c | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | gas | Columbia Gas of PA Design | Matt Coyner, (412) 295-5961, mcoyner@nisource.com Steve Scherling, sscherl@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2016-04-20
450d | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-04-20
450e | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | Comm | Comcast | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-04-20
450f | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | Comm | Verizon Pennsylvania LLC | Mike Carothers, 412-496-1288, mdc1948@verizon.net | Conflict. Lines Nearby | OH |  |  | 2016-04-20
451a | -- | 451 | 3599 | 70804 | 4016803300983 | 11 | Beaver | 100'N.OF SR 4034 | FAIRVIEW RD | UPPER DRY RUN | 04/430 - OHIOVILLE | 40.6602 | -80.4773 |  | Ohioville Borough Municipal Authority | 724-643-6712, 146 Fairlane Dr Industry PA 15052 | Field Marked. | UG |  |  | 2017-06-06
451b | -- | 451 | 3599 | 70804 | 4016803300983 | 11 | Beaver | 100'N.OF SR 4034 | FAIRVIEW RD | UPPER DRY RUN | 04/430 - OHIOVILLE | 40.6602 | -80.4773 | Gas | PEOPLES NATURAL GAS COMPANY LLC | Michael Fontana, 724-857-2176 | Field Marked. Please see letter and map located in the one call folder for the bridge in sharepoint. High pressure line west of Fairview Road | UG |  |  | 2017-06-06
452 | -- | 452 | 3602 | 28944 | 4016805001748 | 11 | Beaver | .4 MI.SW OF TWP.RD.603 | Tuscarawas Road | PAINTERS RUN | 04/217 - SOUTH BEAVER | 40.784 | -80.4542 |  | all facilities responded clear per one call | [5 empty] | 2017-05-22
453a | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matt Hovis, (814)871-8662, HovisM@natfuel.com James Kennedy, 716-857-7368, kennedyj@natfuel.com | Design Conflict. Please send plans to: James Kennedy National Fule Gas 6363 Main St Williamsville, NY 14221. Please see field maps located in the one call folder in share point for the bridge. PLEASE NOTE THAT NAT GAS HAS A HIGH PRESSURE TRANSMISSION LINE (SHOWN IN RED ON MAP) IN THE AREA OF CONSTRUCTION. CONTACT NATIONAL FUEL TO ARRANGE FOR MONITORING DURING ANY EXCAVATION NEAR OUR HIGH PRESSURE TRANSMISSION LINE. Also, gas services are in the area but not shown on the attached map. | UG |  |  | 2016-04-20
453b | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | Comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com | Conflict. Lines Nearby. | OH |  |  | 2016-04-20
453c | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | gas | Columbia Gas of PA Design | Matt Coyner, (412) 295-5961, mcoyner@nisource.com Dominic Tarella, dtarella@nisource.com 724-462-3479 | Marked. | UG |  |  | 2016-04-20
453d | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | gas | Columbia Gas Transmission Ellwood | Ken Houston, 724-858-7676, kphouston@nisource.com | Design Conflict. Please send plans to: Ken Houston Columbia Gas Transmission LLC 315 Shady Rest Rd Ellwood City PA 16117 We will need the drawing or plans for the project. Method of demolition? CPG has a high pressure 20 inch line that crosses Chapel Drive then parallels the road and bridge replacement project. Please see google image located in the one call folder in share point for the bridge. | UG |  |  | 2016-04-20
453e | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | wtr | North Sewickley TWP Water Auth | John M. Shannon, P.E., PMP [O] 412-375-3076 ¦ [M] 412-304-7230 jshannon@mbakerintl.com John Conner, 724-601-2581, johnbconner@zoominternet.net | Marked | UG |  |  | 2016-04-20
453f | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Conflict. Lines Nearby. | UG |  |  | 2016-04-20
453g | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | Comm | Verizon | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Conflict. Lines Nearby. | OH |  |  | 2016-04-20
454a | -- | 454 | 3654 | 29083 | 4101400700193 | 11 | Beaver | 100'NORTHEAST OF PIKE | WISE'S GROVE RD | BRUSH CREEK | 04/210 - MARION | 40.7723 | -80.2369 | Comm | ARMSTRONG | William Norris, 724-452-5213 | Conflict. Lines Nearby. |  |  |  | 2017-05-11
454b | -- | 454 | 3654 | 29083 | 4101400700193 | 11 | Beaver | 100'NORTHEAST OF PIKE | WISE'S GROVE RD | BRUSH CREEK | 04/210 - MARION | 40.7723 | -80.2369 | Wtr | North Sewickley TWP Water Auth | Ken Douglass, 724-846-7480 | Marked. 2/6/15 | UG |  |  | 2017-05-11
454c | -- | 454 | 3654 | 29083 | 4101400700193 | 11 | Beaver | 100'NORTHEAST OF PIKE | WISE'S GROVE RD | BRUSH CREEK | 04/210 - MARION | 40.7723 | -80.2369 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com | DID NOT RESPOND through onecall. Submitted a utility plan located in the onecall folder for the bridge in sharepoint. | OH |  |  | 2017-05-11
455a | -- | 455 | 3693 | 69069 | 4300500800933 | 11 | Beaver | @ INTER.W/TWP.RD.491 | CHAPEL RD | MOON RUN | 04/202 - CENTER | 40.6718 | -80.294 | sanitary | Center TWP Sanitary Auth | Robert Martini, 724) 774–0326, martini@ctsapa.us | Marked | UG |  |  | 2016-08-18
455b | -- | 455 | 3693 | 69069 | 4300500800933 | 11 | Beaver | @ INTER.W/TWP.RD.491 | CHAPEL RD | MOON RUN | 04/202 - CENTER | 40.6718 | -80.294 | Wtr | Center TWP Water Auth | NedMitrovich, P.E 412-264-4400, nmitrovich@lsse.com Bill Dicioccio, dicioccio@Verizon.net Mrs. Verna Dugan, 724–774–7960, verna@ctwa.us | Conflict. Lines Nearby | UG |  |  | 2016-08-18
455c | -- | 455 | 3693 | 69069 | [9 empty] | Gas | Columbia Gas of PA Design | Matt Coyner, (412) 295-5961, mcoyner@nisource.com Steve Scherling, sscherl@nisource.com | Conflict. Lines Nearby |  |  |  | 2016-08-18
455d | -- | 455 | 3693 | 69069 | [9 empty] | Elect | Duquesne Light Company | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | ? |  |  |  | 2016-08-18
455e | -- | 455 | 3693 | 69069 | [9 empty] | Comm | Verizon | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Conflict. Lines Nearby |  |  |  | 2016-08-18
455f | -- | 455 | 3693 | 69069 | [9 empty] | Comm | Comcast | Dave Tatarek, David_Tatarek@cable.comcast.com Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby |  |  |  | 2016-08-18
455g | -- | 455 | 3693 | 69069 | [9 empty] | Comm | SUNESYS | Joe Pankuch, 412.901.6156, jpankuch@sunesys.com Aaron Phillips, 412.779.5277 APhillips@sunesys.com | Conflict. Lines Nearby |  |  |  | 2016-08-18
455h | -- | 455 | 3693 | 69069 | [9 empty] | Comm | ZAYO | John Lynch, 724-850-6241, 724-972-5667 john.lynch@zayo.com | Clear No Conflict |  |  |  | 2016-08-18
455i | -- | 455 | 3693 | 69069 | [9 empty] | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | Conflict. Lines Nearby |  |  |  | 2016-08-18
455j | -- | 455 | 3693 | 69069 | [16 empty] | 2016-08-18
456a | -- | 456 | 3695 | 67378 | 4300900600000 | 11 | Beaver | 0.5 MI.SOUTH OF SR 3007 | KANE RD | TRAMP MILL RUN | 04/103 - HOPEWELL | 40.5944 | -80.28 | Wtr | Creswell Heights Joint Auth | George McElhaney, 724-375-6155 | Marked. 2/18/15 | UG |  |  | 2016-08-29
456b | -- | 456 | 3695 | 67378 | 4300900600000 | 11 | Beaver | 0.5 MI.SOUTH OF SR 3007 | KANE RD | TRAMP MILL RUN | 04/103 - HOPEWELL | 40.5944 | -80.28 | Wtr | Hopewell TWP | Jim Somerville, 724-378-1460 | Marked. | UG |  |  | 2016-08-29
457 | -- | 457 | 3717 | 70805 | 4302500701409 | 11 | Beaver | @ INTER. WITH TWP.RD.544 | BOCKTOWN CORK RD | RAREDON RUN | 04/209 - INDEPENDENCE | 40.5417 | -80.3008 |  | all UG facilities responded clear per one call | [5 empty] | 2016-05-20
457a | -- | 457 | 3717 | 70805 | 4302500701409 | 11 | Beaver | @ INTER. WITH TWP.RD.544 | BOCKTOWN CORK RD | RAREDON RUN | 04/209 - INDEPENDENCE | 40.5417 | -80.3008 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | Conflict. Lines Nearby | OH |  |  | 2016-05-20
457b | -- | 457 | 3717 | 70805 | 4302500701409 | 11 | Beaver | @ INTER. WITH TWP.RD.544 | BOCKTOWN CORK RD | RAREDON RUN | 04/209 - INDEPENDENCE | 40.5417 | -80.3008 | Comm | Verizon | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-05-20
457c | -- | 457 | 3717 | 70805 | 4302500701409 | 11 | Beaver | @ INTER. WITH TWP.RD.544 | BOCKTOWN CORK RD | RAREDON RUN | 04/209 - INDEPENDENCE | 40.5417 | -80.3008 | Comm | Comcast | Craig Tacy, 724-503-4362, Craig_Tacy@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-05-20
458a | -- | 458 | 3722 | 70807 | 4302700400000 | 11 | Beaver | .5 MILE NORTH OF SR 168 | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6116 | -80.4874 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | Conflict. Lines Nearby | OH |  |  | 2016-04-18
458b | -- | 458 | 3722 | 70807 | 4302700400000 | 11 | Beaver | .5 MILE NORTH OF SR 168 | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6116 | -80.4874 | Comm | Verizon | Karen McBeth, karen.s.mcbeth@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-04-18
458c | -- | 458 | 3722 | 70807 | 4302700400000 | 11 | Beaver | .5 MILE NORTH OF SR 168 | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6116 | -80.4874 | Comm | Comcast | Craig Tacy, 724-503-4362, Craig_Tacy@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-04-18
459 | -- | 459 | 3723 | 89058 | 4302700460000 | 11 | Beaver | GREENE TWP.-MILL CREEK | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6224 | -80.4971 |  | all facilities responded clear per one call | [5 empty] | 2016-06-08
459a | -- | 459 | 3723 | 89058 | 4302700460000 | 11 | Beaver | GREENE TWP.-MILL CREEK | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6224 | -80.4971 |  | all UG facilities responded clear per one call |  |  | OH |  |  | 2016-06-08
459b | -- | 459 | 3723 | 89058 | 4302700460000 | 11 | Beaver | GREENE TWP.-MILL CREEK | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6224 | -80.4971 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com |  | OH |  |  | 2016-06-08
459c | -- | 459 | 3723 | 89058 | 4302700460000 | 11 | Beaver | GREENE TWP.-MILL CREEK | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6224 | -80.4971 | Comm | Verizon | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com |  | OH |  |  | 2016-06-08
459d | -- | 460 | 3747 | 99793 | 4401201000519 | 11 | Beaver | 200'EAST&UNDER SR 0060 | BRADY RUN RD | SOUTH BRANCH BRADY RUN | 04/201 - BRIGHTON | 40.7235 | -80.367 | Comm | Comcast | Craig Tacy, 724-503-4362, Craig_Tacy@cable.comcast.com |  | OH |  |  | 2016-09-02
460a | -- | 460 | 3747 | 99793 | 4401201000519 | 11 | Beaver | 200'EAST&UNDER SR 0060 | BRADY RUN RD | SOUTH BRANCH BRADY RUN | 04/201 - BRIGHTON | 40.7235 | -80.367 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | DID NOT RESPOND | OH |  |  | 2016-09-02
460b | -- | 460 | 3747 | 99793 | 4401201000519 | 11 | Beaver | 200'EAST&UNDER SR 0060 | BRADY RUN RD | SOUTH BRANCH BRADY RUN | 04/201 - BRIGHTON | 40.7235 | -80.367 | Comm | Verizon | Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | DID NOT RESPOND | OH |  |  | 2016-09-02
460c | -- | 460 | 3747 | 99793 | 4401201000519 | 11 | Beaver | 200'EAST&UNDER SR 0060 | BRADY RUN RD | SOUTH BRANCH BRADY RUN | 04/201 - BRIGHTON | 40.7235 | -80.367 | Comm | Comcast | Dave Tatarek, David_Tatarek@cable.comcast.com Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | Clear No Conflict | OH |  |  | 2016-09-02
460d | -- | 460 | 3747 | 99793 | 4401201000519 | 11 | Beaver | 200'EAST&UNDER SR 0060 | BRADY RUN RD | SOUTH BRANCH BRADY RUN | 04/201 - BRIGHTON | 40.7235 | -80.367 | Comm | WINDSTREAM | Gail Schmitz, Gail.Schmitz@windstream.com | DID NOT RESPOND | OH |  |  | 2016-09-02
461 | -- | 461 | 3749 | 28957 | 4401201100256 | 11 | Beaver | .2 MI. N.E. OF SR 4018 | BRADYS RUN RD | SOUTH BRANCH BRADY'S RUN | 04/201 - BRIGHTON | 40.7245 | -80.3626 |  | all facilities responded clear per one call | [5 empty] | 2017-07-05
462 | -- | 462 | 3750 | 78310 | 4401201500926 | 11 | Beaver | 100 FT WEST OF SR 0051 | BRADYS RUN RD | BRADYS RUN | 04/201 - BRIGHTON | 40.7325 | -80.3365 |  | all facilities responded clear per one call | [5 empty] | 2017-03-27
463a | -- | 463 | 3755 | 99794 | 4401900500000 | 11 | Beaver | 1/2 MI. WEST OF SR 4021 | PARK RD | N.BR.BRADYS RUN | 04/203 - CHIPPEWA | 40.7468 | -80.3856 |  | Beaver Falls Municipal Auth | James Riggio, 724-846-2400, riggio@bfwater.net Sam Aloi, aloi@bfwater.net | Marked. | UG |  |  | 2016-08-08
463b | -- | 463 | 3755 | 99794 | 4401900500000 | 11 | Beaver | 1/2 MI. WEST OF SR 4021 | PARK RD | N.BR.BRADYS RUN | 04/203 - CHIPPEWA | 40.7468 | -80.3856 | sanitary | Bradys Run Sanitary Authority (Formerly Chippewa Twp. Sanitary Authority) | Todd Beatty, 724 846-3820, wwtp@bradysrunsa.com | Marked | UG |  |  | 2016-08-08
463c | -- | 463 | 3755 | 99794 | 4401900500000 | 11 | Beaver | 1/2 MI. WEST OF SR 4021 | PARK RD | N.BR.BRADYS RUN | 04/203 - CHIPPEWA | 40.7468 | -80.3856 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-08-08
463d | -- | 463 | 3755 | 99794 | [9 empty] | Comm | Verizon | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com |  | OH |  |  | 2016-08-08
463e | -- | 463 | 3755 | 99794 | [9 empty] | Comm | Comcast | Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | Clear No Conflict | OH |  |  | 2016-08-08
464 | -- | 464 | 3769 | 78313 | 4403400200000 | 11 | Beaver | 500' WEST OF SR 0068 | WESTWOOD RD | UPPER DRY RUN | 04/430 - OHIOVILLE | 40.6606 | -80.4837 | Gas | Access Midstream | 607-739-3616 | DID NOT RESPOND | UG |  |  | 2016-08-18
465a | -- | 465 | 22262 | 29374 | 37020800700000 | 11 | Lawrence | 1.5 MI. FROM ST.LINE | PULASKI RD | OVER DEER CREEK | 37/209 - PULASKI | 41.1081 | -80.4759 |  | Pulaski TWP | Frank Taylor, 724-654-6141 | Did Not Respond |  |  |  | 2017-05-26
465b | -- | 465 | 22262 | 29374 | 37020800700000 | 11 | Lawrence | 1.5 MI. FROM ST.LINE | PULASKI RD | OVER DEER CREEK | 37/209 - PULASKI | 41.1081 | -80.4759 |  | Pulaski TWP Municipal Authority | 724-964-8891 x103 | Field Marked. | UG |  |  | 2017-05-26
465c | -- | 465 | 22262 | 29374 | 37020800700000 | 11 | Lawrence | 1.5 MI. FROM ST.LINE | PULASKI RD | OVER DEER CREEK | 37/209 - PULASKI | 41.1081 | -80.4759 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Please see utility map and letter located in the one call folder for the bridge in sharepoint | UG |  |  | 2017-05-26
466 | -- | 466 | 22265 | 78362 | 37020801000000 | 11 | Lawrence | 3000' WEST OF SR 0551 | PULASKI RD | BRANCH DEER CREEK | 37/209 - PULASKI | 41.1062 | -80.4504 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Coordinated | UG |  |  | 2016-06-07
466 | -- | 466 | 22265 | 78362 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-06-07
466 | -- | 466 | 22265 | 78362 | [9 empty] | Comm | Comcast | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-06-07
467a | -- | 467 | 22269 | 29534 | 37020802201379 | 11 | Lawrence | 1/2 MI.WEST / SR0158 | PULASKI RD | MCCLURES RUN | 37/217 - WILMINGTON | 41.1211 | -80.342 | Gas | Peoples Gas Grove City Division | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | Marked. Medium or high pressure line on SR 208. Please see field maps located in the one call folder in sharepoint for this bridge. | UG |  |  | 2017-04-24
467b | -- | 467 | 22269 | 29534 | 37020802201379 | 11 | Lawrence | 1/2 MI.WEST / SR0158 | PULASKI RD | MCCLURES RUN | 37/217 - WILMINGTON | 41.1211 | -80.342 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Did not respond to onecall. Sent letter that they have underground electric facilities in the proposed work construction area. There may also be customer-owned lines or service laterals in the area that they are not aware of. Penn Power maps do not accurately or completely depict customer owned facilities. Please see the utility plans located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-04-24
468 | -- | 468 | 22277 | 78318 | 37022400601429 | 11 | Lawrence | NEAR SR 3016 | YOUNGSTOWN POLA RD | SWAMP | 37/204 - MAHONING | 41.0081 | -80.4686 | Wtr | Aqua Pennsylvania | Dan Conley, 724-981-1200 x50715, DJConley@aquaamerica.com | DID NOT RESPOND | UG |  |  | 2017-04-03
469a | -- | 469 | 22281 | 89094 | 37022401100412 | 11 | Lawrence | @ INTER. WITH SR 4006 | YOUNGSTOWN POLA RD | BRANCH OF MAHONING RIVER | 37/204 - MAHONING | 41.0251 | -80.4328 | Wtr | Aqua Pennsylvania | Dan Conley, 724-981-1200 x50715, DJConley@aquaamerica.com | DID NOT RESPOND | UG |  |  | 2016-07-21
469b | -- | 469 | 22281 | 89094 | 37022401100412 | 11 | Lawrence | @ INTER. WITH SR 4006 | YOUNGSTOWN POLA RD | BRANCH OF MAHONING RIVER | 37/204 - MAHONING | 41.0251 | -80.4328 | Wtr | Pennsylvania American Water CO | Jack Cypher, 412-384-4190 x14 | Marked. | UG |  |  | 2016-07-21
469c | -- | 469 | 22281 | 89094 | 37022401100412 | 11 | Lawrence | @ INTER. WITH SR 4006 | YOUNGSTOWN POLA RD | BRANCH OF MAHONING RIVER | 37/204 - MAHONING | 41.0251 | -80.4328 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Did not respond to onecall. Sent letter that they have underground electric facilities in the proposed work construction area. There may also be customer-owned lines or service laterals in the area that they are not aware of. Penn Power maps do not accurately or completely depict customer owned facilities. Please see the utility plans located in the onecall folder for the bridge in sharepoint. | UG & OH |  |  | 2016-07-21
470a | -- | 470 | 22358 | 78370 | 37095601200542 | 11 | Lawrence | 2 MI.EAST OF SR 0018 | NESHANN0CK FALLS R | NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0894 | -80.289 | Comm | Centurylink formerly Embarq | Leo Hilbert, leo.c.hilbert@centurylink.com | Field Marked. | UG |  |  | 2017-05-22
470b | -- | 470 | 22358 | 78370 | 37095601200542 | 11 | Lawrence | 2 MI.EAST OF SR 0018 | NESHANN0CK FALLS R | NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0894 | -80.289 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Please see utility map and letter located in the one call folder for the bridge in sharepoint | UG |  |  | 2017-05-22
471a | -- | 471 | 22359 | 69103 | 37095601501187 | 11 | Lawrence | 1/2 MI. S.E. OF SR 1005 | NESHANNOCK FALLS R | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0895 | -80.3154 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-05-16
471b | -- | 471 | 22359 | 69103 | 37095601501187 | 11 | Lawrence | 1/2 MI. S.E. OF SR 1005 | NESHANNOCK FALLS R | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0895 | -80.3154 | Comm | Verizon North LLC | Robert Preston, (304) 670-9999, robert.preston@cyient.com Eric Rodrigues, 814 871-2317, eric.rodrigues@verizon.com | Conflict. Lines Nearby | UG & OH |  |  | 2016-05-16
471c | -- | 471 | 22359 | 69103 | 37095601501187 | 11 | Lawrence | 1/2 MI. S.E. OF SR 1005 | NESHANNOCK FALLS R | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0895 | -80.3154 | Comm | Comcast | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-05-16
472 | -- | 472 | 22362 | 78374 | 37095601900000 | 11 | Lawrence | 1 MI.NORTH TWP.RD.601 | NESHANNOCK FALL RD | BR.LITTLE NESHANNOCK CR. | 37/217 - WILMINGTON | 41.1063 | -80.3292 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | DID NOT RESPOND through onecall. Sent letter stating that they are clear other than customer-owned lines or service laterals in the area that they are not aware of. |  |  |  | 2017-03-01
473a | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Please see utility map and letter located in the one call folder for the bridge in sharepoint | UG |  |  | 2017-07-24
473b | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | Gas | Peoples Gas Design Grove City | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | DID NOT RESPOND. | UG |  |  | 2017-07-24
473c | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | Gas | Peoples Gas Grove City Division | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | Marked. Please see utility map located in the one call folder in sharepoint for the bridge. Voice message in one call folder in sharepoint. | UG | 4" |  | 2017-07-24
473d | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | Gas | Laurel Mountain Midstream LLC | Delbert Woloski, delbert.woloski@williams.com | Field Marked. | UG |  |  | 2017-07-24
473e | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | Comm | Verizon North LLC | Michael Geary, michael.geary@verizon.net | Conflict. Lines Nearby. |  |  |  | 2017-07-24
474a | -- | 474 | 22374 | 78378 | 37100900603315 | 11 | Lawrence | 100' SOUTH OF SR 0956 | NESHANNOCK FALL RD | BRANCH NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0892 | -80.2875 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-07-08
474b | -- | 474 | 22374 | 78378 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Eric Rodrigues, 814 871-2317, eric.rodrigues@verizon.com | Clear No Conflict | OH |  |  | 2016-07-08
474c | -- | 474 | 22374 | 78378 | [9 empty] | Comm | ARMSTRONG | Michael Cratty, 724-452-5695, mcratty@agoc.com | DID NOT RESPOND | OH |  |  | 2016-07-08
474d | -- | 474 | 22374 | 78378 | [9 empty] | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-07-08
475a | -- | 475 | 22378 | 99796 | 37101200700000 | 11 | Lawrence | 300'WEST OF TWP.RD.478 | FREW MILL RD. | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9918 | -80.2619 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | DID NOT RESPOND through onecall. Sent letter stating that they are clear other than customer-owned lines or service laterals in the area that they are not aware of. |  |  |  | 2016-07-08
475b | -- | 475 | 22378 | 99796 | 37101200700000 | 11 | Lawrence | 300'WEST OF TWP.RD.478 | FREW MILL RD. | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9918 | -80.2619 |  | Slippery Rock TWP | Jack Armagost, 724-924-2482, srtwp@zoominternt.net | DID NOT RESPOND | UG |  |  | 2016-07-08
476a | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 | Comm | ARMSTRONG | Michael Cratty, 724-452-5695, mcratty@agoc.com | ? | OH |  |  | 2016-08-03
476b | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-08-03
476c | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 |  | Slippery Rock TWP | Slippery Rock Township, Lawrence County 724-794-2482 | ? | UG |  |  | 2016-08-03
476d | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 | Comm | Verizon North LLC | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | ? | OH |  |  | 2016-08-03
477 | -- | 477 | 22396 | 29387 | 37200100802619 | 11 | Lawrence | 100' SOUTH OF SR 2012 | SAVANNAH RD | MCKEE RUN | 37/211 - SHENANGO | 40.9363 | -80.3418 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Conflict. Lines Nearby | UG & OH |  |  | 2016-08-08
477 | -- | 477 | 22396 | 29387 | [9 empty] | Comm | Verizon | Mike Carothers, 412-496-1288, mdc1948@verizon.net Karen McBeth, 724-347-1070 , karen.s.mcbeth@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-08
477 | -- | 477 | 22396 | 29387 | [9 empty] | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-08
478a | -- | 478 | 22416 | 99798 | 37201200103494 | 11 | Lawrence | 100' WEST OF TWP.RD.434 | UNION VALLEY RD | BRANCH OF MCKEE RUN | 37/211 - SHENANGO | 40.9379 | -80.3513 | Wtr | Pennsylvania American Water CO | Bill Lage, 724-654-3706, william.lage@amwater.com | Marked. | UG |  |  | 2016-07-07
478b | -- | 478 | 22416 | 99798 | 37201200103494 | 11 | Lawrence | 100' WEST OF TWP.RD.434 | UNION VALLEY RD | BRANCH OF MCKEE RUN | 37/211 - SHENANGO | 40.9379 | -80.3513 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | DID NOT RESPOND through onecall. Sent letter stating that they are clear other than customer-owned lines or service laterals in the area that they are not aware of. |  |  |  | 2016-07-07
479a | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 |  | Borough of Bessemer | Mary Ann Cardella (secy), 412-667-7061 | Marked. | UG |  |  | 2017-05-11
479b | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 |  | Bessemer Municipal Auth | Mary Ann Cardella (secy), 412-667-7061 | Marked | UG |  |  | 2017-05-11
479c | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Marked. 4" gas main in area of bridge. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG | 4" |  | 2017-05-11
479d | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Did not respond to onecall. Sent letter that they have underground electric facilities in the proposed work construction area. There may also be customer-owned lines or service laterals in the area that they are not aware of. Penn Power maps do not accurately or completely depict customer owned facilities. Please see the utility plans located in the onecall folder for the bridge in sharepoint. | UG & OH |  |  | 2017-05-11
480a | -- | 480 | 22439 | 99797 | 37300300800000 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | STATE LINE RD. | HICKORY CREEK | 37/206 - NORTH BEAVER | 40.9684 | -80.5192 |  | North Beaver TWP | Margaret J. Seltzer (secy), 412-667-7956 | DID NOT RESPOND | UG |  |  | 2016-07-18
480b | -- | 480 | 22439 | 99797 | 37300300800000 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | STATE LINE RD. | HICKORY CREEK | 37/206 - NORTH BEAVER | 40.9684 | -80.5192 |  | North Beaver TWP Muncipal Auth | Margaret J. Seltzer (secy), 412-667-7956 | DID NOT RESPOND | UG |  |  | 2016-07-18
480c | -- | 480 | 22439 | 99797 | 37300300800000 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | STATE LINE RD. | HICKORY CREEK | 37/206 - NORTH BEAVER | 40.9684 | -80.5192 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Did not respond to onecall. Sent letter that they have underground electric facilities in the proposed work construction area. There may also be customer-owned lines or service laterals in the area that they are not aware of. Penn Power maps do not accurately or completely depict customer owned facilities. Please see the utility plans located in the onecall folder for the bridge in sharepoint. | UG & OH |  |  | 2016-07-18
481a | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 |  | North Beaver TWP | Margaret J. Seltzer (secy), 412-667-7956 | DID NOT RESPOND | UG |  |  | 2016-08-18
481b | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 |  | North Beaver TWP Muncipal Auth | Margaret J. Seltzer (secy), 412-667-7956 | DID NOT RESPOND | UG |  |  | 2016-08-18
481c | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | DID NOT RESPOND through onecall. Sent letter stating that they are clear other than customer-owned lines or service laterals in the area that they are not aware of. | OH |  |  | 2016-08-18
481d | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Gail Schmitz, Gail.Schmitz@windstream.com | UG line on Petersburg Road. Please see utility plan located in the onecall folder for the bridge on sharepoint. Windstream responded that it is not in conflict. | UG |  |  | 2016-08-18
482 | -- | 482 | 22455 | 80677 | 37301500201288 | 11 | Lawrence | 1/4 MI W OF SR 2012 | MORAVIA ST | MCKEE RUN | 37/213 - TAYLOR | 40.9376 | -80.3662 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, nickeld@firstenergycorp.com Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | Not Affected | OH |  |  | 2016-05-31
483a | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | gas | Columbia Gas of PA Design | Dominic Tarella, dtarella@nisource.com, 724-462-3479 | Conflict. Lines Nearby. | UG |  |  | 2016-05-05
483b | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | UG |  |  | 2016-05-05
483c | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | Wtr | SOUTHWESTERN PA WATER AUTH | Tim Faddis, 412-260-8294, faddistim@windstream.net | Marked. 12/31/14 | UG |  |  | 2016-05-05
483d | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | Comm | Verizon North LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | DID NOT RESPOND | UG |  |  | 2016-05-05
483e | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | Comm | Atlantic Broadband | Mark Billek, 724-439-1233, MBiLLek@atlanticbb.com | DID NOT RESPOND | UG |  |  | 2016-05-05
483f | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Clear No Conflict | UG |  |  | 2016-05-05
483f | -- | 483 | 16651 | 51503 | [9 empty] | sanitary | REDSTONE TOWNSHIP SEWER AUTHORITY | REDSTONE TOWNSHIP SEWER AUTHORITY REPUBLIC, PA. 154750751 CONTACT: FRANCINE PAVONE EMAIL: redstonesewer@yahoo.com | DID NOT RESPOND | UG |  |  | 2016-05-05
484a | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-05-23
484b | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. | UG |  |  | 2017-05-23
484c | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 | Comm | Comcast Cable of Garrett County MD | Randy Heel, randy_reel@cable.comcast.com | DID NOT RESPOND |  |  |  | 2017-05-23
484d | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 |  | Wharton TWP | Laura Savage (secy), 724-329-8503 | DID NOT RESPOND | UG |  |  | 2017-05-23
485a | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 | wtr | INDIAN CREEK VALLEY WATER AUTHORITY | M. Colburn or R. Kerry Witt, 724-455-2905 | Field Marked. | UG |  |  | 2016-09-19
485b | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 |  | Springfield TWP | Donna J. Kooser (secy), 724-455-3015 | Did not respond. | UG |  |  | 2016-09-19
485c | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 | Comm | VERIZON NORTH | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-09-19
485d | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-09-19
485e | -- | 485 | 16713 | 74174 | [9 empty] | Comm | Laurel Highland Total Communication | Wayne Pritts, 724-455-2409, 724-640-0557, wpritts@lhtot.com Jeff Stough, 724-455-2411, jstough@lhtot.com Rocky Richter, 724-455-0305, rrichter@lhtot.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-09-19
486a | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 | Wtr | INDIAN CREEK VALLEY WATER AUTHORITY | M. Colburn or R. Kerry Witt, 724-455-2905 | Marked. | UG |  |  | 2017-04-10
486b | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 |  | Springfield TWP | Donna J. Kooser (secy), 724-455-3015 | DID NOT RESPOND | UG |  |  | 2017-04-10
486c | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | Conflict. Lines Nearby. |  |  |  | 2017-04-10
486d | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 | Elect | West Penn Power | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | UG |  |  | 2017-04-10
487 | -- | 487 | 16725 | 81961 | 26100700300000 | 12 | Fayette | SALTLICK TOWNSHIP | SR 1007 | CHAMPION CREEK | 26/217 - SALTLICK | 40.0681 | -79.3992 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby |  |  |  | 2017-06-09
488 | -- | 488 | 16736 | 29781 | 26101800100206 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1018 | BUTE RUN | 26/214 - NORTH UNION | 39.9522 | -79.73 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Possible Conflict. Did Not Respond | UG |  |  | 2016-08-05
488 | -- | 488 | 16736 | 29781 | [9 empty] | Comm | VERIZON PENNSYLVANIA LLC | Mike Fowkes, 412-558-5601, michael.g.fowkes@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-05
488 | -- | 488 | 16736 | 29781 | [9 empty] | Comm | Atlantic Broadband | Mark Billek, 724-439-1233, MBiLLek@atlanticbb.com | Conflict. Lines Nearby | OH |  |  | 2016-08-05
489a | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby. 3" line on SR 1031. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2016-08-12
489b | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 |  | City of Connellsville | Antoinette Tesauro, cvstreet@zoominternet.net | DID NOT RESPOND |  |  |  | 2016-08-12
489c | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Not Marked due to no access |  |  |  | 2016-08-12
489d | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 | Not Marked due to no access |  |  |  | 2016-08-12
489e | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | Wtr | Pennsylvania American Water CO | Clayton Wene, clayton.wene@amwater.com | Marked. 2/4/15 | UG |  |  | 2016-08-12
490a | -- | 490 | 16757 | 74345 | 26103100601336 | 12 | Fayette | UPPER TYRONE TOWNSHIP | SR 1031 | GALLEY RUN | 26/222 - UPPER TYRONE | 40.0518 | -79.6059 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 | Conflict. Lines Nearby. |  |  |  | 2017-06-12
490b | -- | 490 | 16757 | 74345 | 26103100601336 | 12 | Fayette | UPPER TYRONE TOWNSHIP | SR 1031 | GALLEY RUN | 26/222 - UPPER TYRONE | 40.0518 | -79.6059 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-06-12
491a | -- | 491 | 16758 | 76009 | 26103100700299 | 12 | Fayette | CONNELLSVILLE & U. TYRONE | SR 1031 | BRANCH OF GALLEY RUN | 26/203 - CONNELLSVILLE | 40.0531 | -79.6047 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 | Conflict. Lines Nearby. |  |  |  | 2017-02-27
491b | -- | 491 | 16758 | 76009 | 26103100700299 | 12 | Fayette | CONNELLSVILLE & U. TYRONE | SR 1031 | BRANCH OF GALLEY RUN | 26/203 - CONNELLSVILLE | 40.0531 | -79.6047 | Elect | West Penn Power | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-02-27
492a | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | Wtr | North Fayette Cnty Municipal Auth | Bob Softcheck, 724-626-1211, nfcmabs@zoominternet.net | Not Affected. Line on SR 51 North side of Rd. email 8/21 | UG |  |  | 2016-05-12
492b | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | Elect | West Penn Power | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-05-12
492c | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | SS | North Union TWP Municipal Services Auth | Kathy Gilbert, nutmsa@atlanticbb.net | Clear No Conflict | UG |  |  | 2016-05-12
492d | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | Comm | VERIZON PENNSYLVANIA LLC | Mike Fowkes, 412-558-5601, michael.g.fowkes@verizon.com | Fiberglass pipes attached to bridge. BOL | OH |  |  | 2016-05-12
492e | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | Comm | Atlantic Broadband | Mark Billek, 724-439-1233, MBiLLek@atlanticbb.com | DID NOT RESPOND | OH |  |  | 2016-05-12
493a | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | Wtr | PLEASANT VALLEY WATER AUTHORITY | Mark Bageant, 412-628-2930, pvwamark@zoominternet.net | (U/G) S.R. 1050, Station 484+30 LT. | UG |  | Incorporated | 2016-03-18
493b | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | Elect | WEST PENN POWER | Frank McLaughlin, 724-626-6239, fmclaug@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | (Aerial) S.R. 1050, Segment 10, Offset 1009. RT. and Offset 1224. RT. | OH |  | Prior | 2016-03-18
493c | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | Comm | ARMSTRONG | Tony Kowalewski, tkowalewski@agoc.com, 724-628-6600 | S.R. 1050, Segment 10, Offset 1009. RT. and Offset 1224. RT. | OH |  | Not Affected | 2016-03-18
493d | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | Comm | Verizon | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | S.R. 1050, Segment 10, Offset 1009. RT. and Offset 1224. RT. | OH |  | Not Affected | 2016-03-18
494 | -- | 494 | 16794 | 90965 | 26105002101302 | 12 | Fayette | SALTLICK TOWNSHIP | SR 1050 | CHAMPION CREEK | 26/217 - SALTLICK | 40.0871 | -79.393 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2016-09-06
495a | -- | 495 | 16806 | 89075 | 26105103000845 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1051 | BRANCH OF BREAKNECK RUN | 26/202 - BULLSKIN | 40.0434 | -79.5299 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 | Conflict. Lines Nearby. |  |  |  | 2016-08-15
495b | -- | 495 | 16806 | 89075 | 26105103000845 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1051 | BRANCH OF BREAKNECK RUN | 26/202 - BULLSKIN | 40.0434 | -79.5299 | wtr | PLEASANT VALLEY WATER AUTHORITY | Mark Bageant, 412-628-2930, pvwamark@zoominternet.net | Field Marked. | UG |  |  | 2016-08-15
496 | -- | 496 | 16827 | 29823 | 26105501401377 | 12 | Fayette | DUNBAR TOWNSHIP | SR 1055 | TUCKER RUN | 26/404 - DUNBAR | 39.9448 | -79.5793 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 | Conflict. Lines Nearby. |  |  |  | 2017-05-30
497a | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | Elect | West Penn Power Company | Scott Clausner, 724-626-6238, sclausn@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-05-23
497b | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | Wtr | INDIAN CREEK VALLEY WATER AUTHORITY | R. Kerry Witt, 724-455-2905, rkwitt@icvwater.org | Marked. 12/26/15 | UG |  |  | 2016-05-23
497c | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | Comm | Verizon Pennsylvania LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | Clear No Conflict | OH |  |  | 2016-05-23
497d | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | Comm | LAUREL HIGHLAND TOTAL COMMUNICATION | Jeff Stough, 724-455-2411, jstough@lhtot.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-05-23
497d | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | Comm | Salsgiver Communications | Amy Lightner, 724 295-1970 ext 116, amyb@salsgiver.com engineering@salsgiver.com | Conflict. Lines Nearby | OH |  |  | 2016-05-23
498a | -- | 498 | 16841 | 29893 | 26105801300864 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/217 - SALTLICK | 40.0744 | -79.3556 | Wtr | West Penn Power Company | Scott Clausner, 724-626-6238, sclausn@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-04-11
498b | -- | 498 | 16841 | 29893 | 26105801300864 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/217 - SALTLICK | 40.0744 | -79.3556 | Elect | INDIAN CREEK VALLEY WATER AUTHORITY | R. Kerry Witt, 724-455-2905, rkwitt@icvwater.org | Marked. 12/26/15 | UG |  |  | 2016-04-11
498c | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | Comm | Verizon Pennsylvania LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | Clear No Conflict | OH |  |  | 2016-05-23
498d | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | Comm | LAUREL HIGHLAND TOTAL COMMUNICATION | Jeff Stough, 724-455-2411, jstough@lhtot.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-05-23
499a | -- | 499 | 16868 | 74184 | 26201500300000 | 12 | Fayette | WHARTON TOWNSHIP | SR 2015 | MEADOW RUN | 26/224 - WHARTON | 39.8234 | -79.5687 | Comm | Comcast Cable of Garrett County MD | Randy Heel, 301-895-4375, randy_reel@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-05
499b | -- | 499 | 16868 | 74184 | 26201500300000 | 12 | Fayette | WHARTON TOWNSHIP | SR 2015 | MEADOW RUN | 26/224 - WHARTON | 39.8234 | -79.5687 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-05
499c | -- | 499 | 16868 | 74184 | 26201500300000 | 12 | Fayette | WHARTON TOWNSHIP | SR 2015 | MEADOW RUN | 26/224 - WHARTON | 39.8234 | -79.5687 | Comm | Qcol Inc | Brian Frazee, 724-329-1121, bfrazee@qcol.net | Possible Conflict. Did Not Respond | ug |  |  | 2016-08-05
499d | -- | 499 | [11 empty] | Comm | VERIZON PENNSYLVANIA LLC | Mike Fowkes, 412-558-5601, michael.g.fowkes@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-05
500 | -- | 500 | 16910 | 74189 | 26301100900000 | 12 | Fayette | NICHOLSON & GERMAN TWPS. | SR 3011 | CATS CREEK | 26/213 - NICHOLSON | 39.8401 | -79.8968 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY |  |  |  | 2016-10-19
501a | -- | 501 | 16922 | 79325 | 26301301700955 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8992 | -79.898 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | CONFLICT. LINES NEARBY. 2" line on SR 3013. Please see utility plan in onecall folder for bridge in sharepoint. | UG |  |  | 2017-05-16
501b | -- | 501 | 16922 | 79325 | 26301301700955 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8992 | -79.898 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY |  |  |  | 2017-05-16
502 | -- | 502 | 16928 | 79328 | 26301301900753 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8926 | -79.914 | Gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | Confirmed through one call that they do not have facilities in area. Sent plans that are located in the onecall folder in sharepoint for the bridge. | UG |  |  | 2017-07-26
503a | -- | 503 | 17052 | 79337 | 26404400201593 | 12 | Fayette | WASHINGTON TOWNSHIP | SR 4044 | DOWNERS RUN | 26/223 - WASHINGTON | 40.1092 | -79.8319 |  | Washington TWP Fayette Cnty | Amy Naulty, 412-223-4200 | Marked. | UG |  |  | 2016-09-06
503b | -- | 503 | 17052 | 79337 | 26404400201593 | 12 | Fayette | WASHINGTON TOWNSHIP | SR 4044 | DOWNERS RUN | 26/223 - WASHINGTON | 40.1092 | -79.8319 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY |  |  |  | 2016-09-06
504a | -- | 504 | 18013 | 79340 | 30001802400670 | 12 | Greene | CENTER TOWNSHIP | SR 0018 | HOUSE RUN | 30/202 - CENTER | 39.8548 | -80.3139 | Comm | Windstream | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | CONFLICT. LINES NEARBY | UG |  |  | 2016-03-25
504b | -- | 504 | 18013 | 79340 | 30001802400670 | 12 | Greene | CENTER TOWNSHIP | SR 0018 | HOUSE RUN | 30/202 - CENTER | 39.8548 | -80.3139 | gas | Columbia Gas of PA Design | Stephanie Hardenstine Cell: 412-584-5015 Office: 412-220-1531 shardenstine@nisource.com | Clear. No Conflict. Abandoned line in area | UG |  |  | 2016-03-25
504c | -- | 504 | 18013 | 79340 | 30001802400670 | 12 | Greene | CENTER TOWNSHIP | SR 0018 | HOUSE RUN | 30/202 - CENTER | 39.8548 | -80.3139 | Elect | WEST PENN POWER | Timothy Blasinsky tblasin@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-03-25
505a | -- | 505 | 18044 | 79342 | 30001805800146 | 12 | Greene | MORRIS TOWNSHIP | SR 0018 | BROWNS CREEK | 30/214 - MORRIS | 39.9689 | -80.317 | Elect | WEST PENN POWER | Timothy Blasinsky, tblasin@firstenergycorp.com Dan Oswald, 724-942-5239, doswald@firstenergycorp.com | CONFLICT. LINES NEARBY | OH |  |  | 2017-02-06
505b | -- | 505 | 18044 | 79342 | 30001805800146 | 12 | Greene | MORRIS TOWNSHIP | SR 0018 | BROWNS CREEK | 30/214 - MORRIS | 39.9689 | -80.317 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona Pilarczyk, Aldona.Pilarczyk@windstream.com, 319-790-6779 | has UG and OH wire in project area. Please see utility map located in the onecall folder for the bridge in sharepoint. | UG & OH |  |  | 2017-02-06
506a | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | Gas | EQUITRANS LP | Dave Spencer, 724-852-7330, dspencer@eqt.com | Conflict. Lines Nearby | UG |  |  | 2016-04-07
506b | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | SS | FRANKLIN TOWNSHIP SEWER AUTHORITY | George Scott, 724-998-6939, 724-627-9728 joyce@ftsasewer.com Craig Brewer, 724-627-8597, 724-350-7409, thebrewcrew@comcast.net Chad Coss, sbc1@windstream.net | Not Affected. Private sewer line under bridge. Parcel 2 Mr. Koratich | UG |  |  | 2016-04-07
506c | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | Gas | Peoples Natural Gas | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Conflict. Lines Nearby | UG |  |  | 2016-04-07
506d | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | Elect | West Penn Power Company | Tim Blasinsky, 724-942-5239, tblasin@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-04-07
506e | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | Wtr | SOUTHWESTERN PA WATER AUTH | Tim Faddis, 412-260-8294, faddistim@windstream.net | Conflict. Lines Nearby | UG |  |  | 2016-04-07
506f | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | Comm | WINDSTREAM | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | DID NOT RESPOND | OH |  |  | 2016-04-07
507a | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | Comm | WINDSTREAM | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-04-14
507b | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | Comm | Verizon | Deborah Delia, (412) 237-2285, deborah.d.delia@verizon.com | Clear. No Conflict | UG |  |  | 2016-04-14
507c | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | SS | DRY TAVERN SEWER AUTHORITY | Eric Harris or Timothy Neil, 724-966-9295, hnhwc@windstream.com | Clear. No Conflict | UG |  |  | 2016-04-14
507d | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | MARKED | UG |  |  | 2016-04-14
507e | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | Elect | West Penn Power Company | Cody Andrews, 724-883-5258, candrews@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | CONFLICT. LINES NEARBY |  |  |  | 2016-04-14
507f | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | Wtr | SOUTHWESTERN PA WATER AUTH | Tim Faddis, 412-260-8294, faddistim@windstream.net Edward J. Mihalsky, 412-260-8945 repshop@verizon.net | CONFLICT. LINES NEARBY | UG |  |  | 2016-04-14
508a | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | Gas | Peoples Gas (Equitable Gas) | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Marked. 12/29/14 | UG |  |  | 2016-05-16
508b | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 |  | Clarksville Borough | Sam Benyi, 724-377-0155, clarksvilleboro@windstream.net | DID NOT RESPOND |  |  |  | 2016-05-16
508c | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | Elect | WEST PENN POWER | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | CONFLICT. LINES NEARBY | OH |  |  | 2016-05-16
508d | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | Wtr | Southwestern PA Water Authority | Tim Faddis, 412-260-8294, faddistim@windstream.net | Marked. 1/7/15 | UG |  |  | 2016-05-16
508e | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | Gas | Columbia Gas of PA Design | Dominic Tarella, dtarella@nisource.com 724-462-3479 | Conflict. Lines Nearby. | UG |  |  | 2016-05-16
508f | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | sanitary | DRY TAVERN SEWER AUTHORITY | Eric Harris, 724-966-9295, hnhwc@windstream.net | Clear No Conflict | UG |  |  | 2016-05-16
508g | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | Comm | WINDSTREAM | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | DID NOT RESPOND | OH |  |  | 2016-05-16
509 | -- | 509 | 18222 | 74203 | 30101400803315 | 12 | Greene | MORGAN TOWNSHIP | SR 1014 | CASTILE RUN | 30/213 - MORGAN | 39.9619 | -80.0536 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-09-06
509 | -- | 509 | [11 empty] | Comm | WINDSTREAM COMMUNICATIONS | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-09-06
510a | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Leigh Anderson, Leigh.Anderson@windstream.com, 501-748-5524 | OH lines near project area. Please see the utility map located in the onecall folder for the bridge in sharepoint. | OH |  |  | 2017-03-16
510b | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 2/2/15. Steel low pressure line on south porter street. Please see utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-03-16
510c | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | sanitary | Franklin TWP Sewer Auth | Chad Coss, sbc1@windstream.net | Marked. 2/3/15 | UG |  |  | 2017-03-16
510d | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Not Marked due to no access |  |  |  | 2017-03-16
510e | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | Marked. 2/9/15 | UG |  |  | 2017-03-16
510f | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 |  | Waynesburg Borough | Bonnie Baily (secy), 724-627-8111, wbgboro@alltel.net | Marked. 2/5/15 | uG |  |  | 2017-03-16
511a | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 14" main crosses garards fort rd just east of bridge. Please see utility map located in the onecall folder for the bridge in sharepoint. | UG | 14" |  | 2016-09-07
511b | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | Marked. | UG |  |  | 2016-09-07
511c | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2016-09-07
511d | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; LaKisha Johnson, Lakisha.Jackson@windstream.com, 501-748-4433 | UG and and OH lines near bridge location. Please see utility map located in the onecall folder for the bridge in sharepoint. | UG & OH |  |  | 2016-09-07
512a | -- | 512 | 18287 | 30289 | 30201600701702 | 12 | Greene | MONOGAHELA TOWNSHIP | SR 2016 | WHITELEY CREEK | 30/212 - MONONGAHELA | 39.8048 | -79.9493 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-03-16
512b | -- | 512 | 18287 | 30289 | 30201600701702 | 12 | Greene | MONOGAHELA TOWNSHIP | SR 2016 | WHITELEY CREEK | 30/212 - MONONGAHELA | 39.8048 | -79.9493 |  | Monongahela TWP | Louis Kovach, 724-943-3034 | DID NOT RESPOND | UG |  |  | 2017-03-16
512c | -- | 512 | 18287 | 30289 | 30201600701702 | 12 | Greene | MONOGAHELA TOWNSHIP | SR 2016 | WHITELEY CREEK | 30/212 - MONONGAHELA | 39.8048 | -79.9493 | Gas | Peoples Gas Monongahela Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 12/29/14 | UG |  |  | 2017-03-16
513a | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | Gas | Equitrans LP | Dave Spencer, 724-852-7330, dspencer@eqt.com | DESIGN CONFLICT. PLEASE SEND PLANS TO: ENGINEERING DEPT EQT PRODUCTION 175 INDUSTRY RD WAYNESBURG PA 15370. Please see the utility map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-04-03
513b | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | sanitary | Franklin TWP Sewer Auth | Carol T. Moore (Secy), 724-627-5473 | Marked. | UG |  |  | 2017-04-03
513c | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. Have steel high pressure pipe located within project area. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-04-03
513d | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | Marked. | UG |  |  | 2017-04-03
513e | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-04-03
514a | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Daniel Piser, 724-852-8301 | DID NOT RESPOND |  |  |  | 2016-11-21
514b | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2016-11-21
514c | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | DID NOT RESPOND | UG |  |  | 2016-11-21
514d | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | Gas | Peoples Gas (Equitable Gas) | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Have 3" and 4" copper high pressure lines within the project area. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG | 3 & 4" |  | 2016-11-21
515a | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | GAS | Columbia Gas Transmission | Ron Johns, rjohns@nisource.com | Design Conflict. Please send plans to: Ron Johns Columbia Gas Transmissions LLC 4360 W Roy Furman HWY Waynesburg PA 15370 | UG |  |  | 2017-03-27
515b | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | Elect | WEST PENN POWER | Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-03-27
515c | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | sanitary | Gilmore TWP | Lisa Gatrell, 724-451-8390, gatrell@windstream.net | DID NOT RESPOND | UG |  |  | 2017-03-27
515d | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | Comm | WINDSTREAM | Bob Dern, 724-852-8227, Robert.Dern@windstream.com Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; | Conflict. Lines Nearby. Please see field maps located in the one call folder in sharepoint for this bridge. | OH |  |  | 2017-03-27
516a | -- | 516 | 18403 | 30231 | 30301300900000 | 12 | Greene | WAYNE TOWNSHIP | SR 3013 | BELLS RUN | 30/219 - WAYNE | 39.7715 | -80.2717 | Elect | West Penn Power Company | Cody Andrews, 724-883-5258, candrews@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Does not appear there would be any conflict | OH |  |  | 2016-04-15
516b | -- | 516 | 18403 | 30231 | 30301300900000 | 12 | Greene | WAYNE TOWNSHIP | SR 3013 | BELLS RUN | 30/219 - WAYNE | 39.7715 | -80.2717 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Conflict. Lines Nearby | UG |  |  | 2016-04-15
516c | -- | 516 | 18403 | 30231 | 30301300900000 | 12 | Greene | WAYNE TOWNSHIP | SR 3013 | BELLS RUN | 30/219 - WAYNE | 39.7715 | -80.2717 | Gas | CNX Gas Corp | JEFF MALCOLM BLUE MOUNTAIN INC J.Malcolm@bluemtninc.com | Possible conflict. Appx 35 ft. south of bridge | UG |  |  | 2016-04-15
516d | -- | 516 | [11 empty] | Comm | WINDSTREAM COMMUNICATIONS | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-04-15
517a | -- | 517 | 34335 | 30975 | 62001900400000 | 12 | Washington | AMWELL TOWNSHIP | SR 0019 | BANE CREEK | 62/201 - AMWELL | 40.024 | -80.2053 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Possible Conflict. Did Not Respond | OH |  |  | 2017-03-13
517b | -- | 517 | 34335 | 30975 | 62001900400000 | 12 | Washington | AMWELL TOWNSHIP | SR 0019 | BANE CREEK | 62/201 - AMWELL | 40.024 | -80.2053 |  | Amwell TWP | Kathleen Wall, amwelltownship@comcast.net | Clear No Conflict | UG |  |  | 2017-03-13
517c | -- | 517 | [11 empty] | Gas | VERIZON PENNSYLVANIA LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2017-03-13
517d | -- | 517 | [11 empty] | Wtr | SOUTHWESTERN PA WATER AUTH | Tim Faddis, 412-260-8294, faddistim@windstream.net | Conflict. Lines Nearby | UG |  |  | 2017-03-13
517e | -- | 517 | [11 empty] | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2017-03-13
517f | -- | 517 | [11 empty] | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | Conflict. Lines Nearby | OH |  |  | 2017-03-13
518a | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 |  | Cecil TWP | Donald A. Gennuso, manager@ceciltownship.com | Clear No Conflict | UG |  |  | 2016-05-23
518b | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 | Gas | Columbia Gas of PA Design | Stephanie Hardenstine, C: 412-584-5015 O: 412-220-1531 shardenstine@nisource.com | Conflict. Lines Nearby | UG |  |  | 2016-05-23
518c | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | Conflict. Lines Nearby | UG |  |  | 2016-05-23
518d | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-05-23
518e | -- | 518 | [11 empty] | Comm | VERIZON PENNSYLVANIA LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-05-23
518f | -- | 518 | [11 empty] | Comm | Comcast | Craig Tacy, 724-503-4362, Craig_Tacy@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-05-23
519a | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 | Wtr | Authority of the Borough of Charleroi | Michael Kalamaras, MichaelKalamaras@abcwater.org | Conflict. Lines Nearby. 12" and 8" DIP WM on the south side of McKean and a 20" CIP WM on the north side of McKean at the bridge. Please see the utility maps located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-02-21
519b | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 |  | Borough of Charleroi | Elaine T. Martinko (secy), 724-483-6011, bcso@charleroiboro.org | DID NOT RESPOND | UG |  |  | 2017-02-21
519c | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby. 6" line on McKean Ave. Please see utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-02-21
519d | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-02-21
520a | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 4" plastic high pressure pipe located in project area. Please see the utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-03-08
520b | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 |  | Finleyville Borough | Sandra Mayak, 724-348-5100 | DID NOT RESPOND. | UG |  |  | 2017-03-08
520c | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-03-08
520d | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | Wtr | Pennsylvania American Water Co | Gary Eiter, 412-854-7619, Gary.Eiter@amwater.com | Conflict. Lines Nearby. 20" DICL WM located near bridge. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-03-08
520e | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | sanitary | Peters Creek Sanitary Auth | Rick Kovack, rickkovach@verizon.net, 724-348-6860 | 24" VCP sanitary line at bridge. Manhole on each side of creek (notated as MH-55 and MH-54a). The pipe is concrete encased under creek. Please see utility as-builts located in the onecall folder for the bridge on sharepoint. | UG |  |  | 2017-03-08
521a | -- | 521 | 34650 | 89048 | 62022100802172 | 12 | Washington | MORRIS TOWNSHIP | SR 0221 | TENMILE CREEK | 62/216 - MORRIS | 40.0344 | -80.2664 | Gas | PEOPLES GAS COMPANY (EQUITABLE) | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Marked. 2" steel high pressure line. Please see the utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2016-08-02
521b | -- | 521 | 34650 | 89048 | 62022100802172 | 12 | Washington | MORRIS TOWNSHIP | SR 0221 | TENMILE CREEK | 62/216 - MORRIS | 40.0344 | -80.2664 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-08-02
521c | -- | 521 | [11 empty] | Comm | Verizon | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-02
522a | -- | 522 | 34673 | 88078 | 62023104300092 | 12 | Washington | BLAINE & INDEPENDENCE TWP | SR 0231 | BRUSH RUN | 62/214 - INDEPENDENCE | 40.1954 | -80.4481 | Gas | Markwest Liberty Midstream and Resources | David Allum 724-579-0440 David.Allum@markwest.com | Design Conflict. Please send plans to: Jeff Stark Markwest Liberty Midstream and Resources 601 Technology Dr Suite 130 Canonsburg PA 15317 | UG |  |  | 2017-03-27
522b | -- | 522 | 34673 | 88078 | 62023104300092 | 12 | Washington | BLAINE & INDEPENDENCE TWP | SR 0231 | BRUSH RUN | 62/214 - INDEPENDENCE | 40.1954 | -80.4481 | Elect | West Penn Power Company | Dave Lucas, 724-942-5239, doswald@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2017-03-27
522c | -- | 522 | 34673 | 88078 | 62023104300092 | 12 | Washington | BLAINE & INDEPENDENCE TWP | SR 0231 | BRUSH RUN | 62/214 - INDEPENDENCE | 40.1954 | -80.4481 | Comm | WINDSTREAM | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | DID NOT RESPOND | OH |  |  | 2017-03-27
522d | -- | 522 | 34673 | 88078 | 62023104300092 | 12 | Washington | BLAINE & INDEPENDENCE TWP | SR 0231 | BRUSH RUN | 62/214 - INDEPENDENCE | 40.1954 | -80.4481 | Comm | ARMSTRONG | Tony Kowalewski tkowalewski@agoc.com, 724-628-6600 | Clear No Conflict | OH |  |  | 2017-03-27
523a | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | gas | CNX Gas Corp | Alex Gower, 304-662-2424, BLUE MOUNTAIN INC a.gower@bluemtninc.com | Clear No Conflict | UG |  |  | 2016-05-23
523b | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | gas | EQUITRANS LP | Jeff Lawrence, 724-627-5176, jjlawrence@eqt.com Robert Crites, 724- 627-5176, rcrites@eqt.com | Conflict. Lines Nearby. 20” steel high pressure transmission pipeline Approximately 70 feet from the bridge that is slated to be replaced. EQT will need to be involved with any field meetings | UG |  |  | 2016-05-23
523c | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | gas | PEOPLES GAS COMPANY (EQUITABLE) | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | Marked. 3" steel high service and 2" copper high service in project area. Please see utility plans located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2016-05-23
523d | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | Elect | West Penn Power Company | Phil Bartolotti, 724-489-3238, jbartol@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-05-23
523e | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | Wtr | West Pike Run TWP | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | Clear No Conflict | UG |  |  | 2016-05-23
523f | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | sanitary | West Pike Run TWP Municipal Auth | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | Clear No Conflict | UG |  |  | 2016-05-23
523g | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | Comm | ARMSTRONG | Tony Kowalewski tkowalewski@agoc.com, 724-628-6600 | Conflict. Lines Nearby. | OH |  |  | 2016-05-23
523h | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | Comm | VERIZON PENNSYLVANIA LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | Conflict. Lines Nearby. | OH |  |  | 2016-05-23
524a | -- | 524 | 34702 | 30813 | 62048102400990 | 12 | Washington | CARROLL TOWNSHIP | SR 0481 | TAYLOR RUN | 62/205 - CARROLL | 40.1804 | -79.9387 | GAS | M3 Appalachia Gathering LLC | Stephen Montgomery, s.montgomery@m3midstream.com | Did Not Respond | UG |  |  | 2017-07-28
524b | -- | 524 | 34702 | 30813 | 62048102400990 | 12 | Washington | CARROLL TOWNSHIP | SR 0481 | TAYLOR RUN | 62/205 - CARROLL | 40.1804 | -79.9387 | gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | Field Marked. Please see map and email located in the onecall folder in sharepoint for the bridge. | UG |  |  | 2017-07-28
525a | -- | 525 | 34847 | 31155 | 62104900520000 | 12 | Washington | SOUTH STRABANE TOWNSHIP | SR 1049 | BR. LITTLE CHARTIERS CK. | 62/227 - SOUTH STRABANE | 40.1717 | -80.1749 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | ? | UG |  |  | 2016-08-05
525b | -- | 525 | 34847 | 31155 | 62104900520000 | 12 | Washington | SOUTH STRABANE TOWNSHIP | SR 1049 | BR. LITTLE CHARTIERS CK. | 62/227 - SOUTH STRABANE | 40.1717 | -80.1749 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | ? | OH |  |  | 2016-08-05
525c | -- | 525 | 34847 | 31155 | 62104900520000 | 12 | Washington | SOUTH STRABANE TOWNSHIP | SR 1049 | BR. LITTLE CHARTIERS CK. | 62/227 - SOUTH STRABANE | 40.1717 | -80.1749 | Comm | VERIZON PENNSYLVANIA LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | ? | OH |  |  | 2016-08-05
525d | -- | 525 | 34847 | 31155 | 62104900520000 | 12 | Washington | SOUTH STRABANE TOWNSHIP | SR 1049 | BR. LITTLE CHARTIERS CK. | 62/227 - SOUTH STRABANE | 40.1717 | -80.1749 | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Clear No Conflict | OH |  |  | 2016-08-05
526a | -- | 526 | 34879 | 98374 | 62200700200048 | 12 | Washington | AMWELL TOWNSHIP | SR 2007 | HORNE RUN | 62/201 - AMWELL | 40.0394 | -80.2224 |  | Amwell TWP | Kathleen Wall, amwelltownship@comcast.net | DID NOT RESPOND | UG |  |  | 2016-08-10
526b | -- | 526 | 34879 | 98374 | 62200700200048 | 12 | Washington | AMWELL TOWNSHIP | SR 2007 | HORNE RUN | 62/201 - AMWELL | 40.0394 | -80.2224 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-08-10
526b | -- | 526 | [11 empty] | Gas | Markwest Liberty Midstream and Resources | David Allum, 724-579-0440 David.Allum@markwest.com | Not Affected | UG |  |  | 2016-08-10
527a | -- | 527 | 34901 | 76072 | 62201102800165 | 12 | Washington | AMWELL TOWNSHIP | SR 2011 | LITTLE TENMILE CREEK | 62/201 - AMWELL | 40.0808 | -80.1777 |  | Amwell TWP | Kathleen Wall, amwelltownship@comcast.net | Did Not Respond |  |  |  | 2017-07-28
527b | -- | 527 | 34901 | 76072 | 62201102800165 | 12 | Washington | AMWELL TOWNSHIP | SR 2011 | LITTLE TENMILE CREEK | 62/201 - AMWELL | 40.0808 | -80.1777 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-07-28
527c | -- | 527 | 34901 | 76072 | 62201102800165 | 12 | Washington | AMWELL TOWNSHIP | SR 2011 | LITTLE TENMILE CREEK | 62/201 - AMWELL | 40.0808 | -80.1777 | gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | Facilities located near one call site. Please see the map located in the one call folder for the bridge in sharepoint. | UG | 8" |  | 2017-07-28
528a | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | sanitary | Marianna West Beth Joint Sewage Auth | Betty Girdish, 724-267-4449, 724-267-4665 | DID NOT RESPOND | UG |  |  | 2016-07-25
528b | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 |  | West Bethlehem TWP | Robert Mercante, 412-267-4665 | DID NOT RESPOND | UG |  |  | 2016-07-25
528c | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby. | OH |  |  | 2016-07-25
528d | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | Comm | FAIRPOINT COMM BENTLEYVILLE | Walter Ziemba, 724-239-1135, WZiemba@fairpoint.com Brad Hart, bhart@fairpoint.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-25
528e | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Anthony Seekins, Anthony.Seekins@windstream.com, 501-748-4447 | DID NOT RESPOND to onecall. Upon further review windstream determined that they werent in conflict | OH |  |  | 2016-07-25
| -- | 529 | 34946 | 89142 | 62202300800032 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | BRANCH OF PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1273 | -79.9895 | [7 empty] | 2017-03-27
530a | -- | 530 | 34949 | 98864 | 62202301100756 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1481 | -79.9792 | Wtr | Authority of the Borough of Charleroi | Michael Kalamaras, MichaelKalamaras@abcwater.org | Conflict. Lines Nearby. 8" HDPE on bentleyville rd. See utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-02-13
530b | -- | 530 | 34949 | 98864 | 62202301100756 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1481 | -79.9792 | Gas | M3 Appalachia Gathering LLC | Stephen Montgomery, s.montgomery@m3midstream.com | DID NOT RESPOND | UG |  |  | 2017-02-13
530c | -- | 530 | 34949 | 98864 | 62202301100756 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1481 | -79.9792 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-02-13
531a | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | gas | CNX Gas Corp | JEFF MALCOLM BLUE MOUNTAIN INC J.Malcolm@bluemtninc.com | Plans for the Bridge are clear of CNX gas | UG |  |  | 2016-04-15
531b | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | Elect | West Penn Power Company | Phil Bartolotti, 724-489-3238, jbartol@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | Clear No Conflict. Closest line is 500 ft east of bridge at Deems Park Road intersection | OH |  |  | 2016-04-15
531c | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | Wtr | West Pike Run TWP | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | Clear No Conflict | UG |  |  | 2016-04-15
531d | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | sanitary | West Pike Run TWP Municipal Auth | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | Clear No Conflict | UG |  |  | 2016-04-15
532a | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | GAS | CNX Gas Corp | Jeff Malcolm, bluemountain5876@gmail.com; Shane Lamkie, 724-954-9067, shane@paproduction.com | DESIGN CONFLICT. PLEASE SEND PLANS TO: JEFF MALCOLM BLUE MOUNTAIN INC 394 KIGER HILL RD 11023 MASON DIXON HIGHWAY MOUNT MORRIS PA 15349 | UG |  |  | 2016-07-18
532b | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 2/9/15. 2" high pressure line on pikes run road. Please see utility plans located in the onecall folder for the bridge in sharepoint | UG |  |  | 2016-07-18
532c | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 |  | West Pike Run TWP | Ruth Dodds, township238@gmail.com | Clear No Conflict | UG |  |  | 2016-07-18
532d | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 |  | West Pike Run TWP Municipal Auth | Ruth Dodds, township238@gmail.com | Clear No Conflict | UG |  |  | 2016-07-18
532e | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-07-18
532f | -- | 532 | [11 empty] | Comm | VERIZON PENNSYLVANIA LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-18
532g | -- | 532 | [11 empty] | Comm | ARMSTRONG | Tony Kowalewski tkowalewski@agoc.com, 724-628-6600 | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-18
532h | -- | 532 | [11 empty] | Comm | FAIRPOINT COMM BENTLEYVILLE | DAVID STOLFER, 724.267.3831, C: 724.350.2086, dstolfer@fairpoint.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-18
533a | -- | 533 | 34985 | 81841 | 62203600500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0523 | -79.9361 | wtr | Pennsylvania American Water CO Brownsville | Greg Hlasnick, greg.hlasnick@amwater.com | Field Marked. | UG |  |  | 2017-05-25
533b | -- | 533 | 34985 | 81841 | 62203600500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0523 | -79.9361 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-05-25
534a | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 |  | Authority of the Borough of Charleroi | CHARLES STIRLING, charlesstirling@abcwater.org Michael Kalamaras, MichaelKalamaras@abcwater.org | Conflict. Lines Nearby | UG |  |  | 2016-07-08
534b | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 | Gas | Columbia Gas of PA Design | Dominic Tarella, dtarella@nisource.com 724-462-3479 | Conflict. Lines Nearby. | UG |  |  | 2016-07-08
534c | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 | Gas | Equitrans LP | Jeff Lawrence, 724-627-5176, jjlawrence@eqt.com Robert Crites, 724- 627-5176, rcrites@eqt.com | Field Marked. | UG |  |  | 2016-07-08
534d | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | CLEAR - NO FACILITIES * 06/03/2015 11:10:03 | UG |  |  | 2016-07-08
534d | -- | 534 | [11 empty] | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-08
534d | -- | 534 | [11 empty] | Comm | VERIZON PENNSYLVANIA LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-08
534d | -- | 534 | [11 empty] | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-07-08
534d | -- | 534 | [11 empty] | Comm | FAIRPOINT COMM BENTLEYVILLE | DAVID STOLFER, 724.267.3831, C: 724.350.2086, dstolfer@fairpoint.com | Clear No Conflict | OH |  |  | 2016-07-08
535 | -- | 535 | 35090 | 30881 | 62303700801515 | 12 | Washington | WEST FINLEY TOWNSHIP | SR 3037 | ROBINSON RUN | 62/230 - WEST FINLEY | 40.0024 | -80.4726 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby |  |  |  | 2016-08-05
536a | -- | 536 | 35103 | 31146 | 62400300701841 | 12 | Washington | HANOVER TOWNSHIP | SR 4003 | KINGS CREEK | 62/212 - HANOVER | 40.4654 | -80.4784 | Elect | West Penn Power | Scott Curcio, 724-743-2021, scurcio@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-05-23
536b | -- | 536 | 35103 | 31146 | 62400300701841 | 12 | Washington | HANOVER TOWNSHIP | SR 4003 | KINGS CREEK | 62/212 - HANOVER | 40.4654 | -80.4784 | Comm | VERIZON PENNSYLVANIA LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | DID NOT RESPOND | OH |  |  | 2016-05-23
537 | -- | 537 | 35171 | 30552 | 62402300200000 | 12 | Washington | CROSS CREEK TOWNSHIP | SR 4023 | NORTH FORK CROSS CREEK | 62/208 - CROSS CREEK | 40.321 | -80.4418 | sanitary | Independence Cross Creek JT SWR Auth | 724-507-6464 | Did Not Respond | UG |  |  | 2017-07-28
538a | -- | 538 | 35178 | 30702 | 62402700100687 | 12 | Washington | CROSS CREEK TOWNSHIP | SR 4027 | NORTH FORK CROSS CREEK | 62/208 - CROSS CREEK | 40.3099 | -80.4451 | Comm | HTC Communications | David Kriebel, htcdig@hky.com | DID NOT RESPOND | OH |  |  | 2016-08-05
538b | -- | 538 | 35178 | 30702 | 62402700100687 | 12 | Washington | CROSS CREEK TOWNSHIP | SR 4027 | NORTH FORK CROSS CREEK | 62/208 - CROSS CREEK | 40.3099 | -80.4451 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-08-05
538c | -- | 538 | [11 empty] | Comm | VERIZON PENNSYLVANIA LLC | Keith Fowler, 724 229-0695, keith.a.fowler@verizon.com | Possible Conflict. Did Not Respond | OH |  |  | 2016-08-05
539 | -- | 539 | 35201 | 81846 | 62403900701840 | 12 | Washington | MOUNT PLEASANT TOWNSHIP | SR 4039 | MILLERS RUN | 62/217 - MOUNT PLEASANT | 40.3266 | -80.2548 |  | all facilities responded clear per one call | [5 empty] | 2017-07-24
540 | -- | 540 | 35227 | 30635 | 62406100401960 | 12 | Washington | HOPEWELL AND BLAINE TWP. | SR 4061 | BRUSH RUN | 62/213 - HOPEWELL | 40.1984 | -80.4077 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby |  |  |  | 2017-03-03
541a | -- | 541 | 35982 | 32045 | 64003103302148 | 12 | Westmoreland | MT. PLEASANT & BULLSKIN T | SR 0031 | JACOBS CREEK | 64/212 - MOUNT PLEASANT | 40.143 | -79.4865 | Comm | ARMSTRONG | Tony Kowalewski tkowalewski@agoc.com, 724-628-6600 | CONFLICT. LINES NEARBY | OH |  |  | 2016-06-16
541b | -- | 541 | 35982 | 32045 | 64003103302148 | 12 | Westmoreland | MT. PLEASANT & BULLSKIN T | SR 0031 | JACOBS CREEK | 64/212 - MOUNT PLEASANT | 40.143 | -79.4865 | Elect | West Penn Power | Scott Curcio, 724-796-1021, scurcio@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-06-16
541c | -- | 541 | 35982 | 32045 | 64003103302148 | 12 | Westmoreland | MT. PLEASANT & BULLSKIN T | SR 0031 | JACOBS CREEK | 64/212 - MOUNT PLEASANT | 40.143 | -79.4865 | Comm | VERIZON PENNSYLVANIA LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | DID NOT RESPOND | OH |  |  | 2016-06-16
542a | Y | 542 | 36002 | 76089 | 64005600501506 | 12 | Westmoreland | CITY OF NEW KENSINGTON | SR 0056 | LITTLE PUCKETA CREEK | 64/305 - NEW KENSINGTON | 40.5714 | -79.7495 | Elect | WEST PENN POWER | Brian Hixenbaugh, 724-334-5236 | SR 0056, Station 10+95 RT | OH |  | Coordinated | 2016-04-06
543a | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | Gas | CNX Gas Corp | Jeff Malcolm, bluemountain5876@gmail.com; Shane Lamkie, 724-954-9067, shane@paproduction.com | Marked. Gas main within project area. Please see the utility map located in the onecall folder for the bridge in sharepoint. Also in folder is CNX construction requirements. | UG |  |  | 2016-09-19
543b | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | gas | DOMINION TRANSMISSION | Bradley Buzzard (724) 331-3695 - Bradley.l.buzzard@dom .com or Jonathan Cherry (724) 468-7730 - jonathan.w.cherry@dom .com | Marked. Please see the utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2016-09-19
543c | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 |  | HEMPFIELD TWP MUNICIPAL AUTHORITY | Donald C. Denezza (secy), 724-834-7232 | Marked. | UG |  |  | 2016-09-19
543d | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | gas | Peoples Gas (Equitable Gas) | Colleen Corona, Rocky Saporito; PE, 412-473-3960, rocky.saporito@peoples-gas.com | Marked. 4" main on SR 0136. Please see the utility map located in the one call folder for the bridge in sharepoint | UG | 4" |  | 2016-09-19
543e | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Guerra, PE, daguerra@mawc.org, 724-755-5800 | Marked. 8" DI WM on SR 0136 and a 20" LJ WM that crosses SR 0136 just west of the RR. Please see the utility map located in the onecall folder for the bridge in sharepoint. Noted that they are currently doing work in Hempfield TWP and that the maps given will be updated. | UG | 8 & 20" |  | 2016-09-19
544a | Y | 544 | 36168 | 31601 | 64025900700000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0259 | COALPIT RUN | 64/210 - LIGONIER | 40.2855 | -79.2348 | NA | NA | NA | SR-Sec: 0259–D11 |  |  | Not Affected | 2015-09-09
545a | Y | 545 | 36207 | 74418 | 64036601720000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 0366 | PUCKETA CREEK | 64/437 - MURRYSVILLE | 40.5188 | -79.6934 | Comm | VERIZON PENNSYLVANIA | Gary Redondo, 412-667-8618 | SR 0366 | OH |  | Coordinated | 2015-08-03
545b | Y | 545 | 36207 | 74418 | 64036601720000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 0366 | PUCKETA CREEK | 64/437 - MURRYSVILLE | 40.5188 | -79.6934 | Comm | COMCAST | David Schade, 724-388-1652 | SR 0366 | OH |  | Coordinated | 2015-08-03
546a | Y | 546 | 36228 | 31826 | 64038102400504 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LINN RUN | 64/210 - LIGONIER | 40.1957 | -79.2407 | Elect | WEST PENN POWER | Brad Herrington, 724-830-2966 | SR 0381, Station 421+30 to Station 423+53, LT | OH |  | Prior | 2016-06-16
546b | Y | 546 | 36228 | 31826 | 64038102400504 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LINN RUN | 64/210 - LIGONIER | 40.1957 | -79.2407 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | SR 0381, Station 421+30 to Station 423+53, LT | OH |  | Prior | 2016-06-16
546c | Y | 546 | 36228 | 31826 | 64038102400504 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LINN RUN | 64/210 - LIGONIER | 40.1957 | -79.2407 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | SR 0381, Station 421+30 to Station 423+53, RT | OH |  | Prior | 2016-06-16
547a | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | Gas | PEOPLES NATURAL GAS | Daniel Andree, 724-832-2859; Melinda Zhukas | SR 0381, Station 48+00 to Station 50+00, LT. | UG | 6 | Prior | 2015-06-22
547b | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | SR 0381, Station 47+00 to Station 51+00, RT | OH |  | Not Affected | 2015-06-22
547c | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | SR 0381, Station 47+00 to Station 51+00, RT | OH |  | Not Affected | 2015-06-22
547d | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | Elect | WEST PENN POWER | Brad Herrington, 724-830-2966 | SR 0381, Station 47+00 to Station 51+00, RT | OH |  | Not Affected | 2015-06-22
548a | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | Wtr | LIGONIER TOWNSHIP MUNICIPAL AUTHORITY | Shane P. Ritenour, 724-238-4138, sritenour@markosky.com Patrick Myers, (724) 238-6428 x107, pmyers@ligoniercamp.org Ligonier Camp & Conference Center Paul Knupp, 724-238-7464, ligtwpmunauth@hotmail.com | Marked. Conlict Lines Nearby Ligonier Twp Municipal has sewer line south of bridge on SR 711. A church camp further north on SR 711 tapped into the Township Sewer Line and church camp’s line is attached to the bridge | UG |  |  | 2016-06-09
548b | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | gas | Peoples Gas Greensburg Division | Carol M. Adams, 724-832-2845, Carol.M.Adams@peoples-gas.com Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | Not Affected. 36” deep. 4” plastic in 6” casing along SR 711. Once it leaves the side of the roadway it’s 7” steel until the other side of the stream where it’s 4” plastic | UG |  |  | 2016-06-09
548c | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | Wtr | Municipal Auth of Westmoreland CO | M. Curtis Fontaine, 724-755-5950, fontaine@mawc.org | Clear No Conflict | UG | 16" |  | 2016-06-09
548d | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | Elect | West Penn Power Company | Brad Herrington, 724-830-2966, bherrin@firstenergycorp.com | Not Affected-Clear No Conflict. West Penn Power facilities are at least 75 feet from the bridge | OH | 16" |  | 2016-06-09
548e | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com | Did Not Respond | OH | 16" |  | 2016-06-09
548f | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | Comm | ZAYO | John Lynch, 724-850-6241, 724-972-5667 john.lynch@zayo.com | Not Affected | OH | 16" |  | 2016-06-09
548g | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601, michael.g.fowkes@verizon.com | Did Not Respond | OH | 16" |  | 2016-06-09
549a | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | Elect | WEST PENN POWER | James Piper, 724-830-2937 | SR 0711, Station 809+07 to Station 811+70, LT | OH |  | Coordinated | 2015-07-20
549b | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | SR 0711, Station 809+07 to Station 811+70, LT | OH |  | Coordinated | 2015-07-20
549c | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | SR 0711, Station 809+90, LT. Remove aerial crossing. Station 810+05 to Station 811+70, RT. | OH |  | Prior | 2015-07-20
549d | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | SR 0711, Station 810+05, RT | OH |  | Prior | 2015-07-20
550a | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Guerra, PE, daguerra@mawc.org, 724-755-5800 | Not Affected 16" PVC WM on SR 0711. | UG |  |  | 2016-04-22
550b | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 |  | Unity Township Municipal Auth | Douglas A. Pike, dougp@utmapa.org | Marked. 1/6/15 | UG |  |  | 2016-04-22
550c | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 | Elect | West Penn Power Company | Brad Herrington, 724-830-2966, bherrin@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-04-22
550d | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 | Comm | Comcast | Brian Woller, 724-219-2571, Brian_Woller@cable.comcast.com | Conflict. Lines Nearby | OH |  |  | 2016-04-22
550e | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 | Comm | VERIZON PENNSYLVANIA LLC | Mike Fowkes, 412-558-5601, michael.g.fowkes@verizon.com | Conflict. Lines Nearby | OH |  |  | 2016-04-22
550f | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 | Comm | Citizens Telephone Company | George Achtiziger, 412-423-4444 | Clear No Conflict | OH |  |  | 2016-04-22
551 | -- | 551 | 36365 | 31972 | 64100400200165 | 12 | Westmoreland | FAIRFIELD TOWNSHIP | SR 1004 | HENDRICKS CREEK | 64/207 - FAIRFIELD | 40.3219 | -79.1307 |  | all facilities responded clear per one call | [5 empty] | 2016-07-25
552a | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | Elect | WEST PENN POWER | James Piper, 724-830-2937 | SR 1017, Station 0+95 to Station 3+49, RT | OH |  | Coordinated | 2015-09-02
552b | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | SR 1017, Station 0+95 to Station 4+10, RT | OH |  | Prior | 2015-09-02
552c | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | SR 1017, Station 0+95 to Station 3+50, RT | OH |  | Prior | 2015-09-02
552d | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | Wtr | LIGONIER TOWNSHIP MUNICIPAL AUTHORITY | Paul Knupp, 724-238-7464 | SR 1017, Station 0+00 to Station 4+00 RT | UG |  | Protect-In-Place | 2015-09-02
553a | -- | 553 | 36389 | 89037 | 64101700600042 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | BRANCH OF HANNAS RUN | 64/210 - LIGONIER | 40.2753 | -79.2044 |  | LIGONIER TOWNSHIP MUNICIPAL AUTHORITY | Mary Lou Johnston, 412 238-9852 | Field Marked. | UG |  |  | 2017-05-04
553b | -- | 553 | 36389 | 89037 | 64101700600042 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | BRANCH OF HANNAS RUN | 64/210 - LIGONIER | 40.2753 | -79.2044 | Wtr | Municipal Auth of Westmoreland Cnty | M. Curtis Fontaine, 724-755-5950 | Please see map located in one call folder for the bridge in sharepoint | UG | 16" |  | 2017-05-04
554a | Y | 554 | 36431 | 31304 | 64103400500000 | 12 | Westmoreland | SALEM TOWNSHIP | SR 1034 | BEAVER RUN | 64/214 - SALEM | 40.4404 | -79.5439 | NA | NA | NA | SR-Sec: 1034–02S |  |  | Not Affected | 2015-08-24
555a | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 | CONFLICT. LINES NEARBY |  |  |  | 2016-08-12
555b | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 |  | Mount Pleasant TWP Municipal Auth | Jaynette Brown (secy), 724-547-6745 | Marked. | UG |  |  | 2016-08-12
555c | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby |  |  |  | 2016-08-12
555d | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 | Wtr | Municipal Auth of Westmoreland Cnty | Engineering Clerk, 724-755-5955 | Marked. 12" WM on SR 2012. Please see utility map located in the one call folder for the bridge in sharepoint. | UG | 12" |  | 2016-08-12
556a | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | Gas | KRIEBEL MINERALS INC | Michele A. Wice 814.226.4160 x 112 MWice@kriebelgas.com or Ron Seich, 814-221-8626 | SR 2013, Station 52+00 to Station 55+00, LT | UG |  | Prior | 2015-10-01
556b | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | Comm | VERIZON PENNSYLVANIA | Jeff Guido, 412-793-7501 | SR 2013, Station 51+25 to Station 54+40, RT | OH |  | Coordinated | 2015-10-01
556c | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | Elect | WEST PENN POWER | Grady Bryant, 724-523-7238 | SR 2013, Station 51+25 to Station 54+40, RT | OH |  | Coordinated | 2015-10-01
556d | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | Comm | COMCAST | Brian Woller, 724-219-2571 | SR 2013, Station 51+25 to Station 54+40, RT | OH |  | Coordinated | 2015-10-01
556e | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | SS | HEMPFIELD TOWNSHIP MUNICIPAL AUTHORITY | Brandon Hassinger, 724-832-0911 | SR 2013, Station 53+60. Existing sanitary sewer will remain | UG |  | Not Affected | 2015-10-01
557a | -- | 557 | 36493 | 79419 | 64202100601976 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2021 | SEWICKLEY CREEK | 64/212 - MOUNT PLEASANT | 40.2137 | -79.4974 | Comm | ARMSTRONG | Tony Kowalewski tkowalewski@agoc.com, 724-628-6600 | Conflict. Lines Nearby. | OH |  |  | 2016-06-16
557b | -- | 557 | 36493 | 79419 | 64202100601976 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2021 | SEWICKLEY CREEK | 64/212 - MOUNT PLEASANT | 40.2137 | -79.4974 | Elect | West Penn Power Company | Brad Herrington, 724-830-2966, bherrin@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby | OH |  |  | 2016-06-16
557c | -- | 557 | 36493 | 79419 | 64202100601976 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2021 | SEWICKLEY CREEK | 64/212 - MOUNT PLEASANT | 40.2137 | -79.4974 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Guerra, PE, daguerra@mawc.org | Clear No Conflict | UG | 4" |  | 2016-06-16
557d | -- | 557 | [11 empty] | Comm | Citizens Telephone Company | Dennis Cutrell, 724-424-2203,724-423-3000, cell 724-244-9166, Dennis.Cutrell@ctzn.net | Conflict. Lines Nearby | OH |  |  | 2016-06-16
557e | -- | 557 | [11 empty] | sanitary | Mount Pleasant TWP Municipal Auth | mptma.com@zoominternet.com, 724.424.5418 | Possible Conflict. Did Not Respond | UG |  |  | 2016-06-16
558a | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | Conflict. Lines Nearby. | UG |  |  | 2017-03-06
558b | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | wtr | City of Jeannette | Edward Antonacci, City Engineer, 724-527-7771, edward.antonacci@verizon.net | Field Marked. | UG |  |  | 2017-03-06
558c | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | sanitary | City of Jeannette Municipal Auth | Robert Bible, Gannett Fleming, Authority Engineer, 724-527-4022 | Field Marked. | UG |  |  | 2017-03-06
558d | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Facilities located near one call site. Please see the map located in the one call folder for the bridge in sharepoint. | UG |  |  | 2017-03-06
558e | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | Wtr | Municipal Auth of Westmoreland Cnty | M. Curtis Fontaine, 724-755-5950 | Please see map located in one call folder for the bridge in sharepoint | UG |  |  | 2017-03-06
559a | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 | Elect | WEST PENN POWER | Robert Holman, 724-523-7238 | SR 4053, Station 4+90, LT | OH |  | Prior | 2015-08-24
559b | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 | Elect | WEST PENN POWER | Robert Holman, 724-523-7238 | SR 4053 | OH |  | Coordinated | 2015-08-24
559c | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 | Comm | Windstream | Jerry Starenchak, 724-733-3333 | SR 4053, Station 4+90 LT | OH |  | Prior | 2015-08-24
559d | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 | Gas | PEOPLES NATURAL GAS | Daniel Andree, 724-832-2859 | SR 4053, Station 3+00 to Station 6+50, RT | UG |  | Prior | 2015-08-24
559e | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 | SS | FRANKLIN TOWNSHIP SANITARY AUTHORITY | Kevin Kaplan, 724-327-1950 | SR 4053, Station 4+90, crossing | UG |  | Protect-In-Place | 2015-08-24
560a | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | Gas | Peoples Gas Design Monongahela | Mary M. Vitalbo-Madden, 724-292-3415 | Design Conflict. Please send plans to: Design Department Peoples Natural Gas Company LLC 1291 W Main St Monongahela, PA 15063 | UG |  |  | 2017-04-24
560b | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | gas | Peoples Gas Monongahela Division | Mary M. Vitalbo-Madden, 724-292-3415 | Conflict. Lines Nearby. | UG |  |  | 2017-04-24
560c | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | sanitary | Rostraver TWP Sewage Authority | 724-930-7667 | Marked. | UG |  |  | 2017-04-24
560d | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | Conflict. Lines Nearby. |  |  |  | 2017-04-24
560e | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | Wtr | Municipal Auth of Westmoreland Cnty | M. Curtis Fontaine, 724-755-5950 | Marked. Please see the utility map located in the onecall folder for the bridge in sharepoint. | UG |  |  | 2017-04-24
561a | -- | 561 | 16920 | 81636 | 26301301601348 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.9017 | -79.8937 | wtr | Southwestern PA Water Authority | Kenneth Frameli, 724-883-2301 | Field Marked. | UG |  |  | 2017-07-24
561b | -- | 561 | 16920 | 81636 | 26301301601348 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.9017 | -79.8937 | Gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | Confirmed through one call that they do not have facilities in area. Sent plans that are located in the onecall folder in sharepoint for the bridge. | UG |  |  | 2017-07-24
562a | -- | 562 | 16923 | 79326 | 26301301701416 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8982 | -79.8993 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | CONFLICT. LINES NEARBY. 2" line on SR 3013. Please see utility plan in onecall folder for bridge in sharepoint. | UG |  |  | 2017-02-24
562b | -- | 562 | 16923 | 79326 | 26301301701416 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8982 | -79.8993 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY |  |  |  | 2017-02-24
563a | -- | 563 | 16930 | 74190 | 26301301901171 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8931 | -79.9153 | gas | Peoples Gas Design Monongahela | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | Design Conflict. Please send plans to: Design Department Peoples Natural Gas Company LLC 1291 W Main St Monongahela PA 15063 | UG |  |  | 2016-09-12
563b | -- | 563 | 16930 | 74190 | 26301301901171 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8931 | -79.9153 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | CONFLICT. LINES NEARBY |  |  |  | 2016-09-12
564 | -- | 564 | 13897 | 102789 | 21203100100187 | 8 | Cumberland | S. of Lisburn on Spangler Mill, mill race (Y.B.) | SR 2031 | MILL RACE | 21/102 - LOWER ALLEN | 40.212 | -76.9072 |  | all facilities responded clear per one call | [5 empty] | 2017-04-17
#N/A
[15 empty] | Fax:330-245-5376 | [5 empty] | #N/A
#N/A
2164 |  | 2171